## Requirements
Requirement ID | Name | Application | Priority | Requirement Type | Requirement Complete Date Planned | Requirement Complete Date Actual | Development Complete Date Planned | Development Complete Date Actual | Deleted | Deleted Date | Deleted Reason
Req 0001 | Req Name 0001 | Application 1 | Med | Functional | 2016-04-06 | 2016-04-20 | 2016-04-23 | 2016-05-11 | No
Req 0002 | Req Name 0002 | Application 1 | Med | Functional | 2016-04-05 | 2016-04-18 | 2016-04-22 | 2016-04-29 | No
Req 0003 | Req Name 0003 | Application 1 | High | Non-Functional | 2016-04-11 | 2016-04-26 | 2016-04-27 | 2016-05-07 | No
Req 0004 | Req Name 0004 | Application 1 | Med | Functional | 2016-04-15 | 2016-04-29 | 2016-05-01 | 2016-05-24 | No
Req 0005 | Req Name 0005 | Application 1 | Low | Functional | 2016-04-29 | 2016-05-08 | 2016-05-16 | 2016-05-31 | Yes | 2016-05-01 | Duplicate
Req 0006 | Req Name 0006 | Application 1 | Low | Non-Functional | 2016-04-10 | 2016-04-22 | 2016-04-27 | 2016-05-11 | No
Req 0007 | Req Name 0007 | Application 1 | Low | Functional | 2016-04-09 | 2016-04-17 | 2016-04-25 | 2016-05-08 | No
Req 0008 | Req Name 0008 | Application 1 | Low | Non-Functional | 2016-04-07 | 2016-04-20 | 2016-04-23 | 2016-05-11 | Yes | 2016-03-28 | Duplicate
Req 0009 | Req Name 0009 | Application 2 | Med | Functional | 2016-04-06 | 2016-04-21 | 2016-04-23 | 2016-05-10 | Yes | 2016-03-29 | Duplicate
Req 0010 | Req Name 0010 | Application 1 | Med | Functional | 2016-04-16 | 2016-04-26 | 2016-05-03 | 2016-05-18 | No
Req 0011 | Req Name 0011 | Application 1 | Med | Non-Functional | 2016-04-10 | 2016-04-18 | 2016-04-26 | 2016-05-10 | Yes | 2016-03-31 | Duplicate
Req 0012 | Req Name 0012 | Application 1 | Low | Functional | 2016-04-04 | 2016-04-16 | 2016-04-20 | 2016-05-02 | Yes | 2016-04-14 | Duplicate
Req 0013 | Req Name 0013 | Application 1 | Med | Non-Functional | 2016-04-04 | 2016-04-19 | 2016-04-21 |  | Yes | 2016-04-16 | Mistake
Req 0014 | Req Name 0014 | Application 1 | Low | Performance | 2016-05-03 | 2016-05-17 | 2016-05-19 |  | No
Req 0015 | Req Name 0015 | Application 1 | High | Functional | 2016-04-05 | 2016-04-12 | 2016-04-22 | 2016-05-06 | No
Req 0016 | Req Name 0016 | Application 1 | Low | Functional | 2016-04-03 | 2016-04-09 | 2016-04-18 | 2016-04-30 | No
Req 0017 | Req Name 0017 | Application 1 | Med | Functional | 2016-04-10 | 2016-04-18 | 2016-04-27 | 2016-05-13 | No
Req 0018 | Req Name 0018 | Application 1 | Low | Functional | 2016-04-06 | 2016-04-15 | 2016-04-21 | 2016-04-30 | No
Req 0019 | Req Name 0019 | Application 2 | High | Functional | 2016-04-03 |  | 2016-04-19 |  | Yes | 2016-04-12 | Duplicate
Req 0020 | Req Name 0020 | Application 1 | Med | Non-Functional | 2016-04-19 | 2016-05-04 | 2016-05-06 |  | No
Req 0021 | Req Name 0021 | Application 2 | Med | Non-Functional | 2016-04-13 | 2016-04-28 | 2016-04-30 | 2016-05-17 | No
Req 0022 | Req Name 0022 | Application 1 | High | Non-Functional | 2016-04-21 | 2016-04-30 | 2016-05-08 | 2016-05-25 | No
Req 0023 | Req Name 0023 | Application 2 | Med | Functional | 2016-04-13 | 2016-04-18 | 2016-04-29 | 2016-05-05 | Yes | 2016-04-12 | Duplicate
Req 0024 | Req Name 0024 | Application 1 | Med | Non-Functional | 2016-04-08 | 2016-04-21 | 2016-04-24 | 2016-05-08 | No
Req 0025 | Req Name 0025 | Application 1 | Med | Functional | 2016-04-11 | 2016-04-20 | 2016-04-29 | 2016-05-09 | No
Req 0026 | Req Name 0026 | Application 2 | Med | Non-Functional | 2016-04-28 | 2016-05-09 | 2016-05-14 |  | No
Req 0027 | Req Name 0027 | Application 1 | Low | Functional | 2016-04-22 | 2016-05-01 | 2016-05-08 | 2016-05-21 | No
Req 0028 | Req Name 0028 | Application 1 | Med | Functional | 2016-04-09 | 2016-04-18 | 2016-04-28 |  | No
Req 0029 | Req Name 0029 | Application 1 | Low | Non-Functional | 2016-04-06 | 2016-04-13 | 2016-04-22 | 2016-05-03 | No
Req 0030 | Req Name 0030 | Application 1 | High | Performance | 2016-04-18 |  | 2016-05-04 |  | No
Req 0031 | Req Name 0031 | Application 1 | Med | Non-Functional | 2016-04-22 | 2016-05-06 | 2016-05-06 | 2016-05-27 | No
Req 0032 | Req Name 0032 | Application 1 | Low | Functional | 2016-04-08 | 2016-04-19 | 2016-04-25 | 2016-05-18 | No
Req 0033 | Req Name 0033 | Application 1 | High | Performance | 2016-04-08 | 2016-04-13 | 2016-04-23 | 2016-05-03 | No
Req 0034 | Req Name 0034 | Application 1 | Med | Non-Functional | 2016-04-16 | 2016-04-21 | 2016-05-03 | 2016-05-13 | No
Req 0035 | Req Name 0035 | Application 1 | Med | Functional | 2016-04-05 | 2016-04-15 | 2016-04-22 | 2016-05-10 | No
Req 0036 | Req Name 0036 | Application 1 | High | Non-Functional | 2016-04-15 |  | 2016-05-01 |  | No
Req 0037 | Req Name 0037 | Application 1 | Low | Non-Functional | 2016-04-03 | 2016-04-11 | 2016-04-19 | 2016-04-19 | Yes | 2016-04-13 | Duplicate
Req 0038 | Req Name 0038 | Application 1 | Low | Non-Functional | 2016-04-04 | 2016-04-09 | 2016-04-19 | 2016-04-26 | No
Req 0039 | Req Name 0039 | Application 1 | High | Functional | 2016-04-20 |  | 2016-05-06 |  | No
Req 0040 | Req Name 0040 | Application 1 | Low | Non-Functional | 2016-04-13 | 2016-04-21 | 2016-04-28 | 2016-05-12 | No
Req 0041 | Req Name 0041 | Application 1 | High | Non-Functional | 2016-04-29 | 2016-05-05 | 2016-05-15 | 2016-05-23 | No
Req 0042 | Req Name 0042 | Application 1 | Med | Functional | 2016-04-10 | 2016-04-18 | 2016-04-27 | 2016-05-09 | No
Req 0043 | Req Name 0043 | Application 1 | High | Functional | 2016-04-08 | 2016-04-13 | 2016-04-25 | 2016-05-01 | No
Req 0044 | Req Name 0044 | Application 1 | Med | Functional | 2016-04-13 | 2016-04-24 | 2016-04-29 | 2016-05-15 | No
Req 0045 | Req Name 0045 | Application 2 | Med | Functional | 2016-04-15 | 2016-04-22 | 2016-05-01 |  | No
Req 0046 | Req Name 0046 | Application 1 | Med | Non-Functional | 2016-04-01 | 2016-04-20 | 2016-04-18 | 2016-05-09 | Yes | 2016-04-14 | Duplicate
Req 0047 | Req Name 0047 | Application 1 | Med | Non-Functional | 2016-04-05 | 2016-04-11 | 2016-04-24 | 2016-05-02 | No
Req 0048 | Req Name 0048 | Application 1 | High | Non-Functional | 2016-04-23 | 2016-04-28 | 2016-05-09 |  | No
Req 0049 | Req Name 0049 | Application 1 | High | Performance | 2016-04-15 | 2016-04-24 | 2016-04-30 | 2016-05-10 | No
Req 0050 | Req Name 0050 | Application 1 | High | Non-Functional | 2016-04-17 | 2016-04-29 | 2016-05-05 | 2016-05-21 | No
Req 0051 | Req Name 0051 | Application 1 | Med | Functional | 2016-04-30 | 2016-05-04 | 2016-05-17 | 2016-05-28 | No
Req 0052 | Req Name 0052 | Application 1 | Med | Functional | 2016-04-20 | 2016-04-28 | 2016-05-06 | 2016-05-17 | No
Req 0053 | Req Name 0053 | Application 1 | Med | Performance | 2016-04-02 | 2016-04-11 | 2016-04-18 | 2016-04-25 | No
Req 0054 | Req Name 0054 | Application 1 | Med | Functional | 2016-04-02 |  | 2016-04-17 |  | No
Req 0055 | Req Name 0055 | Application 1 | Med | Non-Functional | 2016-05-06 | 2016-05-15 | 2016-05-22 | 2016-06-06 | No
Req 0056 | Req Name 0056 | Application 1 | High | Non-Functional | 2016-04-16 |  | 2016-05-02 |  | No
Req 0057 | Req Name 0057 | Application 1 | Low | Functional | 2016-04-11 | 2016-04-20 | 2016-04-28 | 2016-05-09 | No
Req 0058 | Req Name 0058 | Application 1 | Med | Non-Functional | 2016-04-05 | 2016-04-11 | 2016-04-23 |  | Yes | 2016-04-19 | Duplicate
Req 0059 | Req Name 0059 | Application 1 | High | Functional | 2016-04-16 | 2016-04-30 | 2016-05-03 |  | No
Req 0060 | Req Name 0060 | Application 2 | Med | Non-Functional | 2016-04-20 | 2016-04-26 | 2016-05-07 | 2016-05-16 | Yes | 2016-04-10 | Duplicate
Req 0061 | Req Name 0061 | Application 1 | Med | Functional | 2016-04-19 | 2016-05-01 | 2016-05-05 | 2016-05-20 | No
Req 0062 | Req Name 0062 | Application 1 | Med | Non-Functional | 2016-04-24 | 2016-05-11 | 2016-05-10 | 2016-05-28 | No
Req 0063 | Req Name 0063 | Application 1 | Med | Non-Functional | 2016-04-23 | 2016-04-30 | 2016-05-10 | 2016-05-17 | Yes | 2016-04-26 | Duplicate
Req 0064 | Req Name 0064 | Application 1 | Med | Functional | 2016-04-13 | 2016-04-22 | 2016-04-28 | 2016-05-02 | No
Req 0065 | Req Name 0065 | Application 2 | Med | Functional | 2016-04-11 | 2016-04-25 | 2016-04-29 | 2016-05-11 | No
Req 0066 | Req Name 0066 | Application 1 | Med | Non-Functional | 2016-04-03 |  | 2016-04-20 |  | No
Req 0067 | Req Name 0067 | Application 1 | High | Non-Functional | 2016-04-19 | 2016-05-03 | 2016-05-04 | 2016-05-21 | No
Req 0068 | Req Name 0068 | Application 1 | High | Functional | 2016-04-25 | 2016-05-01 | 2016-05-11 | 2016-05-31 | No
Req 0069 | Req Name 0069 | Application 1 | Med | Functional | 2016-04-28 | 2016-05-03 | 2016-05-14 |  | No
Req 0070 | Req Name 0070 | Application 1 | High | Non-Functional | 2016-04-05 | 2016-04-14 | 2016-04-21 | 2016-04-30 | Yes | 2016-04-20 | Duplicate
Req 0071 | Req Name 0071 | Application 1 | High | Functional | 2016-04-09 | 2016-04-21 | 2016-04-25 | 2016-05-06 | No
Req 0072 | Req Name 0072 | Application 1 | Med | Functional | 2016-05-07 | 2016-05-12 | 2016-05-25 |  | No
Req 0073 | Req Name 0073 | Application 1 | Med | Non-Functional | 2016-04-02 | 2016-04-09 | 2016-04-20 |  | Yes | 2016-04-10 | Duplicate
Req 0074 | Req Name 0074 | Application 1 | High | Performance | 2016-04-01 | 2016-04-18 | 2016-04-18 | 2016-05-09 | No
Req 0075 | Req Name 0075 | Application 2 | Med | Functional | 2016-04-11 |  | 2016-04-27 |  | Yes | 2016-04-23 | Duplicate
Req 0076 | Req Name 0076 | Application 2 | High | Functional | 2016-04-23 | 2016-04-28 | 2016-05-09 |  | No
Req 0077 | Req Name 0077 | Application 1 | Med | Non-Functional | 2016-04-18 | 2016-05-04 | 2016-05-05 | 2016-05-29 | No
Req 0078 | Req Name 0078 | Application 1 | Low | Performance | 2016-04-06 | 2016-04-13 | 2016-04-25 | 2016-05-07 | No
Req 0079 | Req Name 0079 | Application 1 | Low | Non-Functional | 2016-04-14 | 2016-04-21 | 2016-05-01 | 2016-05-11 | No
Req 0080 | Req Name 0080 | Application 1 | Med | Functional | 2016-04-06 | 2016-04-21 | 2016-04-23 | 2016-05-11 | Yes | 2016-04-18 | Duplicate
Req 0081 | Req Name 0081 | Application 1 | Med | Functional | 2016-04-22 | 2016-04-30 | 2016-05-07 | 2016-05-16 | No
Req 0082 | Req Name 0082 | Application 1 | Med | Non-Functional | 2016-04-21 | 2016-04-29 | 2016-05-07 | 2016-05-22 | Yes | 2016-05-07 | Descoped
Req 0083 | Req Name 0083 | Application 1 | Med | Functional | 2016-04-10 | 2016-04-19 | 2016-04-26 | 2016-05-12 | No
Req 0084 | Req Name 0084 | Application 1 | Med | Non-Functional | 2016-04-24 | 2016-04-29 | 2016-05-11 | 2016-05-24 | Yes | 2016-04-15 | Duplicate
Req 0085 | Req Name 0085 | Application 1 | Med | Non-Functional | 2016-04-11 | 2016-04-22 | 2016-04-28 | 2016-05-18 | No
Req 0086 | Req Name 0086 | Application 1 | Med | Functional | 2016-04-07 | 2016-04-14 | 2016-04-22 | 2016-05-06 | No
Req 0087 | Req Name 0087 | Application 1 | High | Performance | 2016-04-02 | 2016-04-10 | 2016-04-17 |  | No
Req 0088 | Req Name 0088 | Application 1 | Med | Non-Functional | 2016-04-14 | 2016-04-22 | 2016-04-30 |  | Yes | 2016-04-12 | Mistake
Req 0089 | Req Name 0089 | Application 1 | Med | Functional | 2016-04-14 | 2016-04-21 | 2016-05-02 | 2016-05-08 | Yes | 2016-04-15 | Duplicate
Req 0090 | Req Name 0090 | Application 1 | Low | Non-Functional | 2016-04-22 | 2016-05-02 | 2016-05-10 | 2016-05-20 | No
Req 0091 | Req Name 0091 | Application 1 | Med | Non-Functional | 2016-04-02 | 2016-04-12 | 2016-04-20 |  | Yes | 2016-04-04 | Duplicate
Req 0092 | Req Name 0092 | Application 1 | Med | Non-Functional | 2016-04-02 | 2016-04-15 | 2016-04-20 |  | No
Req 0093 | Req Name 0093 | Application 1 | Med | Non-Functional | 2016-04-02 | 2016-04-10 | 2016-04-19 | 2016-04-29 | Yes | 2016-04-13 | Duplicate
Req 0094 | Req Name 0094 | Application 1 | Med | Non-Functional | 2016-04-07 | 2016-04-16 | 2016-04-23 | 2016-05-04 | No
Req 0095 | Req Name 0095 | Application 1 | Med | Functional | 2016-04-04 | 2016-04-14 | 2016-04-21 | 2016-05-02 | No
Req 0096 | Req Name 0096 | Application 1 | Med | Non-Functional | 2016-04-04 | 2016-04-15 | 2016-04-20 | 2016-05-15 | No
Req 0097 | Req Name 0097 | Application 1 | Med | Functional | 2016-04-21 | 2016-04-30 | 2016-05-05 |  | Yes | 2016-04-13 | Duplicate
Req 0098 | Req Name 0098 | Application 1 | Med | Non-Functional | 2016-04-07 | 2016-04-18 | 2016-04-22 | 2016-05-04 | No
Req 0099 | Req Name 0099 | Application 1 | Low | Non-Functional | 2016-04-03 |  | 2016-04-20 |  | No
Req 0100 | Req Name 0100 | Application 1 | Low | Performance | 2016-04-09 | 2016-04-19 | 2016-04-24 | 2016-05-06 | No

## Test Case Plan
Test Case ID | Name | Requirement ID | Test Phase | Original | Added Date | Added Reason | Deleted Date | Deleted Reason | Status | Open Step | Hold Reason | Planned Start Date | Actual Start Date | Planned End Date | Actual End Date | Test Execution Run Type
Test Case 00001 | Test Case Name 00001 | Req 0001 | SIT | Yes | 2016-03-27 | New | 2016-03-27 | Deleted Requirement | Rejected |  |  | 2016-04-06 | 2016-04-29 | 2016-04-07 |  | Manual
Test Case 00002 | Test Case Name 00002 | Req 0002 | SIT | Yes | 2016-03-26 | New |  |  | Closed | Creation |  | 2016-04-05 | 2016-04-26 | 2016-04-09 | 2016-04-30 14:24 | Automated
Test Case 00003 | Test Case Name 00003 | Req 0003 | SIT | Yes | 2016-04-01 | New |  |  | Closed | Analysis |  | 2016-04-11 | 2016-05-05 | 2016-04-13 | 2016-05-07 19:12 | Automated
Test Case 00004 | Test Case Name 00004 | Req 0004 | SIT | Yes | 2016-04-05 | New |  |  | Closed | Design |  | 2016-04-15 | 2016-05-09 | 2016-04-18 | 2016-05-11 04:48 | Batch
Test Case 00005 | Test Case Name 00005 | Req 0005 | SIT | Yes | 2016-04-19 | New |  |  | Open | Design |  | 2016-04-29 | 2016-05-16 | 2016-05-03 | 2016-05-19 14:24 | Manual
Test Case 00006 | Test Case Name 00006 | Req 0006 | Regression | Yes | 2016-03-31 | New | 2016-03-31 | Duplicate | Rejected |  |  | 2016-04-10 | 2016-04-30 | 2016-04-11 | 2016-05-03 09:36 | Automated
Test Case 00007 | Test Case Name 00007 | Req 0006 | SIT | Yes | 2016-03-31 | New |  |  | Closed | Analysis |  | 2016-04-10 | 2016-05-02 | 2016-04-13 | 2016-05-05 04:48 | Automated
Test Case 00008 | Test Case Name 00008 | Req 0006 | SIT | Yes | 2016-03-31 | New |  |  | Rejected | Creation |  | 2016-04-10 | 2016-05-01 | 2016-04-12 | 2016-05-03 19:12 | Automated
Test Case 00009 | Test Case Name 00009 | Req 0007 | SIT | Yes | 2016-03-30 | New |  |  | Closed | Analysis |  | 2016-04-09 | 2016-04-27 | 2016-04-12 | 2016-05-01 04:48 | Manual
Test Case 00010 | Test Case Name 00010 | Req 0008 | SIT | Yes | 2016-03-28 | New | 2016-03-28 | Deleted Requirement | Rejected |  |  | 2016-04-07 | 2016-04-30 | 2016-04-09 | 2016-05-04 19:12 | Batch
Test Case 00011 | Test Case Name 00011 | Req 0008 | SIT | Yes | 2016-03-28 | New |  |  | Closed | Data Setup |  | 2016-04-07 | 2016-04-30 | 2016-04-11 |  | Automated
Test Case 00012 | Test Case Name 00012 | Req 0008 | SIT | Yes | 2016-03-28 | New |  |  | Hold | Approval | Requirements | 2016-04-07 | 2016-04-29 | 2016-04-09 |  | Batch
Test Case 00013 | Test Case Name 00013 | Req 0009 | SIT | Yes | 2016-03-27 | New | 2016-03-27 | Duplicate | Rejected |  |  | 2016-04-06 | 2016-05-01 | 2016-04-10 | 2016-05-05 14:24 | Automated
Test Case 00014 | Test Case Name 00014 | Req 0009 | SIT | Yes | 2016-03-27 | New |  |  | Rejected | Execution |  | 2016-04-06 | 2016-04-30 | 2016-04-10 | 2016-05-04 14:24 | Manual
Test Case 00015 | Test Case Name 00015 | Req 0010 | SIT | Yes | 2016-04-06 | New |  |  | Rejected | Research |  | 2016-04-16 | 2016-05-05 | 2016-04-19 | 2016-05-09 04:48 | Batch
Test Case 00016 | Test Case Name 00016 | Req 0010 | SIT | Yes | 2016-04-06 | New |  |  | Open | Design |  | 2016-04-16 | 2016-05-07 | 2016-04-20 |  | Batch
Test Case 00017 | Test Case Name 00017 | Req 0010 | SIT | Yes | 2016-04-06 | New |  |  | Rejected | Data Setup |  | 2016-04-16 | 2016-05-06 | 2016-04-20 | 2016-05-09 14:24 | Manual
Test Case 00018 | Test Case Name 00018 | Req 0010 | SIT | Yes | 2016-04-06 | Split |  |  | Hold | Research | Requirements | 2016-04-16 | 2016-05-07 | 2016-04-20 |  | Automated
Test Case 00019 | Test Case Name 00019 | Req 0010 | SIT | Yes | 2016-04-06 | New |  |  | Closed | Research |  | 2016-04-16 | 2016-05-06 | 2016-04-19 |  | Batch
Test Case 00020 | Test Case Name 00020 | Req 0011 | SIT | Yes | 2016-03-31 | New |  |  | Open | Analysis |  | 2016-04-10 | 2016-04-29 | 2016-04-13 | 2016-05-01 04:48 | Batch
Test Case 00021 | Test Case Name 00021 | Req 0011 | SIT | Yes | 2016-03-31 | New |  |  | Closed | Research |  | 2016-04-10 | 2016-04-30 | 2016-04-13 | 2016-05-03 04:48 | Manual
Test Case 00022 | Test Case Name 00022 | Req 0011 | SIT | Yes | 2016-03-31 | New |  |  | Open | Analysis |  | 2016-04-10 | 2016-04-27 | 2016-04-15 | 2016-05-03 | Manual
Test Case 00023 | Test Case Name 00023 | Req 0011 | SIT | Yes | 2016-03-31 | New |  |  | Hold | Analysis | Data | 2016-04-10 | 2016-04-28 | 2016-04-15 |  | Manual
Test Case 00024 | Test Case Name 00024 | Req 0012 | SIT | Yes | 2016-03-25 | New |  |  | Closed | Data Setup |  | 2016-04-04 | 2016-04-25 | 2016-04-08 | 2016-04-30 14:24 | Batch
Test Case 00025 | Test Case Name 00025 | Req 0013 | SIT | Yes | 2016-03-25 | New |  |  | Hold | Analysis | Data | 2016-04-04 | 2016-04-29 | 2016-04-07 |  | Manual
Test Case 00026 | Test Case Name 00026 | Req 0014 | SIT | Yes | 2016-04-23 | New |  |  | Open | Data Setup |  | 2016-05-03 | 2016-05-26 | 2016-05-05 |  | Batch
Test Case 00027 | Test Case Name 00027 | Req 0014 | SIT | Yes | 2016-04-23 | New |  |  | Hold | Creation | Requirements | 2016-05-03 | 2016-05-27 | 2016-05-07 |  | Manual
Test Case 00028 | Test Case Name 00028 | Req 0015 | SIT | Yes | 2016-03-26 | New |  |  | Open | Analysis |  | 2016-04-05 | 2016-04-22 | 2016-04-09 | 2016-04-24 14:24 | Manual
Test Case 00029 | Test Case Name 00029 | Req 0015 | SIT | Yes | 2016-03-26 | Missed |  |  | Closed | Design |  | 2016-04-05 | 2016-04-22 | 2016-04-07 | 2016-04-24 19:12 | Manual
Test Case 00030 | Test Case Name 00030 | Req 0016 | SIT | Yes | 2016-03-24 | New |  |  | Closed | Analysis |  | 2016-04-03 | 2016-04-18 | 2016-04-06 | 2016-04-23 04:48 | Manual
Test Case 00031 | Test Case Name 00031 | Req 0016 | SIT | Yes | 2016-03-24 | New |  |  | Open | Creation |  | 2016-04-03 | 2016-04-17 | 2016-04-07 |  | Automated
Test Case 00032 | Test Case Name 00032 | Req 0017 | SIT | Yes | 2016-03-31 | New | 2016-03-31 | Duplicate | Rejected |  |  | 2016-04-10 | 2016-04-28 | 2016-04-14 | 2016-05-02 14:24 | Manual
Test Case 00033 | Test Case Name 00033 | Req 0018 | SIT | Yes | 2016-03-27 | New |  |  | Closed | Execution |  | 2016-04-06 | 2016-04-25 | 2016-04-09 |  | Automated
Test Case 00034 | Test Case Name 00034 | Req 0018 | SIT | Yes | 2016-03-27 | New |  |  | Closed | Analysis |  | 2016-04-06 | 2016-04-26 | 2016-04-11 |  | Batch
Test Case 00035 | Test Case Name 00035 | Req 0019 | SIT | Yes | 2016-03-24 | New |  |  | Open | Execution |  | 2016-04-03 |  | 2016-04-05 |  | Manual
Test Case 00036 | Test Case Name 00036 | Req 0019 | SIT | Yes | 2016-03-24 | New |  |  | Closed | Design |  | 2016-04-03 |  | 2016-04-05 |  | Manual
Test Case 00037 | Test Case Name 00037 | Req 0020 | Regression | Yes | 2016-04-09 | New |  |  | Closed | Execution |  | 2016-04-19 | 2016-05-12 | 2016-04-22 | 2016-05-17 04:48 | Automated
Test Case 00038 | Test Case Name 00038 | Req 0020 | SIT | Yes | 2016-04-09 | Missed |  |  | Open | Creation |  | 2016-04-19 | 2016-05-14 | 2016-04-23 | 2016-05-19 14:24 | Batch
Test Case 00039 | Test Case Name 00039 | Req 0020 | Regression | Yes | 2016-04-09 | New |  |  | Closed | Creation |  | 2016-04-19 | 2016-05-13 | 2016-04-22 | 2016-05-16 04:48 | Automated
Test Case 00040 | Test Case Name 00040 | Req 0020 | SIT | Yes | 2016-04-09 | New |  |  | Rejected | Creation |  | 2016-04-19 | 2016-05-13 | 2016-04-23 |  | Manual
Test Case 00041 | Test Case Name 00041 | Req 0020 | SIT | Yes | 2016-04-09 | Split |  |  | Closed | Research |  | 2016-04-19 | 2016-05-14 | 2016-04-22 | 2016-05-17 04:48 | Manual
Test Case 00042 | Test Case Name 00042 | Req 0021 | SIT | Yes | 2016-04-03 | New |  |  | Closed | Analysis |  | 2016-04-13 | 2016-05-06 | 2016-04-16 |  | Manual
Test Case 00043 | Test Case Name 00043 | Req 0022 | SIT | Yes | 2016-04-11 | New |  |  | Closed | Design |  | 2016-04-21 | 2016-05-10 | 2016-04-26 | 2016-05-14 | Automated
Test Case 00044 | Test Case Name 00044 | Req 0022 | SIT | Yes | 2016-04-11 | New | 2016-04-11 | Combined | Rejected |  |  | 2016-04-21 | 2016-05-10 | 2016-04-23 | 2016-05-12 19:12 | Manual
Test Case 00045 | Test Case Name 00045 | Req 0023 | SIT | Yes | 2016-04-03 | New |  |  | Open | Design |  | 2016-04-13 | 2016-04-28 | 2016-04-17 | 2016-04-30 14:24 | Manual
Test Case 00046 | Test Case Name 00046 | Req 0024 | SIT | Yes | 2016-03-29 | New | 2016-03-29 | Combined | Rejected |  |  | 2016-04-08 | 2016-05-02 | 2016-04-10 | 2016-05-05 19:12 | Batch
Test Case 00047 | Test Case Name 00047 | Req 0025 | SIT | Yes | 2016-04-01 | New |  |  | Open | Design |  | 2016-04-11 | 2016-04-29 | 2016-04-14 | 2016-05-01 04:48 | Manual
Test Case 00048 | Test Case Name 00048 | Req 0025 | SIT | Yes | 2016-04-01 | New | 2016-04-01 | Duplicate | Rejected |  |  | 2016-04-11 | 2016-04-29 | 2016-04-14 | 2016-05-02 04:48 | Automated
Test Case 00049 | Test Case Name 00049 | Req 0025 | SIT | Yes | 2016-04-01 | New |  |  | Open | Data Setup |  | 2016-04-11 | 2016-04-28 | 2016-04-14 | 2016-05-02 04:48 | Automated
Test Case 00050 | Test Case Name 00050 | Req 0026 | SIT | Yes | 2016-04-18 | New |  |  | Rejected | Design |  | 2016-04-28 | 2016-05-20 | 2016-05-02 | 2016-05-23 14:24 | Manual
Test Case 00051 | Test Case Name 00051 | Req 0026 | SIT | Yes | 2016-04-18 | New | 2016-04-18 | Duplicate | Rejected |  |  | 2016-04-28 | 2016-05-19 | 2016-05-01 | 2016-05-22 04:48 | Automated
Test Case 00052 | Test Case Name 00052 | Req 0027 | SIT | Yes | 2016-04-12 | New |  |  | Open | Data Setup |  | 2016-04-22 | 2016-05-10 | 2016-04-24 |  | Manual
Test Case 00053 | Test Case Name 00053 | Req 0028 | SIT | Yes | 2016-03-30 | Missed |  |  | Closed | Execution |  | 2016-04-09 | 2016-04-28 | 2016-04-10 | 2016-04-29 09:36 | Batch
Test Case 00054 | Test Case Name 00054 | Req 0028 | SIT | Yes | 2016-03-30 | New |  |  | Open | Design |  | 2016-04-09 | 2016-04-27 | 2016-04-14 | 2016-05-02 | Batch
Test Case 00055 | Test Case Name 00055 | Req 0028 | SIT | Yes | 2016-03-30 | New |  |  | Closed | Analysis |  | 2016-04-09 | 2016-04-24 | 2016-04-12 | 2016-04-28 04:48 | Manual
Test Case 00056 | Test Case Name 00056 | Req 0028 | SIT | Yes | 2016-03-30 | New |  |  | Closed | Analysis |  | 2016-04-09 | 2016-04-28 | 2016-04-11 |  | Manual
Test Case 00057 | Test Case Name 00057 | Req 0028 | SIT | Yes | 2016-03-30 | New |  |  | Closed | Design |  | 2016-04-09 | 2016-04-25 | 2016-04-11 | 2016-04-28 19:12 | Manual
Test Case 00058 | Test Case Name 00058 | Req 0029 | SIT | Yes | 2016-03-27 | New | 2016-03-27 | Deleted Requirement | Rejected |  |  | 2016-04-06 | 2016-04-22 | 2016-04-11 | 2016-04-27 | Automated
Test Case 00059 | Test Case Name 00059 | Req 0030 | SIT | Yes | 2016-04-08 | New |  |  | Hold | Design | Requirements | 2016-04-18 |  | 2016-04-22 |  | Manual
Test Case 00060 | Test Case Name 00060 | Req 0030 | SIT | Yes | 2016-04-08 | Split |  |  | Closed | Execution |  | 2016-04-18 |  | 2016-04-22 |  | Manual
Test Case 00061 | Test Case Name 00061 | Req 0031 | SIT | Yes | 2016-04-12 | New |  |  | Hold | Execution | Requirements | 2016-04-22 | 2016-05-15 | 2016-04-25 |  | Automated
Test Case 00062 | Test Case Name 00062 | Req 0032 | SIT | Yes | 2016-03-29 | New |  |  | Closed | Data Setup |  | 2016-04-08 | 2016-04-29 | 2016-04-12 | 2016-05-03 14:24 | Manual
Test Case 00063 | Test Case Name 00063 | Req 0032 | Regression | Yes | 2016-03-29 | New |  |  | Closed | Design |  | 2016-04-08 | 2016-04-27 | 2016-04-10 |  | Manual
Test Case 00064 | Test Case Name 00064 | Req 0033 | SIT | Yes | 2016-03-29 | New |  |  | Closed | Creation |  | 2016-04-08 | 2016-04-22 | 2016-04-13 | 2016-04-26 | Manual
Test Case 00065 | Test Case Name 00065 | Req 0033 | SIT | Yes | 2016-03-29 | New | 2016-03-29 | Combined | Rejected |  |  | 2016-04-08 | 2016-04-21 | 2016-04-11 |  | Automated
Test Case 00066 | Test Case Name 00066 | Req 0034 | SIT | Yes | 2016-04-06 | New |  |  | Open | Design |  | 2016-04-16 | 2016-05-03 | 2016-04-20 | 2016-05-06 14:24 | Manual
Test Case 00067 | Test Case Name 00067 | Req 0034 | SIT | Yes | 2016-04-06 | New |  |  | Closed | Design |  | 2016-04-16 | 2016-04-30 | 2016-04-19 | 2016-05-02 04:48 | Automated
Test Case 00068 | Test Case Name 00068 | Req 0034 | SIT | Yes | 2016-04-06 | New |  |  | Closed | Execution |  | 2016-04-16 | 2016-04-30 | 2016-04-20 |  | Automated
Test Case 00069 | Test Case Name 00069 | Req 0034 | Regression | Yes | 2016-04-06 | New |  |  | Rejected | Execution |  | 2016-04-16 | 2016-05-01 | 2016-04-19 | 2016-05-03 04:48 | Batch
Test Case 00070 | Test Case Name 00070 | Req 0035 | SIT | Yes | 2016-03-26 | New |  |  | Rejected | Analysis |  | 2016-04-05 | 2016-04-24 | 2016-04-08 | 2016-04-29 04:48 | Automated
Test Case 00071 | Test Case Name 00071 | Req 0036 | SIT | Yes | 2016-04-05 | New |  |  | Open | Execution |  | 2016-04-15 |  | 2016-04-21 |  | Manual
Test Case 00072 | Test Case Name 00072 | Req 0037 | SIT | Yes | 2016-03-24 | New | 2016-03-24 | Deleted Requirement | Rejected |  |  | 2016-04-03 | 2016-04-21 | 2016-04-05 |  | Manual
Test Case 00073 | Test Case Name 00073 | Req 0038 | SIT | Yes | 2016-03-25 | New | 2016-03-25 | Duplicate | Rejected |  |  | 2016-04-04 | 2016-04-17 | 2016-04-09 | 2016-04-22 | Manual
Test Case 00074 | Test Case Name 00074 | Req 0038 | SIT | Yes | 2016-03-25 | New | 2016-03-25 | Duplicate | Rejected |  |  | 2016-04-04 | 2016-04-20 | 2016-04-07 | 2016-04-25 04:48 | Batch
Test Case 00075 | Test Case Name 00075 | Req 0038 | SIT | Yes | 2016-03-25 | New |  |  | Rejected | Execution |  | 2016-04-04 | 2016-04-17 | 2016-04-07 | 2016-04-22 04:48 | Batch
Test Case 00076 | Test Case Name 00076 | Req 0038 | SIT | Yes | 2016-03-25 | New | 2016-03-25 | Combined | Rejected |  |  | 2016-04-04 | 2016-04-19 | 2016-04-06 | 2016-04-24 19:12 | Batch
Test Case 00077 | Test Case Name 00077 | Req 0039 | SIT | Yes | 2016-04-10 | New |  |  | Hold | Design | Requirements | 2016-04-20 |  | 2016-04-23 |  | Manual
Test Case 00078 | Test Case Name 00078 | Req 0040 | SIT | Yes | 2016-04-03 | New |  |  | Rejected | Design |  | 2016-04-13 | 2016-05-01 | 2016-04-15 | 2016-05-04 19:12 | Manual
Test Case 00079 | Test Case Name 00079 | Req 0040 | SIT | Yes | 2016-04-03 | New |  |  | Open | Approval |  | 2016-04-13 | 2016-05-02 | 2016-04-17 | 2016-05-05 14:24 | Manual
Test Case 00080 | Test Case Name 00080 | Req 0041 | SIT | Yes | 2016-04-19 | New |  |  | Closed | Creation |  | 2016-04-29 | 2016-05-16 | 2016-05-02 |  | Manual
Test Case 00081 | Test Case Name 00081 | Req 0041 | SIT | Yes | 2016-04-19 | New |  |  | Closed | Analysis |  | 2016-04-29 | 2016-05-14 | 2016-05-01 | 2016-05-17 19:12 | Manual
Test Case 00082 | Test Case Name 00082 | Req 0041 | SIT | Yes | 2016-04-19 | New |  |  | Closed | Creation |  | 2016-04-29 | 2016-05-15 | 2016-05-02 | 2016-05-18 04:48 | Batch
Test Case 00083 | Test Case Name 00083 | Req 0042 | SIT | Yes | 2016-03-31 | New |  |  | Hold | Research | Requirements | 2016-04-10 | 2016-04-28 | 2016-04-13 |  | Manual
Test Case 00084 | Test Case Name 00084 | Req 0042 | SIT | Yes | 2016-03-31 | New |  |  | Open | Analysis |  | 2016-04-10 | 2016-04-26 | 2016-04-14 | 2016-04-29 14:24 | Manual
Test Case 00085 | Test Case Name 00085 | Req 0042 | SIT | Yes | 2016-03-31 | New |  |  | Closed | Data Setup |  | 2016-04-10 | 2016-04-27 | 2016-04-16 | 2016-05-02 09:36 | Automated
Test Case 00086 | Test Case Name 00086 | Req 0043 | SIT | Yes | 2016-03-29 | New |  |  | Closed | Design |  | 2016-04-08 | 2016-04-23 | 2016-04-11 | 2016-04-26 04:48 | Manual
Test Case 00087 | Test Case Name 00087 | Req 0043 | Regression | Yes | 2016-03-29 | New |  |  | Hold | Analysis | Requirements | 2016-04-08 | 2016-04-23 | 2016-04-13 |  | Manual
Test Case 00088 | Test Case Name 00088 | Req 0044 | SIT | Yes | 2016-04-03 | New | 2016-04-03 | Duplicate | Rejected |  |  | 2016-04-13 | 2016-05-03 | 2016-04-15 | 2016-05-04 19:12 | Automated
Test Case 00089 | Test Case Name 00089 | Req 0045 | SIT | Yes | 2016-04-05 | New | 2016-04-05 | Deleted Requirement | Rejected |  |  | 2016-04-15 | 2016-05-01 | 2016-04-19 | 2016-05-04 14:24 | Automated
Test Case 00090 | Test Case Name 00090 | Req 0045 | SIT | Yes | 2016-04-05 | New |  |  | Closed | Execution |  | 2016-04-15 | 2016-05-02 | 2016-04-18 | 2016-05-06 04:48 | Manual
Test Case 00091 | Test Case Name 00091 | Req 0045 | SIT | Yes | 2016-04-05 | New |  |  | Hold | Execution | Requirements | 2016-04-15 | 2016-05-01 | 2016-04-20 |  | Batch
Test Case 00092 | Test Case Name 00092 | Req 0045 | SIT | Yes | 2016-04-05 | New |  |  | Closed | Research |  | 2016-04-15 | 2016-05-01 | 2016-04-20 | 2016-05-06 | Manual
Test Case 00093 | Test Case Name 00093 | Req 0046 | SIT | Yes | 2016-03-22 | New |  |  | Open | Defect |  | 2016-04-01 | 2016-05-02 | 2016-04-04 | 2016-05-08 04:48 | Manual
Test Case 00094 | Test Case Name 00094 | Req 0047 | SIT | Yes | 2016-03-26 | New |  |  | Closed | Data Setup |  | 2016-04-05 | 2016-04-21 | 2016-04-09 | 2016-04-24 14:24 | Manual
Test Case 00095 | Test Case Name 00095 | Req 0048 | SIT | Yes | 2016-04-13 | New |  |  | Rejected | Design |  | 2016-04-23 | 2016-05-08 | 2016-04-26 |  | Automated
Test Case 00096 | Test Case Name 00096 | Req 0049 | SIT | Yes | 2016-04-05 | New | 2016-04-05 | Deleted Requirement | Rejected |  |  | 2016-04-15 | 2016-05-04 | 2016-04-19 | 2016-05-09 14:24 | Batch
Test Case 00097 | Test Case Name 00097 | Req 0050 | SIT | Yes | 2016-04-07 | New |  |  | Rejected | Execution |  | 2016-04-17 | 2016-05-10 | 2016-04-21 | 2016-05-13 14:24 | Batch
Test Case 00098 | Test Case Name 00098 | Req 0051 | SIT | Yes | 2016-04-20 | New | 2016-04-20 | Duplicate | Rejected |  |  | 2016-04-30 | 2016-05-14 | 2016-05-04 |  | Manual
Test Case 00099 | Test Case Name 00099 | Req 0052 | SIT | Yes | 2016-04-10 | New |  |  | Hold | Execution | Requirements | 2016-04-20 | 2016-05-08 | 2016-04-23 |  | Manual
Test Case 00100 | Test Case Name 00100 | Req 0052 | SIT | Yes | 2016-04-10 | New |  |  | Hold | Data Setup | Requirements | 2016-04-20 | 2016-05-08 | 2016-04-23 |  | Manual
Test Case 00101 | Test Case Name 00101 | Req 0052 | SIT | Yes | 2016-04-10 | New |  |  | Closed | Creation |  | 2016-04-20 | 2016-05-08 | 2016-04-22 |  | Automated
Test Case 00102 | Test Case Name 00102 | Req 0052 | SIT | Yes | 2016-04-10 | New |  |  | Open | Research |  | 2016-04-20 | 2016-05-08 | 2016-04-24 |  | Manual
Test Case 00103 | Test Case Name 00103 | Req 0052 | SIT | Yes | 2016-04-10 | New |  |  | Open | Design |  | 2016-04-20 | 2016-05-08 | 2016-04-23 | 2016-05-11 04:48 | Batch
Test Case 00104 | Test Case Name 00104 | Req 0052 | SIT | Yes | 2016-04-10 | New |  |  | Open | Analysis |  | 2016-04-20 | 2016-05-07 | 2016-04-23 | 2016-05-12 04:48 | Manual
Test Case 00105 | Test Case Name 00105 | Req 0053 | SIT | Yes | 2016-03-23 | New |  |  | Open | Analysis |  | 2016-04-02 | 2016-04-21 | 2016-04-06 | 2016-04-24 14:24 | Manual
Test Case 00106 | Test Case Name 00106 | Req 0053 | SIT | Yes | 2016-03-23 | New |  |  | Hold | Execution | Requirements | 2016-04-02 | 2016-04-22 | 2016-04-05 |  | Batch
Test Case 00107 | Test Case Name 00107 | Req 0054 | SIT | Yes | 2016-03-23 | New |  |  | Open | Creation |  | 2016-04-02 |  | 2016-04-05 |  | Batch
Test Case 00108 | Test Case Name 00108 | Req 0054 | SIT | Yes | 2016-03-23 | New |  |  | Open | Data Setup |  | 2016-04-02 |  | 2016-04-06 |  | Batch
Test Case 00109 | Test Case Name 00109 | Req 0054 | SIT | Yes | 2016-03-23 | Split |  |  | Hold | Design | Environment | 2016-04-02 |  | 2016-04-06 |  | Manual
Test Case 00110 | Test Case Name 00110 | Req 0055 | SIT | Yes | 2016-04-26 | New |  |  | Hold | Analysis | Requirements | 2016-05-06 | 2016-05-25 | 2016-05-11 |  | Manual
Test Case 00111 | Test Case Name 00111 | Req 0055 | Regression | Yes | 2016-04-26 | New |  |  | Hold | Design | Requirements | 2016-05-06 | 2016-05-24 | 2016-05-10 |  | Manual
Test Case 00112 | Test Case Name 00112 | Req 0056 | SIT | Yes | 2016-04-06 | New |  |  | Hold | Data Setup | Requirements | 2016-04-16 |  | 2016-04-19 |  | Manual
Test Case 00113 | Test Case Name 00113 | Req 0057 | SIT | Yes | 2016-04-01 | New |  |  | Closed | Design |  | 2016-04-11 | 2016-04-30 | 2016-04-14 |  | Manual
Test Case 00114 | Test Case Name 00114 | Req 0057 | SIT | Yes | 2016-04-01 | New |  |  | Open | Design |  | 2016-04-11 | 2016-04-30 | 2016-04-15 | 2016-05-05 14:24 | Batch
Test Case 00115 | Test Case Name 00115 | Req 0058 | SIT | Yes | 2016-03-26 | New |  |  | Open | Creation |  | 2016-04-05 | 2016-04-20 | 2016-04-09 |  | Batch
Test Case 00116 | Test Case Name 00116 | Req 0058 | SIT | Yes | 2016-03-26 | Split |  |  | Open | Creation |  | 2016-04-05 | 2016-04-19 | 2016-04-07 | 2016-04-22 19:12 | Manual
Test Case 00117 | Test Case Name 00117 | Req 0058 | SIT | Yes | 2016-03-26 | New |  |  | Closed | Design |  | 2016-04-05 | 2016-04-21 | 2016-04-08 |  | Batch
Test Case 00118 | Test Case Name 00118 | Req 0058 | SIT | Yes | 2016-03-26 | New |  |  | Rejected | Creation |  | 2016-04-05 | 2016-04-21 | 2016-04-09 | 2016-04-25 14:24 | Batch
Test Case 00119 | Test Case Name 00119 | Req 0059 | SIT | Yes | 2016-04-06 | New |  |  | Hold | Design | Requirements | 2016-04-16 | 2016-05-10 | 2016-04-20 |  | Manual
Test Case 00120 | Test Case Name 00120 | Req 0060 | SIT | Yes | 2016-04-10 | New |  |  | Hold | Execution | Requirements | 2016-04-20 | 2016-05-08 | 2016-04-24 |  | Batch
Test Case 00121 | Test Case Name 00121 | Req 0061 | SIT | Yes | 2016-04-09 | New |  |  | Hold | Creation | Data | 2016-04-19 | 2016-05-11 | 2016-04-23 |  | Automated
Test Case 00122 | Test Case Name 00122 | Req 0062 | SIT | Yes | 2016-04-14 | New |  |  | Closed | Analysis |  | 2016-04-24 | 2016-05-21 | 2016-04-27 | 2016-05-24 04:48 | Manual
Test Case 00123 | Test Case Name 00123 | Req 0063 | SIT | Yes | 2016-04-13 | New |  |  | Closed | Creation |  | 2016-04-23 | 2016-05-10 | 2016-04-26 | 2016-05-12 04:48 | Manual
Test Case 00124 | Test Case Name 00124 | Req 0063 | SIT | Yes | 2016-04-13 | New |  |  | Closed | Creation |  | 2016-04-23 | 2016-05-08 | 2016-04-26 | 2016-05-12 04:48 | Batch
Test Case 00125 | Test Case Name 00125 | Req 0064 | SIT | Yes | 2016-04-03 | New |  |  | Closed | Design |  | 2016-04-13 | 2016-05-02 | 2016-04-16 | 2016-05-06 04:48 | Automated
Test Case 00126 | Test Case Name 00126 | Req 0065 | SIT | Yes | 2016-04-01 | New |  |  | Hold | Approval | Requirements | 2016-04-11 | 2016-05-03 | 2016-04-15 |  | Manual
Test Case 00127 | Test Case Name 00127 | Req 0065 | SIT | Yes | 2016-04-01 | New |  |  | Closed | Data Setup |  | 2016-04-11 | 2016-05-05 | 2016-04-15 | 2016-05-07 14:24 | Manual
Test Case 00128 | Test Case Name 00128 | Req 0065 | SIT | Yes | 2016-04-01 | New | 2016-04-01 | Deleted Requirement | Rejected |  |  | 2016-04-11 | 2016-05-05 | 2016-04-16 | 2016-05-10 | Batch
Test Case 00129 | Test Case Name 00129 | Req 0065 | SIT | Yes | 2016-04-01 | New |  |  | Open | Research |  | 2016-04-11 | 2016-05-05 | 2016-04-15 | 2016-05-07 14:24 | Automated
Test Case 00130 | Test Case Name 00130 | Req 0066 | SIT | Yes | 2016-03-24 | Missed |  |  | Hold | Analysis | Requirements | 2016-04-03 |  | 2016-04-08 |  | Manual
Test Case 00131 | Test Case Name 00131 | Req 0067 | SIT | Yes | 2016-04-09 | New |  |  | Closed | Research |  | 2016-04-19 | 2016-05-11 | 2016-04-23 | 2016-05-16 14:24 | Automated
Test Case 00132 | Test Case Name 00132 | Req 0067 | SIT | Yes | 2016-04-09 | New |  |  | Open | Research |  | 2016-04-19 | 2016-05-12 | 2016-04-23 | 2016-05-16 14:24 | Manual
Test Case 00133 | Test Case Name 00133 | Req 0068 | SIT | Yes | 2016-04-15 | New |  |  | Closed | Creation |  | 2016-04-25 | 2016-05-09 | 2016-04-28 | 2016-05-12 04:48 | Batch
Test Case 00134 | Test Case Name 00134 | Req 0069 | SIT | Yes | 2016-04-18 | New |  |  | Hold | Data Setup | Requirements | 2016-04-28 | 2016-05-14 | 2016-05-02 |  | Batch
Test Case 00135 | Test Case Name 00135 | Req 0070 | SIT | Yes | 2016-03-26 | New |  |  | Open | Creation |  | 2016-04-05 | 2016-04-22 | 2016-04-09 | 2016-04-27 14:24 | Manual
Test Case 00136 | Test Case Name 00136 | Req 0071 | SIT | Yes | 2016-03-30 | New |  |  | Open | Data Setup |  | 2016-04-09 | 2016-05-01 | 2016-04-14 | 2016-05-05 | Batch
Test Case 00137 | Test Case Name 00137 | Req 0071 | SIT | Yes | 2016-03-30 | New |  |  | Closed | Design |  | 2016-04-09 | 2016-04-30 | 2016-04-12 | 2016-05-04 04:48 | Manual
Test Case 00138 | Test Case Name 00138 | Req 0071 | SIT | Yes | 2016-03-30 | New |  |  | Closed | Design |  | 2016-04-09 | 2016-04-29 | 2016-04-13 |  | Manual
Test Case 00139 | Test Case Name 00139 | Req 0071 | SIT | Yes | 2016-03-30 | New |  |  | Rejected | Design |  | 2016-04-09 | 2016-05-02 | 2016-04-12 |  | Manual
Test Case 00140 | Test Case Name 00140 | Req 0071 | SIT | Yes | 2016-03-30 | New |  |  | Hold | Creation | Requirements | 2016-04-09 | 2016-05-01 | 2016-04-12 |  | Manual
Test Case 00141 | Test Case Name 00141 | Req 0072 | SIT | Yes | 2016-04-27 | New |  |  | Rejected | Analysis |  | 2016-05-07 | 2016-05-23 | 2016-05-11 | 2016-05-27 14:24 | Automated
Test Case 00142 | Test Case Name 00142 | Req 0073 | SIT | Yes | 2016-03-23 | New |  |  | Closed | Creation |  | 2016-04-02 | 2016-04-19 | 2016-04-05 | 2016-04-22 04:48 | Automated
Test Case 00143 | Test Case Name 00143 | Req 0074 | SIT | Yes | 2016-03-22 | New |  |  | Closed | Data Setup |  | 2016-04-01 | 2016-04-28 | 2016-04-04 | 2016-05-01 04:48 | Manual
Test Case 00144 | Test Case Name 00144 | Req 0074 | SIT | Yes | 2016-03-22 | New |  |  | Rejected | Data Setup |  | 2016-04-01 | 2016-04-29 | 2016-04-06 | 2016-05-03 | Manual
Test Case 00145 | Test Case Name 00145 | Req 0075 | SIT | Yes | 2016-04-01 | New |  |  | Open | Design |  | 2016-04-11 |  | 2016-04-12 |  | Batch
Test Case 00146 | Test Case Name 00146 | Req 0076 | SIT | Yes | 2016-04-13 | New |  |  | Rejected | Execution |  | 2016-04-23 | 2016-05-06 | 2016-04-26 | 2016-05-11 04:48 | Manual
Test Case 00147 | Test Case Name 00147 | Req 0076 | SIT | Yes | 2016-04-13 | Split |  |  | Rejected | Execution |  | 2016-04-23 | 2016-05-08 | 2016-04-27 | 2016-05-11 14:24 | Manual
Test Case 00148 | Test Case Name 00148 | Req 0077 | SIT | Yes | 2016-04-08 | New |  |  | Open | Design |  | 2016-04-18 | 2016-05-14 | 2016-04-20 | 2016-05-17 19:12 | Manual
Test Case 00149 | Test Case Name 00149 | Req 0078 | SIT | Yes | 2016-03-27 | New | 2016-03-27 | Deleted Requirement | Rejected |  |  | 2016-04-06 | 2016-04-24 | 2016-04-10 | 2016-04-27 14:24 | Manual
Test Case 00150 | Test Case Name 00150 | Req 0078 | SIT | Yes | 2016-03-27 | Split |  |  | Hold | Approval | Requirements | 2016-04-06 | 2016-04-20 | 2016-04-10 |  | Manual
Test Case 00151 | Test Case Name 00151 | Req 0079 | SIT | Yes | 2016-04-04 | New |  |  | Closed | Execution |  | 2016-04-14 | 2016-04-30 | 2016-04-16 | 2016-05-02 19:12 | Automated
Test Case 00152 | Test Case Name 00152 | Req 0079 | SIT | Yes | 2016-04-04 | New |  |  | Closed | Research |  | 2016-04-14 | 2016-05-02 | 2016-04-17 |  | Manual
Test Case 00153 | Test Case Name 00153 | Req 0080 | SIT | Yes | 2016-03-27 | New |  |  | Closed | Design |  | 2016-04-06 | 2016-05-02 | 2016-04-09 | 2016-05-04 04:48 | Manual
Test Case 00154 | Test Case Name 00154 | Req 0080 | SIT | Yes | 2016-03-27 | New |  |  | Rejected | Creation |  | 2016-04-06 | 2016-04-29 | 2016-04-10 | 2016-05-04 14:24 | Manual
Test Case 00155 | Test Case Name 00155 | Req 0080 | SIT | Yes | 2016-03-27 | New | 2016-03-27 | Duplicate | Rejected |  |  | 2016-04-06 | 2016-04-30 | 2016-04-10 | 2016-05-03 14:24 | Manual
Test Case 00156 | Test Case Name 00156 | Req 0080 | SIT | Yes | 2016-03-27 | New |  |  | Open | Creation |  | 2016-04-06 | 2016-04-30 | 2016-04-10 | 2016-05-06 14:24 | Batch
Test Case 00157 | Test Case Name 00157 | Req 0080 | SIT | Yes | 2016-03-27 | Split |  |  | Open | Research |  | 2016-04-06 | 2016-05-01 | 2016-04-10 | 2016-05-04 14:24 | Automated
Test Case 00158 | Test Case Name 00158 | Req 0081 | SIT | Yes | 2016-04-12 | New |  |  | Open | Data Setup |  | 2016-04-22 | 2016-05-09 | 2016-04-24 | 2016-05-11 19:12 | Automated
Test Case 00159 | Test Case Name 00159 | Req 0081 | SIT | Yes | 2016-04-12 | New |  |  | Rejected | Design |  | 2016-04-22 | 2016-05-10 | 2016-04-24 | 2016-05-15 19:12 | Batch
Test Case 00160 | Test Case Name 00160 | Req 0082 | SIT | Yes | 2016-04-11 | New |  |  | Closed | Design |  | 2016-04-21 | 2016-05-08 | 2016-04-24 | 2016-05-12 04:48 | Manual
Test Case 00161 | Test Case Name 00161 | Req 0082 | SIT | Yes | 2016-04-11 | New |  |  | Hold | Research | Requirements | 2016-04-21 | 2016-05-08 | 2016-04-23 |  | Manual
Test Case 00162 | Test Case Name 00162 | Req 0083 | SIT | Yes | 2016-03-31 | New |  |  | Closed | Creation |  | 2016-04-10 | 2016-04-29 | 2016-04-13 | 2016-05-02 04:48 | Manual
Test Case 00163 | Test Case Name 00163 | Req 0083 | SIT | Yes | 2016-03-31 | New |  |  | Rejected | Design |  | 2016-04-10 | 2016-04-28 | 2016-04-13 |  | Batch
Test Case 00164 | Test Case Name 00164 | Req 0084 | SIT | Yes | 2016-04-14 | New |  |  | Open | Design |  | 2016-04-24 | 2016-05-09 | 2016-04-28 |  | Automated
Test Case 00165 | Test Case Name 00165 | Req 0085 | SIT | Yes | 2016-04-01 | New |  |  | Closed | Execution |  | 2016-04-11 | 2016-05-03 | 2016-04-16 | 2016-05-11 | Manual
Test Case 00166 | Test Case Name 00166 | Req 0086 | SIT | Yes | 2016-03-28 | New |  |  | Rejected | Research |  | 2016-04-07 | 2016-04-23 | 2016-04-11 | 2016-04-24 14:24 | Automated
Test Case 00167 | Test Case Name 00167 | Req 0087 | SIT | Yes | 2016-03-23 | New |  |  | Closed | Research |  | 2016-04-02 | 2016-04-19 | 2016-04-06 | 2016-04-22 14:24 | Manual
Test Case 00168 | Test Case Name 00168 | Req 0088 | SIT | Yes | 2016-04-04 | New |  |  | Rejected | Design |  | 2016-04-14 | 2016-05-03 | 2016-04-17 | 2016-05-07 04:48 | Manual
Test Case 00169 | Test Case Name 00169 | Req 0088 | SIT | Yes | 2016-04-04 | New |  |  | Rejected | Execution |  | 2016-04-14 | 2016-05-01 | 2016-04-17 | 2016-05-06 04:48 | Manual
Test Case 00170 | Test Case Name 00170 | Req 0088 | SIT | Yes | 2016-04-04 | Split |  |  | Hold | Creation | Requirements | 2016-04-14 | 2016-05-01 | 2016-04-17 |  | Automated
Test Case 00171 | Test Case Name 00171 | Req 0089 | SIT | Yes | 2016-04-04 | New |  |  | Rejected | Creation |  | 2016-04-14 | 2016-05-03 | 2016-04-17 | 2016-05-05 04:48 | Batch
Test Case 00172 | Test Case Name 00172 | Req 0090 | SIT | Yes | 2016-04-12 | New |  |  | Closed | Analysis |  | 2016-04-22 | 2016-05-11 | 2016-04-25 |  | Batch
Test Case 00173 | Test Case Name 00173 | Req 0090 | SIT | Yes | 2016-04-12 | New | 2016-04-12 | Combined | Rejected |  |  | 2016-04-22 | 2016-05-12 | 2016-04-27 | 2016-05-15 | Automated
Test Case 00174 | Test Case Name 00174 | Req 0090 | SIT | Yes | 2016-04-12 | New |  |  | Open | Creation |  | 2016-04-22 | 2016-05-12 | 2016-04-26 | 2016-05-15 14:24 | Batch
Test Case 00175 | Test Case Name 00175 | Req 0091 | SIT | Yes | 2016-03-23 | New |  |  | Open | Analysis |  | 2016-04-02 | 2016-04-20 | 2016-04-04 | 2016-04-22 19:12 | Manual
Test Case 00176 | Test Case Name 00176 | Req 0091 | SIT | Yes | 2016-03-23 | New |  |  | Open | Analysis |  | 2016-04-02 | 2016-04-23 | 2016-04-06 |  | Batch
Test Case 00177 | Test Case Name 00177 | Req 0091 | SIT | Yes | 2016-03-23 | New |  |  | Closed | Data Setup |  | 2016-04-02 | 2016-04-21 | 2016-04-06 |  | Batch
Test Case 00178 | Test Case Name 00178 | Req 0091 | Regression | Yes | 2016-03-23 | New |  |  | Open | Design |  | 2016-04-02 | 2016-04-22 | 2016-04-05 | 2016-04-26 04:48 | Batch
Test Case 00179 | Test Case Name 00179 | Req 0092 | SIT | Yes | 2016-03-23 | New | 2016-03-23 | Duplicate | Rejected |  |  | 2016-04-02 | 2016-04-24 | 2016-04-05 | 2016-04-26 04:48 | Batch
Test Case 00180 | Test Case Name 00180 | Req 0092 | SIT | Yes | 2016-03-23 | New |  |  | Closed | Creation |  | 2016-04-02 | 2016-04-25 | 2016-04-04 | 2016-04-26 19:12 | Automated
Test Case 00181 | Test Case Name 00181 | Req 0093 | SIT | Yes | 2016-03-23 | New | 2016-03-23 | Combined | Rejected |  |  | 2016-04-02 | 2016-04-21 | 2016-04-06 |  | Batch
Test Case 00182 | Test Case Name 00182 | Req 0093 | SIT | Yes | 2016-03-23 | New |  |  | Closed | Execution |  | 2016-04-02 | 2016-04-19 | 2016-04-06 | 2016-04-23 14:24 | Manual
Test Case 00183 | Test Case Name 00183 | Req 0093 | SIT | Yes | 2016-03-23 | New |  |  | Closed | Creation |  | 2016-04-02 | 2016-04-20 | 2016-04-07 | 2016-04-25 | Automated
Test Case 00184 | Test Case Name 00184 | Req 0093 | SIT | Yes | 2016-03-23 | New |  |  | Rejected | Creation |  | 2016-04-02 | 2016-04-18 | 2016-04-05 | 2016-04-22 04:48 | Manual
Test Case 00185 | Test Case Name 00185 | Req 0094 | SIT | Yes | 2016-03-28 | New |  |  | Rejected | Research |  | 2016-04-07 | 2016-04-25 | 2016-04-13 | 2016-05-01 09:36 | Manual
Test Case 00186 | Test Case Name 00186 | Req 0094 | SIT | Yes | 2016-03-28 | New |  |  | Closed | Data Setup |  | 2016-04-07 | 2016-04-26 | 2016-04-12 | 2016-04-29 | Batch
Test Case 00187 | Test Case Name 00187 | Req 0094 | SIT | Yes | 2016-03-28 | New | 2016-03-28 | Deleted Requirement | Rejected |  |  | 2016-04-07 | 2016-04-27 | 2016-04-11 | 2016-05-01 14:24 | Automated
Test Case 00188 | Test Case Name 00188 | Req 0095 | SIT | Yes | 2016-03-25 | New |  |  | Rejected | Design |  | 2016-04-04 | 2016-04-20 | 2016-04-07 |  | Manual
Test Case 00189 | Test Case Name 00189 | Req 0095 | SIT | Yes | 2016-03-25 | New |  |  | Hold | Design | Requirements | 2016-04-04 | 2016-04-23 | 2016-04-08 |  | Manual
Test Case 00190 | Test Case Name 00190 | Req 0096 | SIT | Yes | 2016-03-25 | New |  |  | Open | Data Setup |  | 2016-04-04 | 2016-04-24 | 2016-04-08 |  | Manual
Test Case 00191 | Test Case Name 00191 | Req 0097 | SIT | Yes | 2016-04-11 | New |  |  | Open | Design |  | 2016-04-21 | 2016-05-12 | 2016-04-25 | 2016-05-16 14:24 | Manual
Test Case 00192 | Test Case Name 00192 | Req 0098 | SIT | Yes | 2016-03-28 | New |  |  | Rejected | Creation |  | 2016-04-07 | 2016-04-28 | 2016-04-10 |  | Automated
Test Case 00193 | Test Case Name 00193 | Req 0098 | SIT | Yes | 2016-03-28 | New |  |  | Rejected | Creation |  | 2016-04-07 | 2016-04-28 | 2016-04-09 | 2016-04-28 19:12 | Manual
Test Case 00194 | Test Case Name 00194 | Req 0099 | SIT | Yes | 2016-03-24 | New |  |  | Rejected | Data Setup |  | 2016-04-03 |  | 2016-04-06 |  | Manual
Test Case 00195 | Test Case Name 00195 | Req 0099 | SIT | Yes | 2016-03-24 | Split | 2016-03-24 | Duplicate | Rejected |  |  | 2016-04-03 |  | 2016-04-05 |  | Manual
Test Case 00196 | Test Case Name 00196 | Req 0099 | Regression | Yes | 2016-03-24 | New |  |  | Open | Creation |  | 2016-04-03 |  | 2016-04-07 |  | Batch
Test Case 00197 | Test Case Name 00197 | Req 0099 | SIT | Yes | 2016-03-24 | New |  |  | Closed | Data Setup |  | 2016-04-03 |  | 2016-04-05 |  | Batch
Test Case 00198 | Test Case Name 00198 | Req 0099 | SIT | Yes | 2016-03-24 | New |  |  | Closed | Data Setup |  | 2016-04-03 |  | 2016-04-05 |  | Manual
Test Case 00199 | Test Case Name 00199 | Req 0099 | SIT | Yes | 2016-03-24 | New |  |  | Open | Design |  | 2016-04-03 |  | 2016-04-07 |  | Manual
Test Case 00200 | Test Case Name 00200 | Req 0099 | SIT | Yes | 2016-03-24 | New |  |  | Hold | Design | Requirements | 2016-04-03 |  | 2016-04-06 |  | Automated
Test Case 00201 | Test Case Name 00201 | Req 0099 | SIT | Yes | 2016-03-24 | New |  |  | Open | Creation |  | 2016-04-03 |  | 2016-04-05 |  | Automated
Test Case 00202 | Test Case Name 00202 | Req 0099 | SIT | Yes | 2016-03-24 | New |  |  | Hold | Data Setup | Requirements | 2016-04-03 |  | 2016-04-08 |  | Batch
Test Case 00203 | Test Case Name 00203 | Req 0099 | SIT | Yes | 2016-03-24 | New |  |  | Closed | Approval |  | 2016-04-03 |  | 2016-04-07 |  | Batch
Test Case 00204 | Test Case Name 00204 | Req 0099 | SIT | Yes | 2016-03-24 | New |  |  | Hold | Design | Requirements | 2016-04-03 |  | 2016-04-09 |  | Manual
Test Case 00205 | Test Case Name 00205 | Req 0100 | SIT | Yes | 2016-03-30 | New |  |  | Closed | Analysis |  | 2016-04-09 | 2016-04-28 | 2016-04-12 | 2016-05-02 04:48 | Batch

## Execution
Test Case ID | Execution ID | Test Execution Status | Blocked Reason | Planned Start Date | Actual Start Date | Planned End Date | Actual End Date | Fail Reason | Tester
Test Case 00001 | Exec 00001 | Execution |  | 2016-04-07 |  | 2016-04-26 |  |  | Tester 2
Test Case 00002 | Exec 00002 | Approval |  | 2016-04-13 | 2016-05-06 14:24 | 2016-05-13 | 2016-05-20 14:24 |  | Tester 3
Test Case 00003 | Exec 00003 | Approval |  | 2016-04-15 | 2016-05-17 19:12 | 2016-05-11 | 2016-05-31 04:48 |  | Tester 1
Test Case 00004 | Exec 00004 | Passed |  | 2016-04-25 | 2016-05-17 04:48 | 2016-05-14 | 2016-05-27 19:12 |  | Tester 1
Test Case 00004 | Exec 00005 | Analysis |  | 2016-04-21 | 2016-05-16 04:48 | 2016-05-16 | 2016-05-30 04:48 |  | Tester 3
Test Case 00005 | Exec 00006 | Blocked | Test Case | 2016-05-06 | 2016-05-25 14:24 | 2016-05-23 |  |  | Tester 3
Test Case 00005 | Exec 00007 | Approval |  | 2016-05-14 | 2016-05-20 14:24 | 2016-06-06 | 2016-05-31 19:12 |  | Tester 3
Test Case 00006 | Exec 00008 | Execution |  | 2016-04-13 | 2016-05-13 09:36 | 2016-05-01 | 2016-05-23 14:24 |  | Tester 1
Test Case 00007 | Exec 00009 | Planned |  | 2016-04-23 | 2016-05-11 04:48 | 2016-05-17 | 2016-05-24 19:12 |  | Tester 2
Test Case 00008 | Exec 00010 | Approval |  | 2016-04-16 | 2016-05-04 19:12 | 2016-05-09 | 2016-05-18 |  | Tester 2
Test Case 00009 | Exec 00011 | Analysis |  | 2016-04-20 | 2016-05-09 04:48 | 2016-05-16 | 2016-05-22 14:24 |  | Tester 2
Test Case 00010 | Exec 00012 | Analysis |  | 2016-04-15 | 2016-05-08 19:12 | 2016-05-08 | 2016-05-20 |  | Tester 2
Test Case 00011 | Exec 00013 | Execution |  | 2016-04-16 |  | 2016-05-12 |  |  | Tester 2
Test Case 00012 | Exec 00014 | Approval |  | 2016-04-15 |  | 2016-05-04 |  |  | Tester 2
Test Case 00013 | Exec 00015 | Approval |  | 2016-04-13 | 2016-05-11 14:24 | 2016-05-05 | 2016-05-22 09:36 |  | Tester 3
Test Case 00013 | Exec 00016 | Approval |  | 2016-04-14 | 2016-05-12 14:24 | 2016-05-05 | 2016-05-23 |  | Tester 1
Test Case 00014 | Exec 00017 | Approval |  | 2016-04-12 | 2016-05-13 14:24 | 2016-05-08 | 2016-05-27 |  | Tester 1
Test Case 00014 | Exec 00018 | Blocked | Data | 2016-04-17 | 2016-05-05 14:24 | 2016-05-04 |  |  | Tester 2
Test Case 00014 | Exec 00019 | Blocked | Test Case | 2016-04-16 | 2016-05-11 14:24 | 2016-05-13 |  |  | Tester 1
Test Case 00015 | Exec 00020 | Blocked | Test Case | 2016-04-26 | 2016-05-20 04:48 | 2016-05-18 |  |  | Tester 1
Test Case 00016 | Exec 00021 | Execution |  | 2016-04-24 |  | 2016-05-18 |  |  | Tester 1
Test Case 00016 | Exec 00022 | Passed |  | 2016-04-28 |  | 2016-05-19 |  |  | Tester 2
Test Case 00017 | Exec 00023 | Blocked | Test Case | 2016-04-28 | 2016-05-15 14:24 | 2016-05-18 |  |  | Tester 3
Test Case 00018 | Exec 00024 | Analysis |  | 2016-04-27 |  | 2016-05-28 |  |  | Tester 2
Test Case 00019 | Exec 00025 | Passed |  | 2016-04-26 |  | 2016-05-16 |  |  | Tester 1
Test Case 00020 | Exec 00026 | Execution |  | 2016-04-20 | 2016-05-03 04:48 | 2016-05-19 | 2016-05-17 19:12 |  | Tester 2
Test Case 00021 | Exec 00027 | Passed |  | 2016-04-15 | 2016-05-10 04:48 | 2016-04-30 | 2016-05-16 04:48 |  | Tester 2
Test Case 00022 | Exec 00028 | Approval |  | 2016-04-16 | 2016-05-04 | 2016-05-04 | 2016-05-13 04:48 |  | Tester 1
Test Case 00022 | Exec 00029 | Blocked | Test Case | 2016-04-21 | 2016-05-10 | 2016-05-20 |  |  | Tester 1
Test Case 00023 | Exec 00030 | Execution |  | 2016-04-22 |  | 2016-05-16 |  |  | Tester 1
Test Case 00023 | Exec 00031 | Passed |  | 2016-04-22 |  | 2016-05-15 |  |  | Tester 3
Test Case 00024 | Exec 00032 | Passed |  | 2016-04-14 | 2016-05-10 14:24 | 2016-05-06 | 2016-05-20 09:36 |  | Tester 2
Test Case 00025 | Exec 00033 | Passed |  | 2016-04-09 |  | 2016-04-28 |  |  | Tester 3
Test Case 00026 | Exec 00034 | Analysis |  | 2016-05-08 |  | 2016-06-04 |  |  | Tester 1
Test Case 00027 | Exec 00035 | Analysis |  | 2016-05-13 |  | 2016-06-06 |  |  | Tester 2
Test Case 00027 | Exec 00036 | Approval |  | 2016-05-19 |  | 2016-06-09 |  |  | Tester 1
Test Case 00028 | Exec 00037 | Passed |  | 2016-04-16 | 2016-04-30 14:24 | 2016-05-13 | 2016-05-15 09:36 |  | Tester 2
Test Case 00029 | Exec 00038 | Passed |  | 2016-04-12 | 2016-04-28 19:12 | 2016-05-06 | 2016-05-10 09:36 |  | Tester 3
Test Case 00030 | Exec 00039 | Approval |  | 2016-04-11 | 2016-04-26 04:48 | 2016-05-07 | 2016-05-09 14:24 |  | Tester 3
Test Case 00031 | Exec 00040 | Approval |  | 2016-04-14 |  | 2016-05-09 |  |  | Tester 2
Test Case 00032 | Exec 00041 | Analysis |  | 2016-04-21 | 2016-05-09 14:24 | 2016-05-18 | 2016-05-21 09:36 |  | Tester 2
Test Case 00033 | Exec 00042 | Approval |  | 2016-04-17 |  | 2016-05-15 |  |  | Tester 2
Test Case 00034 | Exec 00043 | Passed |  | 2016-04-16 |  | 2016-05-09 |  |  | Tester 2
Test Case 00034 | Exec 00044 | Analysis |  | 2016-04-17 |  | 2016-05-15 |  |  | Tester 1
Test Case 00035 | Exec 00045 | Approval |  | 2016-04-09 |  | 2016-05-01 |  |  | Tester 1
Test Case 00036 | Exec 00046 | Passed |  | 2016-04-11 |  | 2016-05-02 |  |  | Tester 2
Test Case 00036 | Exec 00047 | Blocked | Test Case | 2016-04-08 |  | 2016-04-28 |  |  | Tester 3
Test Case 00037 | Exec 00048 | Analysis |  | 2016-04-22 | 2016-05-23 04:48 | 2016-05-19 | 2016-06-06 |  | Tester 3
Test Case 00038 | Exec 00049 | Blocked | Test Case | 2016-05-03 | 2016-05-24 14:24 | 2016-05-27 |  |  | Tester 1
Test Case 00039 | Exec 00050 | Approval |  | 2016-04-25 | 2016-05-17 04:48 | 2016-05-16 | 2016-05-27 14:24 |  | Tester 2
Test Case 00039 | Exec 00051 | Approval |  | 2016-04-30 | 2016-05-21 04:48 | 2016-05-22 | 2016-06-02 |  | Tester 3
Test Case 00039 | Exec 00052 | Approval |  | 2016-04-29 | 2016-05-23 04:48 | 2016-05-21 | 2016-06-04 |  | Tester 2
Test Case 00039 | Exec 00053 | Approval |  | 2016-04-29 | 2016-05-25 04:48 | 2016-05-29 | 2016-06-08 04:48 |  | Tester 3
Test Case 00040 | Exec 00054 | Blocked | Test Case | 2016-04-29 |  | 2016-05-26 |  |  | Tester 2
Test Case 00041 | Exec 00055 | Passed |  | 2016-04-25 | 2016-05-18 04:48 | 2016-05-15 | 2016-05-29 04:48 |  | Tester 3
Test Case 00042 | Exec 00056 | Passed |  | 2016-04-17 |  | 2016-05-05 |  |  | Tester 3
Test Case 00043 | Exec 00057 | Analysis |  | 2016-05-04 | 2016-05-15 | 2016-05-31 | 2016-05-25 19:12 |  | Tester 1
Test Case 00044 | Exec 00058 | Passed |  | 2016-05-01 | 2016-05-21 19:12 | 2016-05-18 | 2016-05-31 14:24 |  | Tester 1
Test Case 00045 | Exec 00059 | Execution |  | 2016-04-19 | 2016-05-01 14:24 | 2016-05-13 | 2016-05-14 04:48 |  | Tester 2
Test Case 00046 | Exec 00060 | Approval |  | 2016-04-16 | 2016-05-07 19:12 | 2016-05-13 | 2016-05-18 14:24 |  | Tester 2
Test Case 00047 | Exec 00061 | Approval |  | 2016-04-22 | 2016-05-08 04:48 | 2016-05-18 | 2016-05-20 14:24 |  | Tester 2
Test Case 00047 | Exec 00062 | Passed |  | 2016-04-17 | 2016-05-06 04:48 | 2016-05-04 | 2016-05-14 |  | Tester 1
Test Case 00048 | Exec 00063 | Passed |  | 2016-04-19 | 2016-05-06 04:48 | 2016-05-15 | 2016-05-18 14:24 |  | Tester 2
Test Case 00049 | Exec 00064 | Analysis |  | 2016-04-15 | 2016-05-10 04:48 | 2016-05-09 | 2016-05-23 19:12 |  | Tester 3
Test Case 00050 | Exec 00065 | Execution |  | 2016-05-10 | 2016-05-28 14:24 | 2016-06-04 | 2016-06-12 14:24 |  | Tester 1
Test Case 00051 | Exec 00066 | Passed |  | 2016-05-08 | 2016-05-26 04:48 | 2016-05-31 | 2016-06-08 09:36 |  | Tester 1
Test Case 00052 | Exec 00067 | Approval |  | 2016-05-03 |  | 2016-05-30 |  |  | Tester 1
Test Case 00053 | Exec 00068 | Passed |  | 2016-04-19 | 2016-05-07 09:36 | 2016-05-07 | 2016-05-15 14:24 |  | Tester 3
Test Case 00053 | Exec 00069 | Approval |  | 2016-04-16 | 2016-05-07 09:36 | 2016-05-15 | 2016-05-21 |  | Tester 3
Test Case 00053 | Exec 00070 | Execution |  | 2016-04-15 | 2016-05-03 09:36 | 2016-05-09 | 2016-05-16 |  | Tester 2
Test Case 00054 | Exec 00071 | Blocked | Test Case | 2016-04-15 | 2016-05-08 | 2016-05-10 |  |  | Tester 3
Test Case 00055 | Exec 00072 | Execution |  | 2016-04-19 | 2016-05-02 04:48 | 2016-05-20 | 2016-05-16 14:24 |  | Tester 1
Test Case 00056 | Exec 00073 | Passed |  | 2016-04-17 |  | 2016-05-09 |  |  | Tester 2
Test Case 00057 | Exec 00074 | Passed |  | 2016-04-19 | 2016-05-04 19:12 | 2016-05-13 | 2016-05-15 09:36 |  | Tester 3
Test Case 00058 | Exec 00075 | Passed |  | 2016-04-16 | 2016-04-28 | 2016-05-09 | 2016-05-10 04:48 |  | Tester 1
Test Case 00059 | Exec 00076 | Approval |  | 2016-04-24 |  | 2016-05-21 |  |  | Tester 3
Test Case 00060 | Exec 00077 | Passed |  | 2016-04-29 |  | 2016-05-26 |  |  | Tester 3
Test Case 00060 | Exec 00078 | Execution |  | 2016-05-01 |  | 2016-06-01 |  |  | Tester 3
Test Case 00061 | Exec 00079 | Analysis |  | 2016-04-25 |  | 2016-05-17 |  |  | Tester 2
Test Case 00062 | Exec 00080 | Analysis |  | 2016-04-19 | 2016-05-07 14:24 | 2016-05-09 | 2016-05-17 14:24 |  | Tester 1
Test Case 00063 | Exec 00081 | Approval |  | 2016-04-18 |  | 2016-05-05 |  |  | Tester 2
Test Case 00064 | Exec 00082 | Analysis |  | 2016-04-19 | 2016-04-27 | 2016-05-04 | 2016-05-08 |  | Tester 1
Test Case 00065 | Exec 00083 | Passed |  | 2016-04-18 |  | 2016-05-09 |  |  | Tester 1
Test Case 00066 | Exec 00084 | Approval |  | 2016-04-27 | 2016-05-11 14:24 | 2016-05-17 | 2016-05-20 14:24 |  | Tester 1
Test Case 00067 | Exec 00085 | Passed |  | 2016-04-24 | 2016-05-03 04:48 | 2016-05-14 | 2016-05-13 04:48 |  | Tester 1
Test Case 00068 | Exec 00086 | Analysis |  | 2016-04-20 |  | 2016-05-20 |  |  | Tester 2
Test Case 00069 | Exec 00087 | Approval |  | 2016-04-29 | 2016-05-04 04:48 | 2016-05-18 | 2016-05-15 19:12 |  | Tester 2
Test Case 00069 | Exec 00088 | Analysis |  | 2016-04-24 | 2016-05-08 04:48 | 2016-05-13 | 2016-05-18 19:12 |  | Tester 3
Test Case 00070 | Exec 00089 | Analysis |  | 2016-04-14 | 2016-05-02 04:48 | 2016-05-06 | 2016-05-14 |  | Tester 2
Test Case 00071 | Exec 00090 | Execution |  | 2016-04-26 |  | 2016-05-22 |  |  | Tester 3
Test Case 00072 | Exec 00091 | Passed |  | 2016-04-10 |  | 2016-05-08 |  |  | Tester 2
Test Case 00073 | Exec 00092 | Passed |  | 2016-04-21 | 2016-04-27 | 2016-05-15 | 2016-05-10 14:24 |  | Tester 1
Test Case 00074 | Exec 00093 | Execution |  | 2016-04-12 | 2016-04-25 04:48 | 2016-04-28 | 2016-05-04 14:24 |  | Tester 2
Test Case 00074 | Exec 00094 | Approval |  | 2016-04-11 | 2016-04-28 04:48 | 2016-05-09 | 2016-05-12 09:36 |  | Tester 3
Test Case 00074 | Exec 00095 | Analysis |  | 2016-04-10 | 2016-04-30 04:48 | 2016-05-03 | 2016-05-13 09:36 |  | Tester 1
Test Case 00075 | Exec 00096 | Approval |  | 2016-04-16 | 2016-04-22 04:48 | 2016-05-10 | 2016-05-03 19:12 |  | Tester 2
Test Case 00076 | Exec 00097 | Approval |  | 2016-04-09 | 2016-04-30 19:12 | 2016-04-24 | 2016-05-10 19:12 |  | Tester 3
Test Case 00077 | Exec 00098 | Execution |  | 2016-04-28 |  | 2016-05-24 |  |  | Tester 3
Test Case 00078 | Exec 00099 | Approval |  | 2016-04-21 | 2016-05-08 19:12 | 2016-05-16 | 2016-05-21 19:12 |  | Tester 1
Test Case 00079 | Exec 00100 | Analysis |  | 2016-04-27 | 2016-05-08 14:24 | 2016-05-12 | 2016-05-16 14:24 |  | Tester 2
Test Case 00080 | Exec 00101 | Analysis |  | 2016-05-07 |  | 2016-06-02 |  |  | Tester 3
Test Case 00081 | Exec 00102 | Analysis |  | 2016-05-07 | 2016-05-21 19:12 | 2016-06-01 | 2016-06-03 19:12 |  | Tester 2
Test Case 00082 | Exec 00103 | Analysis |  | 2016-05-11 | 2016-05-25 04:48 | 2016-06-06 | 2016-06-06 14:24 |  | Tester 1
Test Case 00083 | Exec 00104 | Blocked | Test Case | 2016-04-18 |  | 2016-05-16 |  |  | Tester 2
Test Case 00084 | Exec 00105 | Passed |  | 2016-04-23 | 2016-05-04 14:24 | 2016-05-12 | 2016-05-15 04:48 |  | Tester 1
Test Case 00084 | Exec 00106 | Execution |  | 2016-04-22 | 2016-05-02 14:24 | 2016-05-13 | 2016-05-15 |  | Tester 1
Test Case 00085 | Exec 00107 | Analysis |  | 2016-04-25 | 2016-05-03 09:36 | 2016-05-22 | 2016-05-17 04:48 |  | Tester 1
Test Case 00085 | Exec 00108 | Approval |  | 2016-04-21 | 2016-05-06 09:36 | 2016-05-22 | 2016-05-20 19:12 |  | Tester 2
Test Case 00085 | Exec 00109 | Analysis |  | 2016-04-22 | 2016-05-03 09:36 | 2016-05-18 | 2016-05-15 19:12 |  | Tester 2
Test Case 00086 | Exec 00110 | Passed |  | 2016-04-12 | 2016-04-28 04:48 | 2016-05-11 | 2016-05-12 19:12 |  | Tester 3
Test Case 00087 | Exec 00111 | Approval |  | 2016-04-14 |  | 2016-05-06 |  |  | Tester 3
Test Case 00088 | Exec 00112 | Approval |  | 2016-04-21 | 2016-05-12 19:12 | 2016-05-14 | 2016-05-25 |  | Tester 2
Test Case 00089 | Exec 00113 | Execution |  | 2016-04-22 | 2016-05-08 14:24 | 2016-05-16 | 2016-05-21 04:48 |  | Tester 3
Test Case 00090 | Exec 00114 | Passed |  | 2016-04-25 | 2016-05-14 04:48 | 2016-05-15 | 2016-05-24 04:48 |  | Tester 1
Test Case 00091 | Exec 00115 | Passed |  | 2016-04-29 |  | 2016-05-19 |  |  | Tester 1
Test Case 00092 | Exec 00116 | Execution |  | 2016-04-25 | 2016-05-15 | 2016-05-17 | 2016-05-25 19:12 |  | Tester 1
Test Case 00092 | Exec 00117 | Execution |  | 2016-04-28 | 2016-05-13 | 2016-05-20 | 2016-05-22 19:12 |  | Tester 1
Test Case 00093 | Exec 00118 | Approval |  | 2016-04-06 | 2016-05-09 04:48 | 2016-04-28 | 2016-05-18 |  | Tester 1
Test Case 00093 | Exec 00119 | Execution |  | 2016-04-14 | 2016-05-13 04:48 | 2016-05-12 | 2016-05-25 09:36 |  | Tester 3
Test Case 00093 | Exec 00120 | Passed |  | 2016-04-07 | 2016-05-15 04:48 | 2016-04-30 | 2016-05-28 09:36 |  | Tester 2
Test Case 00094 | Exec 00121 | Analysis |  | 2016-04-17 | 2016-05-01 14:24 | 2016-05-06 | 2016-05-12 04:48 |  | Tester 1
Test Case 00095 | Exec 00122 | Blocked | Test Case | 2016-05-04 |  | 2016-05-20 |  |  | Tester 1
Test Case 00096 | Exec 00123 | Approval |  | 2016-04-27 | 2016-05-14 14:24 | 2016-05-15 | 2016-05-25 19:12 |  | Tester 2
Test Case 00096 | Exec 00124 | Approval |  | 2016-04-23 | 2016-05-13 14:24 | 2016-05-08 | 2016-05-22 14:24 |  | Tester 1
Test Case 00097 | Exec 00125 | Passed |  | 2016-04-25 | 2016-05-14 14:24 | 2016-05-19 | 2016-05-25 04:48 |  | Tester 1
Test Case 00098 | Exec 00126 | Passed |  | 2016-05-08 |  | 2016-05-26 |  |  | Tester 1
Test Case 00098 | Exec 00127 | Execution |  | 2016-05-14 |  | 2016-06-14 |  |  | Tester 1
Test Case 00099 | Exec 00128 | Blocked | Test Case | 2016-04-30 |  | 2016-05-24 |  |  | Tester 2
Test Case 00100 | Exec 00129 | Blocked | Test Case | 2016-04-28 |  | 2016-05-22 |  |  | Tester 1
Test Case 00101 | Exec 00130 | Analysis |  | 2016-05-04 |  | 2016-06-01 |  |  | Tester 1
Test Case 00102 | Exec 00131 | Passed |  | 2016-04-28 |  | 2016-05-22 |  |  | Tester 1
Test Case 00103 | Exec 00132 | Planned |  | 2016-04-27 | 2016-05-13 04:48 | 2016-05-21 | 2016-05-26 19:12 |  | Tester 3
Test Case 00104 | Exec 00133 | Approval |  | 2016-04-29 | 2016-05-15 04:48 | 2016-05-27 | 2016-05-30 09:36 |  | Tester 1
Test Case 00105 | Exec 00134 | Planned |  | 2016-04-12 | 2016-05-02 14:24 | 2016-04-30 | 2016-05-12 19:12 |  | Tester 1
Test Case 00106 | Exec 00135 | Approval |  | 2016-04-13 |  | 2016-04-29 |  |  | Tester 1
Test Case 00106 | Exec 00136 | Approval |  | 2016-04-07 |  | 2016-04-26 |  |  | Tester 2
Test Case 00107 | Exec 00137 | Execution |  | 2016-04-12 |  | 2016-05-09 |  |  | Tester 3
Test Case 00108 | Exec 00138 | Analysis |  | 2016-04-10 |  | 2016-05-06 |  |  | Tester 1
Test Case 00109 | Exec 00139 | Execution |  | 2016-04-14 |  | 2016-05-10 |  |  | Tester 1
Test Case 00110 | Exec 00140 | Approval |  | 2016-05-14 |  | 2016-06-07 |  |  | Tester 2
Test Case 00110 | Exec 00141 | Approval |  | 2016-05-17 |  | 2016-06-08 |  |  | Tester 1
Test Case 00111 | Exec 00142 | Passed |  | 2016-05-19 |  | 2016-06-15 |  |  | Tester 1
Test Case 00111 | Exec 00143 | Approval |  | 2016-05-18 |  | 2016-06-08 |  |  | Tester 2
Test Case 00112 | Exec 00144 | Passed |  | 2016-04-21 |  | 2016-05-13 |  |  | Tester 2
Test Case 00113 | Exec 00145 | Approval |  | 2016-04-19 |  | 2016-05-15 |  |  | Tester 2
Test Case 00114 | Exec 00146 | Approval |  | 2016-04-25 | 2016-05-05 14:24 | 2016-05-20 | 2016-05-17 14:24 |  | Tester 3
Test Case 00114 | Exec 00147 | Planned |  | 2016-04-22 | 2016-05-08 14:24 | 2016-05-08 | 2016-05-16 |  | Tester 1
Test Case 00115 | Exec 00148 | Approval |  | 2016-04-13 |  | 2016-05-05 |  |  | Tester 1
Test Case 00116 | Exec 00149 | Passed |  | 2016-04-12 | 2016-04-25 19:12 | 2016-05-04 | 2016-05-07 14:24 |  | Tester 2
Test Case 00117 | Exec 00150 | Blocked | Test Case | 2016-04-15 |  | 2016-05-09 |  |  | Tester 1
Test Case 00117 | Exec 00151 | Passed |  | 2016-04-12 |  | 2016-05-10 |  |  | Tester 2
Test Case 00118 | Exec 00152 | Execution |  | 2016-04-13 | 2016-04-29 14:24 | 2016-05-09 | 2016-05-13 |  | Tester 1
Test Case 00119 | Exec 00153 | Approval |  | 2016-04-26 |  | 2016-05-18 |  |  | Tester 3
Test Case 00120 | Exec 00154 | Blocked | Test Case | 2016-04-28 |  | 2016-05-27 |  |  | Tester 3
Test Case 00120 | Exec 00155 | Approval |  | 2016-04-29 |  | 2016-05-28 |  |  | Tester 3
Test Case 00121 | Exec 00156 | Analysis |  | 2016-04-30 |  | 2016-05-24 |  |  | Tester 1
Test Case 00122 | Exec 00157 | Planned |  | 2016-05-02 | 2016-05-30 04:48 | 2016-05-19 | 2016-06-09 |  | Tester 3
Test Case 00123 | Exec 00158 | Analysis |  | 2016-04-29 | 2016-05-16 04:48 | 2016-05-23 | 2016-05-27 19:12 |  | Tester 3
Test Case 00124 | Exec 00159 | Approval |  | 2016-05-06 | 2016-05-18 04:48 | 2016-05-28 | 2016-05-29 |  | Tester 3
Test Case 00125 | Exec 00160 | Approval |  | 2016-04-24 | 2016-05-10 04:48 | 2016-05-17 | 2016-05-22 09:36 |  | Tester 1
Test Case 00125 | Exec 00161 | Passed |  | 2016-04-18 | 2016-05-15 04:48 | 2016-05-11 | 2016-05-24 09:36 |  | Tester 1
Test Case 00126 | Exec 00162 | Blocked | Test Case | 2016-04-17 |  | 2016-05-09 |  |  | Tester 2
Test Case 00126 | Exec 00163 | Passed |  | 2016-04-17 |  | 2016-05-20 |  |  | Tester 3
Test Case 00127 | Exec 00164 | Blocked | Test Case | 2016-04-25 | 2016-05-12 14:24 | 2016-05-20 |  |  | Tester 2
Test Case 00127 | Exec 00165 | Execution |  | 2016-04-19 | 2016-05-11 14:24 | 2016-05-12 | 2016-05-21 19:12 |  | Tester 2
Test Case 00128 | Exec 00166 | Passed |  | 2016-04-20 | 2016-05-16 | 2016-05-12 | 2016-05-25 19:12 |  | Tester 3
Test Case 00128 | Exec 00167 | Passed |  | 2016-04-19 | 2016-05-14 | 2016-05-14 | 2016-05-28 |  | Tester 1
Test Case 00129 | Exec 00168 | Blocked | Data | 2016-04-25 | 2016-05-10 14:24 | 2016-05-21 |  |  | Tester 1
Test Case 00130 | Exec 00169 | Approval |  | 2016-04-18 |  | 2016-05-15 |  |  | Tester 1
Test Case 00131 | Exec 00170 | Blocked | Test Case | 2016-04-27 | 2016-05-18 14:24 | 2016-05-18 |  |  | Tester 3
Test Case 00132 | Exec 00171 | Analysis |  | 2016-04-25 | 2016-05-18 14:24 | 2016-05-22 | 2016-05-30 09:36 |  | Tester 3
Test Case 00132 | Exec 00172 | Passed |  | 2016-04-29 | 2016-05-19 14:24 | 2016-05-24 | 2016-06-02 14:24 |  | Tester 3
Test Case 00133 | Exec 00173 | Passed |  | 2016-04-30 | 2016-05-21 04:48 | 2016-05-24 | 2016-06-01 19:12 |  | Tester 1
Test Case 00134 | Exec 00174 | Approval |  | 2016-05-14 |  | 2016-06-06 |  |  | Tester 2
Test Case 00135 | Exec 00175 | Analysis |  | 2016-04-14 | 2016-05-06 14:24 | 2016-05-08 | 2016-05-18 04:48 |  | Tester 3
Test Case 00136 | Exec 00176 | Passed |  | 2016-04-25 | 2016-05-06 | 2016-05-13 | 2016-05-15 04:48 |  | Tester 1
Test Case 00137 | Exec 00177 | Passed |  | 2016-04-21 | 2016-05-07 04:48 | 2016-05-18 | 2016-05-21 |  | Tester 3
Test Case 00138 | Exec 00178 | Analysis |  | 2016-04-24 |  | 2016-05-19 |  |  | Tester 2
Test Case 00138 | Exec 00179 | Analysis |  | 2016-04-20 |  | 2016-05-07 |  |  | Tester 3
Test Case 00138 | Exec 00180 | Approval |  | 2016-04-20 |  | 2016-05-19 |  |  | Tester 3
Test Case 00139 | Exec 00181 | Passed |  | 2016-04-18 |  | 2016-05-13 |  |  | Tester 3
Test Case 00140 | Exec 00182 | Passed |  | 2016-04-20 |  | 2016-05-09 |  |  | Tester 3
Test Case 00141 | Exec 00183 | Passed |  | 2016-05-15 | 2016-05-31 14:24 | 2016-06-05 | 2016-06-13 |  | Tester 1
Test Case 00141 | Exec 00184 | Execution |  | 2016-05-14 | 2016-05-29 14:24 | 2016-06-07 | 2016-06-09 04:48 |  | Tester 1
Test Case 00142 | Exec 00185 | Analysis |  | 2016-04-08 | 2016-04-28 04:48 | 2016-05-02 | 2016-05-08 19:12 |  | Tester 3
Test Case 00142 | Exec 00186 | Approval |  | 2016-04-07 | 2016-04-28 04:48 | 2016-05-01 | 2016-05-10 19:12 |  | Tester 1
Test Case 00143 | Exec 00187 | Approval |  | 2016-04-06 | 2016-05-01 04:48 | 2016-05-06 | 2016-05-14 04:48 |  | Tester 2
Test Case 00143 | Exec 00188 | Approval |  | 2016-04-09 | 2016-05-05 04:48 | 2016-05-02 | 2016-05-17 09:36 |  | Tester 3
Test Case 00144 | Exec 00189 | Blocked | Test Case | 2016-04-11 | 2016-05-03 | 2016-04-30 |  |  | Tester 1
Test Case 00145 | Exec 00190 | Passed |  | 2016-04-14 |  | 2016-05-03 |  |  | Tester 2
Test Case 00146 | Exec 00191 | Blocked | Test Case | 2016-05-06 | 2016-05-16 04:48 | 2016-05-31 |  |  | Tester 2
Test Case 00147 | Exec 00192 | Approval |  | 2016-04-30 | 2016-05-12 14:24 | 2016-05-28 | 2016-05-27 19:12 |  | Tester 1
Test Case 00148 | Exec 00193 | Analysis |  | 2016-05-02 | 2016-05-19 19:12 | 2016-05-26 | 2016-06-02 09:36 |  | Tester 2
Test Case 00149 | Exec 00194 | Execution |  | 2016-04-11 | 2016-05-02 14:24 | 2016-05-09 | 2016-05-16 19:12 |  | Tester 1
Test Case 00150 | Exec 00195 | Approval |  | 2016-04-17 |  | 2016-05-09 |  |  | Tester 2
Test Case 00151 | Exec 00196 | Blocked | Test Case | 2016-04-18 | 2016-05-09 19:12 | 2016-05-07 |  |  | Tester 1
Test Case 00152 | Exec 00197 | Approval |  | 2016-04-20 |  | 2016-05-13 |  |  | Tester 3
Test Case 00152 | Exec 00198 | Approval |  | 2016-04-21 |  | 2016-05-20 |  |  | Tester 2
Test Case 00153 | Exec 00199 | Blocked | Test Case | 2016-04-13 | 2016-05-05 04:48 | 2016-05-07 |  |  | Tester 2
Test Case 00154 | Exec 00200 | Passed |  | 2016-04-15 | 2016-05-06 14:24 | 2016-05-03 | 2016-05-15 19:12 |  | Tester 1
Test Case 00155 | Exec 00201 | Analysis |  | 2016-04-21 | 2016-05-04 14:24 | 2016-05-07 | 2016-05-13 |  | Tester 3
Test Case 00156 | Exec 00202 | Analysis |  | 2016-04-13 | 2016-05-11 14:24 | 2016-05-02 | 2016-05-20 04:48 |  | Tester 1
Test Case 00157 | Exec 00203 | Approval |  | 2016-04-17 | 2016-05-10 14:24 | 2016-05-16 | 2016-05-24 04:48 |  | Tester 1
Test Case 00158 | Exec 00204 | Approval |  | 2016-05-02 | 2016-05-16 19:12 | 2016-05-28 | 2016-05-28 04:48 |  | Tester 3
Test Case 00159 | Exec 00205 | Approval |  | 2016-05-04 | 2016-05-19 19:12 | 2016-06-03 | 2016-06-03 19:12 |  | Tester 3
Test Case 00160 | Exec 00206 | Passed |  | 2016-04-28 | 2016-05-19 04:48 | 2016-05-24 | 2016-05-30 14:24 |  | Tester 2
Test Case 00161 | Exec 00207 | Approval |  | 2016-05-02 |  | 2016-05-26 |  |  | Tester 2
Test Case 00162 | Exec 00208 | Approval |  | 2016-04-22 | 2016-05-08 04:48 | 2016-05-09 | 2016-05-18 |  | Tester 1
Test Case 00163 | Exec 00209 | Analysis |  | 2016-04-19 |  | 2016-05-12 |  |  | Tester 3
Test Case 00164 | Exec 00210 | Planned |  | 2016-05-09 |  | 2016-05-31 |  |  | Tester 3
Test Case 00165 | Exec 00211 | Approval |  | 2016-04-18 | 2016-05-13 | 2016-05-07 | 2016-05-22 14:24 |  | Tester 3
Test Case 00166 | Exec 00212 | Analysis |  | 2016-04-16 | 2016-04-27 14:24 | 2016-05-10 | 2016-05-10 04:48 |  | Tester 1
Test Case 00166 | Exec 00213 | Planned |  | 2016-04-18 | 2016-04-26 14:24 | 2016-05-13 | 2016-05-06 14:24 |  | Tester 1
Test Case 00167 | Exec 00214 | Analysis |  | 2016-04-13 | 2016-04-23 14:24 | 2016-05-07 | 2016-05-06 04:48 |  | Tester 2
Test Case 00167 | Exec 00215 | Execution |  | 2016-04-12 | 2016-04-22 14:24 | 2016-05-02 | 2016-05-02 14:24 |  | Tester 2
Test Case 00168 | Exec 00216 | Analysis |  | 2016-04-18 | 2016-05-17 04:48 | 2016-05-08 | 2016-05-27 04:48 |  | Tester 1
Test Case 00169 | Exec 00217 | Approval |  | 2016-04-17 | 2016-05-06 04:48 | 2016-05-05 | 2016-05-16 09:36 |  | Tester 2
Test Case 00170 | Exec 00218 | Passed |  | 2016-04-25 |  | 2016-05-22 |  |  | Tester 1
Test Case 00170 | Exec 00219 | Analysis |  | 2016-04-25 |  | 2016-05-19 |  |  | Tester 1
Test Case 00171 | Exec 00220 | Passed |  | 2016-04-21 | 2016-05-07 04:48 | 2016-05-16 | 2016-05-20 04:48 |  | Tester 3
Test Case 00172 | Exec 00221 | Blocked | Test Case | 2016-05-04 |  | 2016-05-29 |  |  | Tester 2
Test Case 00173 | Exec 00222 | Execution |  | 2016-05-07 | 2016-05-17 | 2016-05-29 | 2016-05-27 19:12 |  | Tester 1
Test Case 00173 | Exec 00223 | Blocked | Test Case | 2016-05-02 | 2016-05-16 | 2016-05-28 |  |  | Tester 3
Test Case 00173 | Exec 00224 | Approval |  | 2016-05-01 | 2016-05-17 | 2016-05-22 | 2016-05-27 09:36 |  | Tester 2
Test Case 00174 | Exec 00225 | Approval |  | 2016-04-28 | 2016-05-26 14:24 | 2016-05-21 | 2016-06-06 19:12 |  | Tester 3
Test Case 00175 | Exec 00226 | Passed |  | 2016-04-08 | 2016-05-01 19:12 | 2016-04-26 | 2016-05-10 |  | Tester 1
Test Case 00176 | Exec 00227 | Approval |  | 2016-04-16 |  | 2016-05-06 |  |  | Tester 1
Test Case 00177 | Exec 00228 | Passed |  | 2016-04-11 |  | 2016-05-02 |  |  | Tester 2
Test Case 00178 | Exec 00229 | Passed |  | 2016-04-11 | 2016-04-30 04:48 | 2016-05-12 | 2016-05-14 14:24 |  | Tester 2
Test Case 00179 | Exec 00230 | Blocked | Test Case | 2016-04-14 | 2016-05-03 04:48 | 2016-05-03 |  |  | Tester 1
Test Case 00180 | Exec 00231 | Passed |  | 2016-04-10 | 2016-05-03 19:12 | 2016-05-06 | 2016-05-15 04:48 |  | Tester 2
Test Case 00181 | Exec 00232 | Approval |  | 2016-04-07 |  | 2016-05-01 |  |  | Tester 1
Test Case 00181 | Exec 00233 | Approval |  | 2016-04-12 |  | 2016-05-04 |  |  | Tester 1
Test Case 00181 | Exec 00234 | Approval |  | 2016-04-18 |  | 2016-05-12 |  |  | Tester 3
Test Case 00181 | Exec 00235 | Passed |  | 2016-04-11 |  | 2016-05-09 |  |  | Tester 1
Test Case 00182 | Exec 00236 | Approval |  | 2016-04-06 | 2016-04-24 14:24 | 2016-04-29 | 2016-05-03 19:12 |  | Tester 1
Test Case 00183 | Exec 00237 | Blocked | Test Case | 2016-04-13 | 2016-04-28 | 2016-05-07 |  |  | Tester 2
Test Case 00184 | Exec 00238 | Approval |  | 2016-04-16 | 2016-04-28 04:48 | 2016-05-04 | 2016-05-06 09:36 |  | Tester 3
Test Case 00185 | Exec 00239 | Execution |  | 2016-04-17 | 2016-05-11 09:36 | 2016-05-16 | 2016-05-27 |  | Tester 1
Test Case 00186 | Exec 00240 | Blocked | Resources | 2016-04-15 | 2016-05-06 | 2016-05-02 |  |  | Tester 3
Test Case 00187 | Exec 00241 | Planned |  | 2016-04-17 | 2016-05-07 14:24 | 2016-05-04 | 2016-05-16 09:36 |  | Tester 3
Test Case 00188 | Exec 00242 | Passed |  | 2016-04-17 |  | 2016-05-19 |  |  | Tester 3
Test Case 00189 | Exec 00243 | Analysis |  | 2016-04-16 |  | 2016-05-06 |  |  | Tester 2
Test Case 00190 | Exec 00244 | Approval |  | 2016-04-12 |  | 2016-05-17 |  |  | Tester 3
Test Case 00190 | Exec 00245 | Approval |  | 2016-04-13 |  | 2016-05-08 |  |  | Tester 1
Test Case 00191 | Exec 00246 | Approval |  | 2016-05-05 | 2016-05-24 14:24 | 2016-05-30 | 2016-06-04 14:24 |  | Tester 3
Test Case 00191 | Exec 00247 | Execution |  | 2016-05-03 | 2016-05-22 14:24 | 2016-05-26 | 2016-06-01 19:12 |  | Tester 3
Test Case 00192 | Exec 00248 | Execution |  | 2016-04-15 |  | 2016-05-05 |  |  | Tester 2
Test Case 00193 | Exec 00249 | Approval |  | 2016-04-13 | 2016-05-06 19:12 | 2016-05-07 | 2016-05-18 09:36 |  | Tester 2
Test Case 00194 | Exec 00250 | Execution |  | 2016-04-15 |  | 2016-05-13 |  |  | Tester 2
Test Case 00194 | Exec 00251 | Analysis |  | 2016-04-14 |  | 2016-05-06 |  |  | Tester 3
Test Case 00195 | Exec 00252 | Passed |  | 2016-04-16 |  | 2016-05-09 |  |  | Tester 1
Test Case 00196 | Exec 00253 | Approval |  | 2016-04-15 |  | 2016-05-14 |  |  | Tester 2
Test Case 00196 | Exec 00254 | Analysis |  | 2016-04-09 |  | 2016-05-04 |  |  | Tester 3
Test Case 00197 | Exec 00255 | Approval |  | 2016-04-13 |  | 2016-05-13 |  |  | Tester 1
Test Case 00198 | Exec 00256 | Passed |  | 2016-04-08 |  | 2016-05-10 |  |  | Tester 2
Test Case 00198 | Exec 00257 | Execution |  | 2016-04-13 |  | 2016-05-09 |  |  | Tester 2
Test Case 00198 | Exec 00258 | Execution |  | 2016-04-13 |  | 2016-05-08 |  |  | Tester 1
Test Case 00199 | Exec 00259 | Approval |  | 2016-04-07 |  | 2016-05-04 |  |  | Tester 2
Test Case 00200 | Exec 00260 | Passed |  | 2016-04-12 |  | 2016-05-11 |  |  | Tester 1
Test Case 00200 | Exec 00261 | Execution |  | 2016-04-10 |  | 2016-04-30 |  |  | Tester 3
Test Case 00200 | Exec 00262 | Blocked | Test Case | 2016-04-11 |  | 2016-05-04 |  |  | Tester 1
Test Case 00200 | Exec 00263 | Blocked | Test Case | 2016-04-14 |  | 2016-05-06 |  |  | Tester 1
Test Case 00201 | Exec 00264 | Analysis |  | 2016-04-13 |  | 2016-05-09 |  |  | Tester 1
Test Case 00202 | Exec 00265 | Passed |  | 2016-04-13 |  | 2016-05-05 |  |  | Tester 2
Test Case 00203 | Exec 00266 | Passed |  | 2016-04-11 |  | 2016-04-28 |  |  | Tester 3
Test Case 00204 | Exec 00267 | Analysis |  | 2016-04-15 |  | 2016-05-11 |  |  | Tester 1
Test Case 00205 | Exec 00268 | Blocked | Test Case | 2016-04-12 | 2016-05-06 04:48 | 2016-05-01 |  |  | Tester 3

## Defects
Defect ID | Name | Test Case ID | Execution ID | Priority | Severity | Defect Type | Status | Created Date | Closed Date
Defect 00002 | Defect Name00002 | Test Case 00002 | Exec 00002 | Med | Med | Environment | Open | 2016-05-07 07:34
Defect 00003 | Defect Name00003 | Test Case 00003 | Exec 00003 | Med | High | Code | Open | 2016-05-18 00:38
Defect 00004 | Defect Name00004 | Test Case 00004 | Exec 00004 | Low | Med | Invalid | Open | 2016-05-18 23:34
Defect 00005 | Defect Name00005 | Test Case 00004 | Exec 00005 | High | Med | Code | Open | 2016-05-19 17:56
Defect 00006 | Defect Name00006 | Test Case 00005 | Exec 00006 | High | Low | Invalid | Open | 2016-05-28 22:42
Defect 00007 | Defect Name00007 | Test Case 00005 | Exec 00007 | Med | High | Code | Open | 2016-05-21 17:37
Defect 00010 | Defect Name00010 | Test Case 00008 | Exec 00010 | Med | Low | Environment | Open | 2016-05-06 13:40
Defect 00011 | Defect Name00011 | Test Case 00009 | Exec 00011 | Med | Low | Invalid | Hold | 2016-05-12 22:53
Defect 00012 | Defect Name00012 | Test Case 00010 | Exec 00012 | High | Med | Code | Invalid | 2016-05-12 06:11
Defect 00015 | Defect Name00015 | Test Case 00013 | Exec 00015 | Med | Low | Code | Open | 2016-05-16 04:19
Defect 00018 | Defect Name00018 | Test Case 00014 | Exec 00018 | Low | Med | Code | Open | 2016-05-07 01:37
Defect 00019 | Defect Name00019 | Test Case 00014 | Exec 00019 | Med | Low | Environment | Open | 2016-05-13 13:35
Defect 00020 | Defect Name00020 | Test Case 00015 | Exec 00020 | Low | Low | Code | Hold | 2016-05-21 02:28
Defect 00023 | Defect Name00023 | Test Case 00017 | Exec 00023 | Low | Med | Code | Open | 2016-05-17 01:11
Defect 00027 | Defect Name00027 | Test Case 00021 | Exec 00027 | Med | Med | Code | Invalid | 2016-05-14 10:59
Defect 00029 | Defect Name00029 | Test Case 00022 | Exec 00029 | Med | Low | Code | Closed | 2016-05-10 02:52 | 2016-05-10 05:26
Defect 00032 | Defect Name00032 | Test Case 00024 | Exec 00032 | Med | High | Code | Open | 2016-05-11 20:14
Defect 00038 | Defect Name00038 | Test Case 00029 | Exec 00038 | Med | Med | Code | Open | 2016-05-02 13:37
Defect 00041 | Defect Name00041 | Test Case 00032 | Exec 00041 | Med | Med | Code | Hold | 2016-05-13 13:04
Defect 00048 | Defect Name00048 | Test Case 00037 | Exec 00048 | Med | Med | Environment | Open | 2016-05-26 23:33
Defect 00049 | Defect Name00049 | Test Case 00038 | Exec 00049 | Med | High | Code | Open | 2016-05-27 07:32
Defect 00050 | Defect Name00050 | Test Case 00039 | Exec 00050 | Med | Med | Environment | Open | 2016-05-18 18:55
Defect 00051 | Defect Name00051 | Test Case 00039 | Exec 00051 | Low | Low | Invalid | Hold | 2016-05-25 12:18
Defect 00052 | Defect Name00052 | Test Case 00039 | Exec 00052 | Med | High | Code | Hold | 2016-05-26 18:10
Defect 00053 | Defect Name00053 | Test Case 00039 | Exec 00053 | Low | Med | Environment | Hold | 2016-05-25 16:10
Defect 00055 | Defect Name00055 | Test Case 00041 | Exec 00055 | Low | Med | Invalid | Open | 2016-05-19 12:26
Defect 00058 | Defect Name00058 | Test Case 00044 | Exec 00058 | Med | High | Code | Open | 2016-05-22 23:38
Defect 00061 | Defect Name00061 | Test Case 00047 | Exec 00061 | Low | Low | Requirements | Open | 2016-05-09 05:52
Defect 00062 | Defect Name00062 | Test Case 00047 | Exec 00062 | Med | Med | Environment | Hold | 2016-05-10 01:44
Defect 00063 | Defect Name00063 | Test Case 00048 | Exec 00063 | Med | Med | Code | Closed | 2016-05-09 08:54 | 2016-05-11 13:53
Defect 00064 | Defect Name00064 | Test Case 00049 | Exec 00064 | Med | Med | Code | Duplicate | 2016-05-15 04:21
Defect 00066 | Defect Name00066 | Test Case 00051 | Exec 00066 | Low | High | Code | Closed | 2016-05-29 16:07 | 2016-06-02 08:49
Defect 00068 | Defect Name00068 | Test Case 00053 | Exec 00068 | Med | Med | Code | Open | 2016-05-08 14:39
Defect 00069 | Defect Name00069 | Test Case 00053 | Exec 00069 | Med | High | Code | Open | 2016-05-07 15:24
Defect 00071 | Defect Name00071 | Test Case 00054 | Exec 00071 | Med | High | Environment | Duplicate | 2016-05-12 13:40
Defect 00074 | Defect Name00074 | Test Case 00057 | Exec 00074 | Med | Low | Invalid | Hold | 2016-05-08 11:39
Defect 00075 | Defect Name00075 | Test Case 00058 | Exec 00075 | Low | Med | Design | Hold | 2016-04-29 01:29
Defect 00082 | Defect Name00082 | Test Case 00064 | Exec 00082 | High | Med | Code | Hold | 2016-04-28 12:09
Defect 00084 | Defect Name00084 | Test Case 00066 | Exec 00084 | Med | High | Environment | Invalid | 2016-05-15 22:11
Defect 00085 | Defect Name00085 | Test Case 00067 | Exec 00085 | High | Low | Code | Open | 2016-05-04 02:59
Defect 00088 | Defect Name00088 | Test Case 00069 | Exec 00088 | Med | High | Design | Duplicate | 2016-05-11 23:29
Defect 00089 | Defect Name00089 | Test Case 00070 | Exec 00089 | Low | Med | Code | Invalid | 2016-05-03 18:36
Defect 00094 | Defect Name00094 | Test Case 00074 | Exec 00094 | Low | High | Design | Open | 2016-04-30 14:33
Defect 00095 | Defect Name00095 | Test Case 00074 | Exec 00095 | High | High | Environment | Open | 2016-04-30 19:00
Defect 00096 | Defect Name00096 | Test Case 00075 | Exec 00096 | High | High | Code | Open | 2016-04-23 11:08
Defect 00097 | Defect Name00097 | Test Case 00076 | Exec 00097 | Low | Low | Code | Open | 2016-05-01 06:58
Defect 00099 | Defect Name00099 | Test Case 00078 | Exec 00099 | High | High | Design | Open | 2016-05-12 12:23
Defect 00100 | Defect Name00100 | Test Case 00079 | Exec 00100 | Med | Low | Code | Open | 2016-05-09 18:13
Defect 00102 | Defect Name00102 | Test Case 00081 | Exec 00102 | High | Med | Code | Open | 2016-05-23 03:54
Defect 00103 | Defect Name00103 | Test Case 00082 | Exec 00103 | Med | Low | Code | Open | 2016-05-29 12:54
Defect 00105 | Defect Name00105 | Test Case 00084 | Exec 00105 | Low | Med | Requirements | Duplicate | 2016-05-08 06:13
Defect 00107 | Defect Name00107 | Test Case 00085 | Exec 00107 | Med | Low | Code | Open | 2016-05-05 02:52
Defect 00108 | Defect Name00108 | Test Case 00085 | Exec 00108 | Med | High | Code | Closed | 2016-05-07 17:09 | 2016-05-10 08:10
Defect 00109 | Defect Name00109 | Test Case 00085 | Exec 00109 | Med | Med | Invalid | Open | 2016-05-05 00:43
Defect 00112 | Defect Name00112 | Test Case 00088 | Exec 00112 | Med | Low | Code | Open | 2016-05-13 22:51
Defect 00114 | Defect Name00114 | Test Case 00090 | Exec 00114 | Low | High | Environment | Open | 2016-05-18 04:34
Defect 00118 | Defect Name00118 | Test Case 00093 | Exec 00118 | Med | Med | Code | Open | 2016-05-10 14:45
Defect 00120 | Defect Name00120 | Test Case 00093 | Exec 00120 | Med | High | Code | Open | 2016-05-19 00:54
Defect 00121 | Defect Name00121 | Test Case 00094 | Exec 00121 | High | Med | Code | Hold | 2016-05-06 00:15
Defect 00123 | Defect Name00123 | Test Case 00096 | Exec 00123 | Low | Med | Code | Hold | 2016-05-15 06:43
Defect 00124 | Defect Name00124 | Test Case 00096 | Exec 00124 | High | High | Code | Open | 2016-05-18 11:04
Defect 00125 | Defect Name00125 | Test Case 00097 | Exec 00125 | Low | Med | Code | Duplicate | 2016-05-15 16:06
Defect 00133 | Defect Name00133 | Test Case 00104 | Exec 00133 | High | Med | Code | Closed | 2016-05-16 20:56 | 2016-05-18 06:05
Defect 00146 | Defect Name00146 | Test Case 00114 | Exec 00146 | Med | Med | Code | Open | 2016-05-09 14:04
Defect 00149 | Defect Name00149 | Test Case 00116 | Exec 00149 | Med | Med | Code | Invalid | 2016-04-28 22:15
Defect 00158 | Defect Name00158 | Test Case 00123 | Exec 00158 | High | Med | Code | Hold | 2016-05-16 19:45
Defect 00159 | Defect Name00159 | Test Case 00124 | Exec 00159 | Med | Low | Code | Open | 2016-05-19 05:24
Defect 00160 | Defect Name00160 | Test Case 00125 | Exec 00160 | High | Med | Code | Hold | 2016-05-12 22:58
Defect 00161 | Defect Name00161 | Test Case 00125 | Exec 00161 | Med | Med | Environment | Open | 2016-05-17 13:46
Defect 00164 | Defect Name00164 | Test Case 00127 | Exec 00164 | Med | Med | Code | Hold | 2016-05-12 19:55
Defect 00167 | Defect Name00167 | Test Case 00128 | Exec 00167 | Low | High | Invalid | Open | 2016-05-18 15:49
Defect 00168 | Defect Name00168 | Test Case 00129 | Exec 00168 | Low | Low | Environment | Open | 2016-05-13 02:16
Defect 00170 | Defect Name00170 | Test Case 00131 | Exec 00170 | High | Med | Code | Invalid | 2016-05-22 22:48
Defect 00171 | Defect Name00171 | Test Case 00132 | Exec 00171 | Low | High | Invalid | Open | 2016-05-19 20:54
Defect 00173 | Defect Name00173 | Test Case 00133 | Exec 00173 | High | Low | Environment | Duplicate | 2016-05-23 08:32
Defect 00175 | Defect Name00175 | Test Case 00135 | Exec 00175 | High | High | Code | Hold | 2016-05-11 12:44
Defect 00176 | Defect Name00176 | Test Case 00136 | Exec 00176 | High | Low | Code | Hold | 2016-05-08 04:12
Defect 00177 | Defect Name00177 | Test Case 00137 | Exec 00177 | Low | Med | Environment | Duplicate | 2016-05-08 09:40
Defect 00183 | Defect Name00183 | Test Case 00141 | Exec 00183 | High | Med | Code | Hold | 2016-06-02 13:26
Defect 00185 | Defect Name00185 | Test Case 00142 | Exec 00185 | Low | Med | Code | Open | 2016-04-29 09:02
Defect 00186 | Defect Name00186 | Test Case 00142 | Exec 00186 | Med | Low | Design | Open | 2016-04-29 02:37
Defect 00187 | Defect Name00187 | Test Case 00143 | Exec 00187 | Med | Med | Requirements | Open | 2016-05-04 20:34
Defect 00188 | Defect Name00188 | Test Case 00143 | Exec 00188 | High | Med | Code | Hold | 2016-05-10 01:19
Defect 00189 | Defect Name00189 | Test Case 00144 | Exec 00189 | High | High | Design | Open | 2016-05-05 10:34
Defect 00191 | Defect Name00191 | Test Case 00146 | Exec 00191 | High | Med | Environment | Open | 2016-05-16 11:05
Defect 00193 | Defect Name00193 | Test Case 00148 | Exec 00193 | High | High | Design | Open | 2016-05-24 03:30
Defect 00196 | Defect Name00196 | Test Case 00151 | Exec 00196 | Med | High | Requirements | Open | 2016-05-13 20:34
Defect 00199 | Defect Name00199 | Test Case 00153 | Exec 00199 | High | High | Requirements | Open | 2016-05-05 05:52
Defect 00200 | Defect Name00200 | Test Case 00154 | Exec 00200 | High | Low | Code | Open | 2016-05-07 12:32
Defect 00201 | Defect Name00201 | Test Case 00155 | Exec 00201 | Med | Med | Code | Hold | 2016-05-06 17:49
Defect 00202 | Defect Name00202 | Test Case 00156 | Exec 00202 | High | Med | Requirements | Open | 2016-05-15 06:58
Defect 00203 | Defect Name00203 | Test Case 00157 | Exec 00203 | Med | Med | Code | Open | 2016-05-11 00:31
Defect 00204 | Defect Name00204 | Test Case 00158 | Exec 00204 | High | Low | Code | Hold | 2016-05-18 10:32
Defect 00205 | Defect Name00205 | Test Case 00159 | Exec 00205 | High | Med | Requirements | Open | 2016-05-24 14:36
Defect 00206 | Defect Name00206 | Test Case 00160 | Exec 00206 | Med | Med | Code | Hold | 2016-05-23 06:51
Defect 00208 | Defect Name00208 | Test Case 00162 | Exec 00208 | High | Low | Invalid | Open | 2016-05-08 19:12
Defect 00211 | Defect Name00211 | Test Case 00165 | Exec 00211 | Low | Med | Design | Invalid | 2016-05-14 21:50
Defect 00212 | Defect Name00212 | Test Case 00166 | Exec 00212 | Med | Low | Environment | Closed | 2016-05-01 07:07 | 2016-05-03 13:29
Defect 00214 | Defect Name00214 | Test Case 00167 | Exec 00214 | Med | High | Requirements | Open | 2016-04-27 02:12
Defect 00216 | Defect Name00216 | Test Case 00168 | Exec 00216 | Low | High | Design | Open | 2016-05-18 18:19
Defect 00217 | Defect Name00217 | Test Case 00169 | Exec 00217 | High | High | Code | Open | 2016-05-07 04:37
Defect 00220 | Defect Name00220 | Test Case 00171 | Exec 00220 | Low | Low | Code | Duplicate | 2016-05-10 15:08
Defect 00223 | Defect Name00223 | Test Case 00173 | Exec 00223 | High | Low | Code | Open | 2016-05-16 13:01
Defect 00224 | Defect Name00224 | Test Case 00173 | Exec 00224 | Low | High | Requirements | Duplicate | 2016-05-20 08:12
Defect 00225 | Defect Name00225 | Test Case 00174 | Exec 00225 | High | Med | Invalid | Open | 2016-05-28 08:03
Defect 00229 | Defect Name00229 | Test Case 00178 | Exec 00229 | High | Med | Code | Open | 2016-05-04 06:18
Defect 00236 | Defect Name00236 | Test Case 00182 | Exec 00236 | Med | High | Environment | Duplicate | 2016-04-25 00:31
Defect 00237 | Defect Name00237 | Test Case 00183 | Exec 00237 | Med | High | Requirements | Duplicate | 2016-04-30 11:57
Defect 00238 | Defect Name00238 | Test Case 00184 | Exec 00238 | Med | Low | Invalid | Open | 2016-04-29 10:20
Defect 00240 | Defect Name00240 | Test Case 00186 | Exec 00240 | Low | Med | Code | Open | 2016-05-08 04:47
Defect 00246 | Defect Name00246 | Test Case 00191 | Exec 00246 | High | Med | Code | Open | 2016-05-27 02:39
Defect 00268 | Defect Name00268 | Test Case 00205 | Exec 00268 | Med | High | Requirements | Duplicate | 2016-05-08 17:39