## Dashboard
TBD

## Req. Stats
Stat | Title | Value
Requirements | Count | 100
Business Area | Admin | 20
| Billing | 18
| Customer | 20
| Reports | 16
| UI | 17
| Financial | 9
Application | Admin | 20
| Billing | 40
| Customer | 40
Priority | 1 | 50
| 2 | 19
| 3 | 13
| 4 | 5
| 5 | 13
SIT Status | Pending | 100
| Pass | 0
| Fail | 0
| N/A | 0
UAT Status | Pending | 47
| Pass | 0
| Fail | 0
| N/A | 53
Parallel Status | Pending | 28
| Pass | 0
| Fail | 0
| N/A | 72
Regression Status | Pending | 14
| Pass | 0
| Fail | 0
| N/A | 86
Requirements Complete | Count | 40
| Early | 22
| Average Early Days | 3.2273
| On Time | 5
| Late | 13
| Average Late Days | 3.3077
Development Complete | Count | 35
| Early | 17
| Average Early Days | 2.8824
| On Time | 4
| Late | 14
| Average Late Days | 3.0714
Test Complete | Count | 30
| Early | 17
| Average Early Days | 3.3529
| On Time | 1
| Late | 12
| Average Late Days | 3.1667
Production Complete | Count | 30
| Early | 14
| Average Early Days | 2.2857
| On Time | 1
| Late | 15
| Average Late Days | 2.8667
Requirements Changed | Changed | 3
| Changed After Req. Completion Date | 2
| Rejected | 3

## Requirements
Identification |  |  |  |  | Area |  |  |  |  | Test Levels | [7 empty] | Scheduled | [28 empty] | Notes
ID | Name | Requirement Text | Source | Source Location | Business Area | Application | Priority | Business Analyst | User | SIT | SIT Signoff | UAT | UAT Signoff | Parallel | Parallel Signoff | Regression | Regression Signoff | Req. Comp. Date Planned | Req. Comp. Date Actual | Req. Days off of Plan | Req. Early/Late/OnTime | Req. Days Early | Req. Days Late | Dev. Comp. Date Planned | Dev. Comp. Date Actual | Dev. Days off of Plan | Dev. Early/Late/OnTime | Dev. Days Early | Dev. Days Late | Test Comp. Date Planned | Test Comp. Date Actual | Test Days off of Plan | Test Early/Late/OnTime | Test Days Early | Test Days Late | Prod Date Plammed | Prod Date Actual | Prod Days off of Plan | Prod Early/Late/OnTime | Prod Days Early | Prod Days Late | Last Update Date | Updated after Started | Rejected | Rejected Date | Rejected Reason | Notes | Comments | Issues
1 | Customer Data Load: ID | "Blah Blah Blah" | Customer Data Input File.doc | W:/Project A/Requirements | Customer | Customer | 1 | Jane Doe | Cathrine Snow | Pending |  | N/A |  | Pending |  | Pending |  | 2016-09-09 | 2016-09-07 | -2 | Early | -2 | 0 | 2016-09-16 | 2016-09-14 | -2 | Early | -2 | 0 | 2016-09-23 | 2016-09-21 | -2 | Early | -2 | 0 | 2016-02-17 | 2016-02-19 | 2 | Late | 0 | 2
2 | Customer Data Load: Last Name | "Blah Blah Blah" | Customer Data Input File.doc | W:/Project A/Requirements | Customer | Customer | 1 | Jane Doe | Cathrine Snow | Pending |  | N/A |  | N/A |  | N/A |  | 2016-09-09 | 2016-09-04 | -5 | Early | -5 | 0 | 2016-09-16 | 2016-09-18 | 2 | Late | 0 | 2 | 2016-09-23 | 2016-09-20 | -3 | Early | -3 | 0 | 2016-02-17 | 2016-02-14 | -3 | Early | -3 | 0
3 | Customer Data Load: First Name | "Blah Blah Blah" | Customer Data Input File.doc | W:/Project A/Requirements | Customer | Customer | 3 | Jane Doe | Cathrine Snow | Pending |  | N/A |  | N/A |  | N/A |  | 2016-09-09 | 2016-09-05 | -4 | Early | -4 | 0 | 2016-09-16 | 2016-09-13 | -3 | Early | -3 | 0 | 2016-09-23 | 2016-09-27 | 4 | Late | 0 | 4 | 2016-02-17 | 2016-02-20 | 3 | Late | 0 | 3
4 | Customer Data Load: Street | "Blah Blah Blah" | Customer Data Input File.doc | W:/Project A/Requirements | Customer | Customer | 1 | Jane Doe | Cathrine Snow | Pending |  | N/A |  | N/A |  | N/A |  | 2016-09-09 | 2016-09-05 | -4 | Early | -4 | 0 | 2016-09-16 | 2016-09-11 | -5 | Early | -5 | 0 | 2016-09-23 | 2016-09-19 | -4 | Early | -4 | 0 | 2016-02-17 | 2016-02-17 | 0 | On Time | 0 | 0
5 | Customer Data Load: City | "Blah Blah Blah" | Customer Data Input File.doc | W:/Project A/Requirements | Customer | Customer | 1 | Jane Doe | Cathrine Snow | Pending |  | N/A |  | N/A |  | N/A |  | 2016-09-09 | 2016-09-04 | -5 | Early | -5 | 0 | 2016-09-16 | 2016-09-16 | 0 | On Time | 0 | 0 | 2016-09-23 | 2016-09-21 | -2 | Early | -2 | 0 | 2016-02-17 | 2016-02-16 | -1 | Early | -1 | 0
6 | Customer Data Load: State | "Blah Blah Blah" | Customer Data Input File.doc | W:/Project A/Requirements | Customer | Customer | 1 | Jane Doe | Cathrine Snow | Pending |  | N/A |  | N/A |  | N/A |  | 2016-09-16 | 2016-09-15 | -1 | Early | -1 | 0 | 2016-09-23 | 2016-09-20 | -3 | Early | -3 | 0 | 2016-09-30 | 2016-09-28 | -2 | Early | -2 | 0 | 2016-02-17 | 2016-02-21 | 4 | Late | 0 | 4
7 | Customer Data Load: ZIP | "Blah Blah Blah" | Customer Data Input File.doc | W:/Project A/Requirements | Customer | Customer | 1 | Jane Doe | Cathrine Snow | Pending |  | N/A |  | N/A |  | N/A |  | 2016-09-16 | 2016-09-14 | -2 | Early | -2 | 0 | 2016-09-23 | 2016-09-19 | -4 | Early | -4 | 0 | 2016-09-30 | 2016-09-26 | -4 | Early | -4 | 0 | 2016-02-17 | 2016-02-12 | -5 | Early | -5 | 0
8 | Customer Data Load: Phone | "Blah Blah Blah" | Customer Data Input File.doc | W:/Project A/Requirements | Customer | Customer | 1 | Jane Doe | Cathrine Snow | Pending |  | N/A |  | N/A |  | N/A |  | 2016-09-16 | 2016-09-19 | 3 | Late | 0 | 3 | 2016-09-23 | 2016-09-23 | 0 | On Time | 0 | 0 | 2016-09-30 | 2016-09-30 | 0 | On Time | 0 | 0 | 2016-02-17 | 2016-02-21 | 4 | Late | 0 | 4 | 2016-10-28 | Yes
9 | Customer Data Load: Mobile | "Blah Blah Blah" | Customer Data Input File.doc | W:/Project A/Requirements | Customer | Customer | 3 | Jane Doe | Cathrine Snow | Pending |  | N/A |  | N/A |  | N/A |  | 2016-09-16 | 2016-09-16 | 0 | On Time | 0 | 0 | 2016-09-23 | 2016-09-18 | -5 | Early | -5 | 0 | 2016-09-30 | 2016-10-04 | 4 | Late | 0 | 4 | 2016-02-17 | 2016-02-16 | -1 | Early | -1 | 0 | 2016-11-02 | Yes
10 | Customer Data Load: Fax | "Blah Blah Blah" | Customer Data Input File.doc | W:/Project A/Requirements | Customer | Customer | 3 | Jane Doe | Cathrine Snow | Pending |  | N/A |  | N/A |  | N/A |  | 2016-09-16 | 2016-09-14 | -2 | Early | -2 | 0 | 2016-09-23 | 2016-09-23 | 0 | On Time | 0 | 0 | 2016-09-30 | 2016-09-25 | -5 | Early | -5 | 0 | 2016-02-17 | 2016-02-15 | -2 | Early | -2 | 0 | 2016-09-01 |  | Yes | 2016-09-01 | Descoped
11 | Customer Pre-Process: Verify ID | "Blah Blah Blah" | Customer Pre-Processing.doc | W:/Project A/Requirements | Customer | Customer | 1 | Jane Doe | Cathrine Snow | Pending |  | N/A |  | Pending |  | Pending |  | 2016-09-23 | 2016-09-19 | -4 | Early | -4 | 0 | 2016-09-30 | 2016-10-04 | 4 | Late | 0 | 4 | 2016-10-07 | 2016-10-03 | -4 | Early | -4 | 0 | 2016-02-17 | 2016-02-16 | -1 | Early | -1 | 0
12 | Customer Pre-Process: Merge to Existing Customer | "Blah Blah Blah" | Customer Pre-Processing.doc | W:/Project A/Requirements | Customer | Customer | 1 | Jane Doe | Cathrine Snow | Pending |  | N/A |  | N/A |  | N/A |  | 2016-09-23 | 2016-09-23 | 0 | On Time | 0 | 0 | 2016-09-30 | 2016-09-26 | -4 | Early | -4 | 0 | 2016-10-07 | 2016-10-09 | 2 | Late | 0 | 2 | 2016-02-17 | 2016-02-20 | 3 | Late | 0 | 3
13 | Customer Pre-Process: Create New Customer | "Blah Blah Blah" | Customer Pre-Processing.doc | W:/Project A/Requirements | Customer | Customer | 1 | Jane Doe | Cathrine Snow | Pending |  | N/A |  | N/A |  | N/A |  | 2016-09-23 | 2016-09-22 | -1 | Early | -1 | 0 | 2016-09-30 | 2016-10-04 | 4 | Late | 0 | 4 | 2016-10-07 | 2016-10-03 | -4 | Early | -4 | 0 | 2016-02-17 | 2016-02-15 | -2 | Early | -2 | 0
14 | Customer Pre-Process: Calculate Region | "Blah Blah Blah" | Customer Pre-Processing.doc | W:/Project A/Requirements | Customer | Customer | 1 | Jane Doe | Cathrine Snow | Pending |  | N/A |  | Pending |  | Pending |  | 2016-09-23 | 2016-09-27 | 4 | Late | 0 | 4 | 2016-09-30 | 2016-10-04 | 4 | Late | 0 | 4 | 2016-10-07 | 2016-10-11 | 4 | Late | 0 | 4 | 2016-02-17 | 2016-02-15 | -2 | Early | -2 | 0
15 | Customer Pre-Process: Assign Sales Agent | "Blah Blah Blah" | Customer Pre-Processing.doc | W:/Project A/Requirements | Customer | Customer | 1 | Jane Doe | Cathrine Snow | Pending |  | Pending |  | Pending |  | Pending |  | 2016-09-23 | 2016-09-24 | 1 | Late | 0 | 1 | 2016-09-30 | 2016-09-26 | -4 | Early | -4 | 0 | 2016-10-07 | 2016-10-04 | -3 | Early | -3 | 0 | 2016-02-17 | 2016-02-16 | -1 | Early | -1 | 0
16 | Customer Pre-Process: Balance Sales Agents | "Blah Blah Blah" | Customer Pre-Processing.doc | W:/Project A/Requirements | Customer | Customer | 2 | Jane Doe | Cathrine Snow | Pending |  | Pending |  | Pending |  | Pending |  | 2016-09-30 | 2016-10-04 | 4 | Late | 0 | 4 | 2016-10-07 | 2016-10-11 | 4 | Late | 0 | 4 | 2016-10-14 | 2016-10-18 | 4 | Late | 0 | 4 | 2016-02-17 | 2016-02-12 | -5 | Early | -5 | 0
17 | Customer Pre-Process: Generate Customer List | "Blah Blah Blah" | Customer Pre-Processing.doc | W:/Project A/Requirements | Customer | Customer | 1 | Jane Doe | Cathrine Snow | Pending |  | Pending |  | Pending |  | Pending |  | 2016-09-30 | 2016-10-03 | 3 | Late | 0 | 3 | 2016-10-07 | 2016-10-09 | 2 | Late | 0 | 2 | 2016-10-14 | 2016-10-12 | -2 | Early | -2 | 0 | 2016-02-17 | 2016-02-20 | 3 | Late | 0 | 3
18 | Customer Pre-Process: Set up Invoice Template | "Blah Blah Blah" | Customer Pre-Processing.doc | W:/Project A/Requirements | Customer | Customer | 2 | Jane Doe | Cathrine Snow | Pending |  | N/A |  | N/A |  | N/A |  | 2016-09-30 | 2016-09-26 | -4 | Early | -4 | 0 | 2016-10-07 | 2016-10-09 | 2 | Late | 0 | 2 | 2016-10-14 | 2016-10-18 | 4 | Late | 0 | 4 | 2016-02-17 | 2016-02-16 | -1 | Early | -1 | 0
19 | Customer Pre-Process: Send Welcome Letter | "Blah Blah Blah" | Customer Pre-Processing.doc | W:/Project A/Requirements | Customer | Customer | 2 | Jane Doe | Cathrine Snow | Pending |  | Pending |  | Pending |  | Pending |  | 2016-09-30 | 2016-09-26 | -4 | Early | -4 | 0 | 2016-10-07 | 2016-10-06 | -1 | Early | -1 | 0 | 2016-10-14 | 2016-10-15 | 1 | Late | 0 | 1 | 2016-02-17 | 2016-02-15 | -2 | Early | -2 | 0
20 | Customer Pre-Process: Merge to Existing Customer | "Blah Blah Blah" | Customer Pre-Processing.doc | W:/Project A/Requirements | Customer | Customer | 2 | Jane Doe | Cathrine Snow | Pending |  | Pending |  | Pending |  | Pending |  | 2016-09-30 | 2016-09-30 | 0 | On Time | 0 | 0 | 2016-10-07 | 2016-10-03 | -4 | Early | -4 | 0 | 2016-10-14 | 2016-10-09 | -5 | Early | -5 | 0 | 2016-02-17 | 2016-02-21 | 4 | Late | 0 | 4 |  |  | Yes | 2016-09-30 | Duplicate
21 | Customer Maintence UI: Change Last Name | "Blah Blah Blah" | Customer Maintenance UI.doc | W:/Project A/Requirements | UI | Customer | 1 | Bob Smith | Cathrine Snow | Pending |  | Pending |  | N/A |  | N/A |  | 2016-10-07 | 2016-10-10 | 3 | Late | 0 | 3 | 2016-10-14 | 2016-10-15 | 1 | Late | 0 | 1 | 2016-10-21 | 2016-10-24 | 3 | Late | 0 | 3 | 2016-02-17 | 2016-02-18 | 1 | Late | 0 | 1
22 | Customer Maintence UI: Change First Name | "Blah Blah Blah" | Customer Maintenance UI.doc | W:/Project A/Requirements | UI | Customer | 3 | Bob Smith | Cathrine Snow | Pending |  | Pending |  | N/A |  | N/A |  | 2016-10-07 | 2016-10-11 | 4 | Late | 0 | 4 | 2016-10-14 | 2016-10-12 | -2 | Early | -2 | 0 | 2016-10-21 | 2016-10-25 | 4 | Late | 0 | 4 | 2016-02-17 | 2016-02-15 | -2 | Early | -2 | 0
23 | Customer Maintence UI: Change Street | "Blah Blah Blah" | Customer Maintenance UI.doc | W:/Project A/Requirements | UI | Customer | 1 | Bob Smith | Cathrine Snow | Pending |  | Pending |  | N/A |  | N/A |  | 2016-10-07 | 2016-10-04 | -3 | Early | -3 | 0 | 2016-10-14 | 2016-10-18 | 4 | Late | 0 | 4 | 2016-10-21 | 2016-10-16 | -5 | Early | -5 | 0 | 2016-02-17 | 2016-02-20 | 3 | Late | 0 | 3
24 | Customer Maintence UI: Change City | "Blah Blah Blah" | Customer Maintenance UI.doc | W:/Project A/Requirements | UI | Customer | 1 | Bob Smith | Cathrine Snow | Pending |  | Pending |  | N/A |  | N/A |  | 2016-10-07 | 2016-10-03 | -4 | Early | -4 | 0 | 2016-10-14 | 2016-10-18 | 4 | Late | 0 | 4 | 2016-10-21 | 2016-10-24 | 3 | Late | 0 | 3 | 2016-02-17 | 2016-02-18 | 1 | Late | 0 | 1
25 | Customer Maintence UI: Change State | "Blah Blah Blah" | Customer Maintenance UI.doc | W:/Project A/Requirements | UI | Customer | 1 | Bob Smith | Cathrine Snow | Pending |  | Pending |  | N/A |  | N/A |  | 2016-10-07 | 2016-10-11 | 4 | Late | 0 | 4 | 2016-10-14 | 2016-10-18 | 4 | Late | 0 | 4 | 2016-10-21 | 2016-10-16 | -5 | Early | -5 | 0 | 2016-02-17 | 2016-02-21 | 4 | Late | 0 | 4
26 | Customer Maintence UI: Change ZIP | "Blah Blah Blah" | Customer Maintenance UI.doc | W:/Project A/Requirements | UI | Customer | 1 | Bob Smith | Cathrine Snow | Pending |  | Pending |  | N/A |  | N/A |  | 2016-10-14 | 2016-10-18 | 4 | Late | 0 | 4 | 2016-10-21 | 2016-10-20 | -1 | Early | -1 | 0 | 2016-10-28 | 2016-10-25 | -3 | Early | -3 | 0 | 2016-02-17 | 2016-02-21 | 4 | Late | 0 | 4
27 | Customer Maintence UI: Change Phone | "Blah Blah Blah" | Customer Maintenance UI.doc | W:/Project A/Requirements | UI | Customer | 1 | Bob Smith | Cathrine Snow | Pending |  | Pending |  | N/A |  | N/A |  | 2016-10-14 | 2016-10-17 | 3 | Late | 0 | 3 | 2016-10-21 | 2016-10-22 | 1 | Late | 0 | 1 | 2016-10-28 | 2016-10-26 | -2 | Early | -2 | 0 | 2016-02-17 | 2016-02-19 | 2 | Late | 0 | 2
28 | Customer Maintence UI: Change Mobile | "Blah Blah Blah" | Customer Maintenance UI.doc | W:/Project A/Requirements | UI | Customer | 2 | Bob Smith | Cathrine Snow | Pending |  | Pending |  | N/A |  | N/A |  | 2016-10-14 | 2016-10-14 | 0 | On Time | 0 | 0 | 2016-10-21 | 2016-10-24 | 3 | Late | 0 | 3 | 2016-10-28 | 2016-11-01 | 4 | Late | 0 | 4 | 2016-02-17 | 2016-02-18 | 1 | Late | 0 | 1
29 | Customer Maintence UI: Change Fax | "Blah Blah Blah" | Customer Maintenance UI.doc | W:/Project A/Requirements | UI | Customer | 2 | Bob Smith | Cathrine Snow | Pending |  | Pending |  | N/A |  | N/A |  | 2016-10-14 | 2016-10-09 | -5 | Early | -5 | 0 | 2016-10-21 | 2016-10-20 | -1 | Early | -1 | 0 | 2016-10-28 | 2016-10-26 | -2 | Early | -2 | 0 | 2016-02-17 | 2016-02-21 | 4 | Late | 0 | 4
30 | Customer Maintence UI: Save Changes | "Blah Blah Blah" | Customer Maintenance UI.doc | W:/Project A/Requirements | UI | Customer | 1 | Bob Smith | Cathrine Snow | Pending |  | Pending |  | N/A |  | N/A |  | 2016-10-14 | 2016-10-13 | -1 | Early | -1 | 0 | 2016-10-21 | 2016-10-20 | -1 | Early | -1 | 0 | 2016-10-28 | 2016-10-29 | 1 | Late | 0 | 1 | 2016-02-17 | 2016-02-13 | -4 | Early | -4 | 0 |  |  | Yes | 2016-11-02 | Descoped
31 | Customer Reporting: Report 1 | "Blah Blah Blah" | Customer Reporting.doc | W:/Project A/Requirements | Reports | Customer | 1 | Ravi Unil | Cathrine Snow | Pending |  | Pending |  | Pending |  | Pending |  | 2016-10-21 | 2016-10-21 | 0 | On Time | 0 | 0 | 2016-10-28 | 2016-10-28 | 0 | On Time | 0 | 0 | 2016-11-04 | [5 empty] | 2016-02-17
32 | Customer Reporting: Report 2 | "Blah Blah Blah" | Customer Reporting.doc | W:/Project A/Requirements | Reports | Customer | 1 | Ravi Unil | Cathrine Snow | Pending |  | Pending |  | Pending |  | Pending |  | 2016-10-21 | 2016-10-25 | 4 | Late | 0 | 4 | 2016-10-28 | 2016-10-24 | -4 | Early | -4 | 0 | 2016-11-04 | [5 empty] | 2016-02-17
33 | Customer Reporting: Report 3 | "Blah Blah Blah" | Customer Reporting.doc | W:/Project A/Requirements | Reports | Customer | 1 | Ravi Unil | Cathrine Snow | Pending |  | Pending |  | Pending |  | Pending |  | 2016-10-21 | 2016-10-17 | -4 | Early | -4 | 0 | 2016-10-28 | 2016-11-01 | 4 | Late | 0 | 4 | 2016-11-04 | [5 empty] | 2016-02-17
34 | Customer Reporting: Report 4 | "Blah Blah Blah" | Customer Reporting.doc | W:/Project A/Requirements | Reports | Customer | 2 | Ravi Unil | Cathrine Snow | Pending |  | Pending |  | Pending |  | N/A |  | 2016-10-21 | 2016-10-16 | -5 | Early | -5 | 0 | 2016-10-28 | 2016-10-26 | -2 | Early | -2 | 0 | 2016-11-04 | [5 empty] | 2016-02-17
35 | Customer Reporting: Report 5 | "Blah Blah Blah" | Customer Reporting.doc | W:/Project A/Requirements | Reports | Customer | 2 | Ravi Unil | Cathrine Snow | Pending |  | Pending |  | Pending |  | N/A |  | 2016-10-21 | 2016-10-23 | 2 | Late | 0 | 2 | 2016-10-28 | 2016-10-25 | -3 | Early | -3 | 0 | 2016-11-04 | [5 empty] | 2016-02-17
36 | Customer Reporting: Report 6 | "Blah Blah Blah" | Customer Reporting.doc | W:/Project A/Requirements | Reports | Customer | 3 | Ravi Unil | Cathrine Snow | Pending |  | Pending |  | N/A |  | N/A |  | 2016-10-28 | 2016-10-26 | -2 | Early | -2 | 0 | 2016-11-04 | [5 empty] | 2016-11-11 | [5 empty] | 2016-02-17
37 | Customer Reporting: Report 7 | "Blah Blah Blah" | Customer Reporting.doc | W:/Project A/Requirements | Reports | Customer | 3 | Ravi Unil | Cathrine Snow | Pending |  | Pending |  | N/A |  | N/A |  | 2016-10-28 | 2016-10-25 | -3 | Early | -3 | 0 | 2016-11-04 | [5 empty] | 2016-11-11 | [5 empty] | 2016-02-17
38 | Customer Reporting: Report 8 | "Blah Blah Blah" | Customer Reporting.doc | W:/Project A/Requirements | Reports | Customer | 4 | Ravi Unil | Cathrine Snow | Pending |  | Pending |  | N/A |  | N/A |  | 2016-10-28 | 2016-10-27 | -1 | Early | -1 | 0 | 2016-11-04 | [5 empty] | 2016-11-11 | [5 empty] | 2016-02-17
39 | Customer Reporting: Report 9 | "Blah Blah Blah" | Customer Reporting.doc | W:/Project A/Requirements | Reports | Customer | 4 | Ravi Unil | Cathrine Snow | Pending |  | Pending |  | N/A |  | N/A |  | 2016-10-28 | 2016-11-01 | 4 | Late | 0 | 4 | 2016-11-04 | [5 empty] | 2016-11-11 | [5 empty] | 2016-02-17
40 | Customer Reporting: Report 10 | "Blah Blah Blah" | Customer Reporting.doc | W:/Project A/Requirements | Financial | Customer | 5 | Ravi Unil | Cathrine Snow | Pending |  | Pending |  | N/A |  | N/A |  | 2016-10-28 | 2016-10-23 | -5 | Early | -5 | 0 | 2016-11-04 | [5 empty] | 2016-11-11 | [5 empty] | 2016-02-17
41 | Invoice/Billing UI: Attach new Invoice to Customer | "Blah Blah Blah" | Invoice/Billing UI.doc | W:/Project A/Requirements | UI | Billing | 1 | Bob Smith | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-11-04 | [5 empty] | 2016-11-11 | [5 empty] | 2016-11-18 | [5 empty] | 2016-02-17
42 | Invoice/Billing UI: Add Item | "Blah Blah Blah" | Invoice/Billing UI.doc | W:/Project A/Requirements | UI | Billing | 1 | Bob Smith | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-11-04 | [5 empty] | 2016-11-11 | [5 empty] | 2016-11-18 | [5 empty] | 2016-02-17
43 | Invoice/Billing UI: Remove Item | "Blah Blah Blah" | Invoice/Billing UI.doc | W:/Project A/Requirements | UI | Billing | 1 | Bob Smith | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-11-04 | [5 empty] | 2016-11-11 | [5 empty] | 2016-11-18 | [5 empty] | 2016-02-17
44 | Invoice/Billing UI: Total Order | "Blah Blah Blah" | Invoice/Billing UI.doc | W:/Project A/Requirements | Financial | Billing | 1 | Bob Smith | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-11-04 | [5 empty] | 2016-11-11 | [5 empty] | 2016-11-18 | [5 empty] | 2016-02-17
45 | Invoice/Billing UI: Calcualate Tax | "Blah Blah Blah" | Invoice/Billing UI.doc | W:/Project A/Requirements | Financial | Billing | 1 | Bob Smith | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-11-04 | [5 empty] | 2016-11-11 | [5 empty] | 2016-11-18 | [5 empty] | 2016-02-17
46 | Invoice/Billing UI: Calculate Shipping | "Blah Blah Blah" | Invoice/Billing UI.doc | W:/Project A/Requirements | Financial | Billing | 1 | Bob Smith | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-11-11 | [5 empty] | 2016-11-18 | [5 empty] | 2016-11-25 | [5 empty] | 2016-02-17
47 | Invoice/Billing UI: Visa Card Transaction | "Blah Blah Blah" | Invoice/Billing UI.doc | W:/Project A/Requirements | UI | Billing | 1 | Bob Smith | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-11-11 | [5 empty] | 2016-11-18 | [5 empty] | 2016-11-25 | [5 empty] | 2016-02-17
48 | Invoice/Billing UI: Post Invoice | "Blah Blah Blah" | Invoice/Billing UI.doc | W:/Project A/Requirements | UI | Billing | 2 | Bob Smith | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-11-11 | [5 empty] | 2016-11-18 | [5 empty] | 2016-11-25 | [5 empty] | 2016-02-17
49 | Invoice/Billing UI: Cancel Invoice | "Blah Blah Blah" | Invoice/Billing UI.doc | W:/Project A/Requirements | UI | Billing | 2 | Bob Smith | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-11-11 | [5 empty] | 2016-11-18 | [5 empty] | 2016-11-25 | [5 empty] | 2016-02-17
50 | Invoice/Billing UI: Update Existing Invoice | "Blah Blah Blah" | Invoice/Billing UI.doc | W:/Project A/Requirements | UI | Billing | 1 | Bob Smith | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-11-11 | [5 empty] | 2016-11-18 | [5 empty] | 2016-11-25 | [5 empty] | 2016-02-17
51 | Invoice Billing Financials: Daily Totals | "Blah Blah Blah" | Invoice Billing Financials.doc | W:/Project A/Requirements | Billing | Billing | 1 | Terry Jones | Scott Williams | Pending |  | N/A |  | Pending |  | N/A |  | 2016-11-18 | [5 empty] | 2016-11-25 | [5 empty] | 2016-12-02 | [5 empty] | 2016-02-17
52 | Invoice Billing Financials: Weekly Totals | "Blah Blah Blah" | Invoice Billing Financials.doc | W:/Project A/Requirements | Billing | Billing | 1 | Terry Jones | Scott Williams | Pending |  | N/A |  | Pending |  | N/A |  | 2016-11-18 | [5 empty] | 2016-11-25 | [5 empty] | 2016-12-02 | [5 empty] | 2016-02-17
53 | Invoice Billing Financials: Monthly Totals | "Blah Blah Blah" | Invoice Billing Financials.doc | W:/Project A/Requirements | Billing | Billing | 1 | Terry Jones | Scott Williams | Pending |  | N/A |  | Pending |  | N/A |  | 2016-11-18 | [5 empty] | 2016-11-25 | [5 empty] | 2016-12-02 | [5 empty] | 2016-02-17
54 | Invoice Billing Financials: Quarterly Totals | "Blah Blah Blah" | Invoice Billing Financials.doc | W:/Project A/Requirements | Billing | Billing | 2 | Terry Jones | Scott Williams | Pending |  | N/A |  | Pending |  | N/A |  | 2016-11-18 | [5 empty] | 2016-11-25 | [5 empty] | 2016-12-02 | [5 empty] | 2016-02-17
55 | Invoice Billing Financials: Yearly Totals | "Blah Blah Blah" | Invoice Billing Financials.doc | W:/Project A/Requirements | Billing | Billing | 3 | Terry Jones | Scott Williams | Pending |  | N/A |  | Pending |  | N/A |  | 2016-11-18 | [5 empty] | 2016-11-25 | [5 empty] | 2016-12-02 | [5 empty] | 2016-02-17
56 | Invoice Billing Financials: Quarterly Tax Due | "Blah Blah Blah" | Invoice Billing Financials.doc | W:/Project A/Requirements | Billing | Billing | 2 | Terry Jones | Scott Williams | Pending |  | N/A |  | Pending |  | N/A |  | 2016-11-25 | [5 empty] | 2016-12-02 | [5 empty] | 2016-12-09 | [5 empty] | 2016-02-17
57 | Invoice Billing Financials: Quarterly Profit | "Blah Blah Blah" | Invoice Billing Financials.doc | W:/Project A/Requirements | Financial | Billing | 2 | Terry Jones | Scott Williams | Pending |  | N/A |  | Pending |  | N/A |  | 2016-11-25 | [5 empty] | 2016-12-02 | [5 empty] | 2016-12-09 | [5 empty] | 2016-02-17
58 | Invoice Billing Financials: Quarterly Unpaid | "Blah Blah Blah" | Invoice Billing Financials.doc | W:/Project A/Requirements | Billing | Billing | 2 | Terry Jones | Scott Williams | Pending |  | N/A |  | Pending |  | N/A |  | 2016-11-25 | [5 empty] | 2016-12-02 | [5 empty] | 2016-12-09 | [5 empty] | 2016-02-17
59 | Invoice Billing Financials: Yearly Profit | "Blah Blah Blah" | Invoice Billing Financials.doc | W:/Project A/Requirements | Financial | Billing | 3 | Terry Jones | Scott Williams | Pending |  | N/A |  | Pending |  | N/A |  | 2016-11-25 | [5 empty] | 2016-12-02 | [5 empty] | 2016-12-09 | [5 empty] | 2016-02-17
60 | Invoice Billing Financials: Yearly Loss | "Blah Blah Blah" | Invoice Billing Financials.doc | W:/Project A/Requirements | Billing | Billing | 3 | Terry Jones | Scott Williams | Pending |  | N/A |  | Pending |  | N/A |  | 2016-11-25 | [5 empty] | 2016-12-02 | [5 empty] | 2016-12-09 | [5 empty] | 2016-02-17
61 | Invoice Billing Mailings: Mail Invoice | "Blah Blah Blah" | Invoice Billing Mailings.doc | W:/Project A/Requirements | Billing | Billing | 1 | Terry Jones | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-12-02 | [5 empty] | 2016-12-09 | [5 empty] | 2016-12-16 | [5 empty] | 2016-02-17
62 | Invoice Billing Mailings: Mail First Late Notice | "Blah Blah Blah" | Invoice Billing Mailings.doc | W:/Project A/Requirements | Billing | Billing | 2 | Terry Jones | Scott Williams | Pending |  | N/A |  | N/A |  | N/A |  | 2016-12-02 | [5 empty] | 2016-12-09 | [5 empty] | 2016-12-16 | [5 empty] | 2016-02-17
63 | Invoice Billing Mailings: Mail Second Late Notice | "Blah Blah Blah" | Invoice Billing Mailings.doc | W:/Project A/Requirements | Billing | Billing | 3 | Terry Jones | Scott Williams | Pending |  | N/A |  | N/A |  | N/A |  | 2016-12-02 | [5 empty] | 2016-12-09 | [5 empty] | 2016-12-16 | [5 empty] | 2016-02-17
64 | Invoice Billing Mailings: Mail Payment Thank You | "Blah Blah Blah" | Invoice Billing Mailings.doc | W:/Project A/Requirements | Billing | Billing | 1 | Terry Jones | Scott Williams | Pending |  | N/A |  | N/A |  | N/A |  | 2016-12-02 | [5 empty] | 2016-12-09 | [5 empty] | 2016-12-16 | [5 empty] | 2016-02-17
65 | Invoice Billing Mailings: Mail Monthly Recap | "Blah Blah Blah" | Invoice Billing Mailings.doc | W:/Project A/Requirements | Billing | Billing | 3 | Terry Jones | Scott Williams | Pending |  | N/A |  | N/A |  | N/A |  | 2016-12-02 | [5 empty] | 2016-12-09 | [5 empty] | 2016-12-16 | [5 empty] | 2016-02-17
66 | Invoice Billing Mailings: Mail Catalogs | "Blah Blah Blah" | Invoice Billing Mailings.doc | W:/Project A/Requirements | Billing | Billing | 4 | Terry Jones | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-12-09 | [5 empty] | 2016-12-16 | [5 empty] | 2016-12-23 | [5 empty] | 2016-02-17
67 | Invoice Billing Mailings: Calculate Postage | "Blah Blah Blah" | Invoice Billing Mailings.doc | W:/Project A/Requirements | Billing | Billing | 1 | Terry Jones | Scott Williams | Pending |  | N/A |  | N/A |  | N/A |  | 2016-12-09 | [5 empty] | 2016-12-16 | [5 empty] | 2016-12-23 | [5 empty] | 2016-02-17
68 | Invoice Billing Mailings: Calculate Foreign Postage | "Blah Blah Blah" | Invoice Billing Mailings.doc | W:/Project A/Requirements | Billing | Billing | 2 | Terry Jones | Scott Williams | Pending |  | N/A |  | N/A |  | N/A |  | 2016-12-09 | [5 empty] | 2016-12-16 | [5 empty] | 2016-12-23 | [5 empty] | 2016-02-17
69 | Invoice Billing Mailings: Process Returned Mail | "Blah Blah Blah" | Invoice Billing Mailings.doc | W:/Project A/Requirements | Billing | Billing | 5 | Terry Jones | Scott Williams | Pending |  | N/A |  | N/A |  | N/A |  | 2016-12-09 | [5 empty] | 2016-12-16 | [5 empty] | 2016-12-23 | [5 empty] | 2016-02-17
70 | Invoice Billing Mailings: Pay Postage Charges | "Blah Blah Blah" | Invoice Billing Mailings.doc | W:/Project A/Requirements | Billing | Billing | 2 | Terry Jones | Scott Williams | Pending |  | N/A |  | N/A |  | N/A |  | 2016-12-09 | [5 empty] | 2016-12-16 | [5 empty] | 2016-12-23 | [5 empty] | 2016-02-17
71 | Invoice Reporting: Report 1 | "Blah Blah Blah" | Invoice Reporting.doc | W:/Project A/Requirements | Reports | Billing | 1 | Ravi Unil | Scott Williams | Pending |  | Pending |  | Pending |  | Pending |  | 2016-12-16 | [5 empty] | 2016-12-23 | [5 empty] | 2016-12-30 | [5 empty] | 2016-02-17
72 | Invoice Reporting: Report 2 | "Blah Blah Blah" | Invoice Reporting.doc | W:/Project A/Requirements | Reports | Billing | 1 | Ravi Unil | Scott Williams | Pending |  | Pending |  | Pending |  | Pending |  | 2016-12-16 | [5 empty] | 2016-12-23 | [5 empty] | 2016-12-30 | [5 empty] | 2016-02-17
73 | Invoice Reporting: Report 3 | "Blah Blah Blah" | Invoice Reporting.doc | W:/Project A/Requirements | Reports | Billing | 1 | Ravi Unil | Scott Williams | Pending |  | Pending |  | Pending |  | Pending |  | 2016-12-16 | [5 empty] | 2016-12-23 | [5 empty] | 2016-12-30 | [5 empty] | 2016-02-17
74 | Invoice Reporting: Report 4 | "Blah Blah Blah" | Invoice Reporting.doc | W:/Project A/Requirements | Reports | Billing | 2 | Ravi Unil | Scott Williams | Pending |  | Pending |  | Pending |  | N/A |  | 2016-12-16 | [5 empty] | 2016-12-23 | [5 empty] | 2016-12-30 | [5 empty] | 2016-02-17
75 | Invoice Reporting: Report 5 | "Blah Blah Blah" | Invoice Reporting.doc | W:/Project A/Requirements | Reports | Billing | 2 | Ravi Unil | Scott Williams | Pending |  | Pending |  | Pending |  | N/A |  | 2016-12-16 | [5 empty] | 2016-12-23 | [5 empty] | 2016-12-30 | [5 empty] | 2016-02-17
76 | Invoice Reporting: Report 6 | "Blah Blah Blah" | Invoice Reporting.doc | W:/Project A/Requirements | Reports | Billing | 3 | Ravi Unil | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-12-23 | [5 empty] | 2016-12-30 | [5 empty] | 2017-01-06 | [5 empty] | 2016-02-17
77 | Invoice Reporting: Report 7 | "Blah Blah Blah" | Invoice Reporting.doc | W:/Project A/Requirements | Reports | Billing | 3 | Ravi Unil | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-12-23 | [5 empty] | 2016-12-30 | [5 empty] | 2017-01-06 | [5 empty] | 2016-02-17
78 | Invoice Reporting: Report 8 | "Blah Blah Blah" | Invoice Reporting.doc | W:/Project A/Requirements | Financial | Billing | 4 | Ravi Unil | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-12-23 | [5 empty] | 2016-12-30 | [5 empty] | 2017-01-06 | [5 empty] | 2016-02-17
79 | Invoice Reporting: Report 9 | "Blah Blah Blah" | Invoice Reporting.doc | W:/Project A/Requirements | Financial | Billing | 4 | Ravi Unil | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-12-23 | [5 empty] | 2016-12-30 | [5 empty] | 2017-01-06 | [5 empty] | 2016-02-17
80 | Invoice Reporting: Report 10 | "Blah Blah Blah" | Invoice Reporting.doc | W:/Project A/Requirements | Financial | Billing | 5 | Ravi Unil | Scott Williams | Pending |  | Pending |  | N/A |  | N/A |  | 2016-12-23 | [5 empty] | 2016-12-30 | [5 empty] | 2017-01-06 | [5 empty] | 2016-02-17
81 | Data Archive: Customer | "Blah Blah Blah" | Data Archive.doc | W:/Project A/Requirements | Admin | Admin | 5 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-06 | [5 empty] | 2016-01-13 | [5 empty] | 2016-01-20 | [5 empty] | 2016-02-17
82 | Data Archive: Invoice | "Blah Blah Blah" | Data Archive.doc | W:/Project A/Requirements | Admin | Admin | 5 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-06 | [5 empty] | 2016-01-13 | [5 empty] | 2016-01-20 | [5 empty] | 2016-02-17
83 | Data Archive: Hourly | "Blah Blah Blah" | Data Archive.doc | W:/Project A/Requirements | Admin | Admin | 5 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-06 | [5 empty] | 2016-01-13 | [5 empty] | 2016-01-20 | [5 empty] | 2016-02-17
84 | Data Archive: Daily | "Blah Blah Blah" | Data Archive.doc | W:/Project A/Requirements | Admin | Admin | 5 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-06 | [5 empty] | 2016-01-13 | [5 empty] | 2016-01-20 | [5 empty] | 2016-02-17
85 | Data Archive: Weekly | "Blah Blah Blah" | Data Archive.doc | W:/Project A/Requirements | Admin | Admin | 5 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-06 | [5 empty] | 2016-01-13 | [5 empty] | 2016-01-20 | [5 empty] | 2016-02-17
86 | Data Archive: Quarterly | "Blah Blah Blah" | Data Archive.doc | W:/Project A/Requirements | Admin | Admin | 5 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-13 | [5 empty] | 2016-01-20 | [5 empty] | 2016-01-27 | [5 empty] | 2016-02-17
87 | Data Archive: Yearly | "Blah Blah Blah" | Data Archive.doc | W:/Project A/Requirements | Admin | Admin | 5 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-13 | [5 empty] | 2016-01-20 | [5 empty] | 2016-01-27 | [5 empty] | 2016-02-17
88 | Data Archive: Retreive Backup | "Blah Blah Blah" | Data Archive.doc | W:/Project A/Requirements | Admin | Admin | 5 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-13 | [5 empty] | 2016-01-20 | [5 empty] | 2016-01-27 | [5 empty] | 2016-02-17
89 | Data Archive: Apply Backup | "Blah Blah Blah" | Data Archive.doc | W:/Project A/Requirements | Admin | Admin | 5 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-13 | [5 empty] | 2016-01-20 | [5 empty] | 2016-01-27 | [5 empty] | 2016-02-17
90 | Data Archive: Verify Backup | "Blah Blah Blah" | Data Archive.doc | W:/Project A/Requirements | Admin | Admin | 5 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-13 | [5 empty] | 2016-01-20 | [5 empty] | 2016-01-27 | [5 empty] | 2016-02-17
91 | Administration: User Logon Restrictions | "Blah Blah Blah" | Administration.doc | W:/Project A/Requirements | Admin | Admin | 1 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-20 | [5 empty] | 2016-01-27 | [5 empty] | 2016-02-03 | [5 empty] | 2016-02-17
92 | Administration: Add Normal User | "Blah Blah Blah" | Administration.doc | W:/Project A/Requirements | Admin | Admin | 1 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-20 | [5 empty] | 2016-01-27 | [5 empty] | 2016-02-03 | [5 empty] | 2016-02-17
93 | Administration: Add Administrator User | "Blah Blah Blah" | Administration.doc | W:/Project A/Requirements | Admin | Admin | 1 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-20 | [5 empty] | 2016-01-27 | [5 empty] | 2016-02-03 | [5 empty] | 2016-02-17
94 | Administration: Remove Normal User | "Blah Blah Blah" | Administration.doc | W:/Project A/Requirements | Admin | Admin | 1 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-20 | [5 empty] | 2016-01-27 | [5 empty] | 2016-02-03 | [5 empty] | 2016-02-17
95 | Administration: Remove Administration User | "Blah Blah Blah" | Administration.doc | W:/Project A/Requirements | Admin | Admin | 1 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-20 | [5 empty] | 2016-01-27 | [5 empty] | 2016-02-03 | [5 empty] | 2016-02-17
96 | Administration: Reset User Password | "Blah Blah Blah" | Administration.doc | W:/Project A/Requirements | Admin | Admin | 1 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-27 | [5 empty] | 2016-02-03 | [5 empty] | 2016-02-10 | [5 empty] | 2016-02-17
97 | Administration: Initiate Backup Restore | "Blah Blah Blah" | Administration.doc | W:/Project A/Requirements | Admin | Admin | 1 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-27 | [5 empty] | 2016-02-03 | [5 empty] | 2016-02-10 | [5 empty] | 2016-02-17
98 | Administration: Initiate Report | "Blah Blah Blah" | Administration.doc | W:/Project A/Requirements | Admin | Admin | 1 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-27 | [5 empty] | 2016-02-03 | [5 empty] | 2016-02-10 | [5 empty] | 2016-02-17
99 | Administration: Override Invoice Price | "Blah Blah Blah" | Administration.doc | W:/Project A/Requirements | Admin | Admin | 1 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-27 | [5 empty] | 2016-02-03 | [5 empty] | 2016-02-10 | [5 empty] | 2016-02-17
100 | Administration: Override Invoice Total | "Blah Blah Blah" | Administration.doc | W:/Project A/Requirements | Admin | Admin | 1 | Emanual Blanco | Chris Andrews | Pending |  | N/A |  | N/A |  | N/A |  | 2016-01-27 | [5 empty] | 2016-02-03 | [5 empty] | 2016-02-10 | [5 empty] | 2016-02-17
Formulas:
Req. Comp. Date Actual = +[Scheduled]+(MOD(INT(RAND()*10),10)-5)
Req. Days off of Plan = DAYS([Req. Comp. Date Actual],[Scheduled])
Req. Days Early = IF([Req. Early/Late/OnTime]="Early",(DAYS([Req. Comp. Date Actual],[Scheduled])),0)
Req. Days Late = IF([Req. Early/Late/OnTime]="Late",(DAYS([Req. Comp. Date Actual],[Scheduled])),0)
Dev. Comp. Date Planned = +[Scheduled]+7
Dev. Comp. Date Actual = +[Dev. Comp. Date Planned]+(MOD(INT(RAND()*10),10)-5)
Dev. Days off of Plan = DAYS([Dev. Comp. Date Actual],[Dev. Comp. Date Planned])
Dev. Days Early = IF([Dev. Early/Late/OnTime]="Early",(DAYS([Dev. Comp. Date Actual],[Dev. Comp. Date Planned])),0)
Dev. Days Late = IF([Dev. Early/Late/OnTime]="Late",(DAYS([Dev. Comp. Date Actual],[Dev. Comp. Date Planned])),0)
Test Comp. Date Planned = +[Dev. Comp. Date Planned]+7
Test Comp. Date Actual = +[Test Comp. Date Planned]+(MOD(INT(RAND()*10),10)-5)
Test Days off of Plan = DAYS([Test Comp. Date Actual],[Test Comp. Date Planned])
Test Days Early = IF([Test Early/Late/OnTime]="Early",(DAYS([Test Comp. Date Actual],[Test Comp. Date Planned])),0)
Test Days Late = IF([Test Early/Late/OnTime]="Late",(DAYS([Test Comp. Date Actual],[Test Comp. Date Planned])),0)
Prod Date Actual = +[Prod Date Plammed]+(MOD(INT(RAND()*10),10)-5)
Prod Days off of Plan = DAYS([Prod Date Actual],[Prod Date Plammed])
Prod Days Early = IF([Prod Early/Late/OnTime]="Early",(DAYS([Prod Date Actual],[Prod Date Plammed])),0)
Prod Days Late = IF([Prod Early/Late/OnTime]="Late",(DAYS([Prod Date Actual],[Prod Date Plammed])),0)

## Test Case Req. Matrix
Requirement |  | Test Case |  | Notes
Requirement ID | Requirement Name | Test Case ID | Test Case Name | Notes | Comments | Issues
1 | Customer Data Load: ID | 1 | Customer Data Load: ID
2 | Customer Data Load: Last Name | 2 | Customer Data Load: Last Name
3 | Customer Data Load: First Name | 3 | Customer Data Load: First Name
4 | Customer Data Load: Street | 4 | Customer Data Load: Street
5 | Customer Data Load: City | 5 | Customer Data Load: City
6 | Customer Data Load: State | 6 | Customer Data Load: State
7 | Customer Data Load: ZIP | 7 | Customer Data Load: ZIP
8 | Customer Data Load: Phone | 8 | Customer Data Load: Phone
9 | Customer Data Load: Mobile | 9 | Customer Data Load: Mobile
10 | Customer Data Load: Fax | 10 | Customer Data Load: Fax
11 | Customer Pre-Process: Verify ID | 11 | Customer Pre-Process: Verify ID
12 | Customer Pre-Process: Merge to Existing Customer | 12 | Customer Pre-Process: Merge to Existing Customer
13 | Customer Pre-Process: Create New Customer | 13 | Customer Pre-Process: Create New Customer
14 | Customer Pre-Process: Calculate Region | 14 | Customer Pre-Process: Calculate Region
15 | Customer Pre-Process: Assign Sales Agent | 15 | Customer Pre-Process: Assign Sales Agent
16 | Customer Pre-Process: Balance Sales Agents | 16 | Customer Pre-Process: Balance Sales Agents
17 | Customer Pre-Process: Generate Customer List | 17 | Customer Pre-Process: Generate Customer List
18 | Customer Pre-Process: Set up Invoice Template | 18 | Customer Pre-Process: Set up Invoice Template
19 | Customer Pre-Process: Send Welcome Letter | 19 | Customer Pre-Process: Send Welcome Letter
20 | Customer Pre-Process: Merge to Existing Customer | 20 | Customer Pre-Process: Merge to Existing Customer
21 | Customer Maintence UI: Change Last Name | 21 | Customer Maintence UI: Change Last Name
22 | Customer Maintence UI: Change First Name | 22 | Customer Maintence UI: Change First Name
23 | Customer Maintence UI: Change Street | 23 | Customer Maintence UI: Change Street
24 | Customer Maintence UI: Change City | 24 | Customer Maintence UI: Change City
25 | Customer Maintence UI: Change State | 25 | Customer Maintence UI: Change State
26 | Customer Maintence UI: Change ZIP | 26 | Customer Maintence UI: Change ZIP
27 | Customer Maintence UI: Change Phone | 27 | Customer Maintence UI: Change Phone
28 | Customer Maintence UI: Change Mobile | 28 | Customer Maintence UI: Change Mobile
29 | Customer Maintence UI: Change Fax | 29 | Customer Maintence UI: Change Fax
30 | Customer Maintence UI: Save Changes | 30 | Customer Maintence UI: Save Changes
31 | Customer Reporting: Report 1 | 31 | Customer Reporting: Report 1
32 | Customer Reporting: Report 2 | 32 | Customer Reporting: Report 2
33 | Customer Reporting: Report 3 | 33 | Customer Reporting: Report 3
34 | Customer Reporting: Report 4 | 34 | Customer Reporting: Report 4
35 | Customer Reporting: Report 5 | 35 | Customer Reporting: Report 5
36 | Customer Reporting: Report 6 | 36 | Customer Reporting: Report 6
37 | Customer Reporting: Report 7 | 37 | Customer Reporting: Report 7
38 | Customer Reporting: Report 8 | 38 | Customer Reporting: Report 8
39 | Customer Reporting: Report 9 | 39 | Customer Reporting: Report 9
40 | Customer Reporting: Report 10 | 40 | Customer Reporting: Report 10
41 | Invoice/Billing UI: Attach new Invoice to Customer | 41 | Invoice/Billing UI: Attach new Invoice to Customer
42 | Invoice/Billing UI: Add Item | 42 | Invoice/Billing UI: Add Item
43 | Invoice/Billing UI: Remove Item | 43 | Invoice/Billing UI: Remove Item
44 | Invoice/Billing UI: Total Order | 44 | Invoice/Billing UI: Total Order
45 | Invoice/Billing UI: Calcualate Tax | 45 | Invoice/Billing UI: Calcualate Tax
46 | Invoice/Billing UI: Calculate Shipping | 46 | Invoice/Billing UI: Calculate Shipping
47 | Invoice/Billing UI: Visa Card Transaction | 47 | Invoice/Billing UI: Visa Card Transaction
48 | Invoice/Billing UI: Post Invoice | 48 | Invoice/Billing UI: Post Invoice
49 | Invoice/Billing UI: Cancel Invoice | 49 | Invoice/Billing UI: Cancel Invoice
50 | Invoice/Billing UI: Update Existing Invoice | 50 | Invoice/Billing UI: Update Existing Invoice
51 | Invoice Billing Financials: Daily Totals | 51 | Invoice Billing Financials: Daily Totals
52 | Invoice Billing Financials: Weekly Totals | 52 | Invoice Billing Financials: Weekly Totals
53 | Invoice Billing Financials: Monthly Totals | 53 | Invoice Billing Financials: Monthly Totals
54 | Invoice Billing Financials: Quarterly Totals | 54 | Invoice Billing Financials: Quarterly Totals
55 | Invoice Billing Financials: Yearly Totals | 55 | Invoice Billing Financials: Yearly Totals
56 | Invoice Billing Financials: Quarterly Tax Due | 56 | Invoice Billing Financials: Quarterly Tax Due
57 | Invoice Billing Financials: Quarterly Profit | 57 | Invoice Billing Financials: Quarterly Profit
58 | Invoice Billing Financials: Quarterly Unpaid | 58 | Invoice Billing Financials: Quarterly Unpaid
59 | Invoice Billing Financials: Yearly Profit | 59 | Invoice Billing Financials: Yearly Profit
60 | Invoice Billing Financials: Yearly Loss | 60 | Invoice Billing Financials: Yearly Loss
61 | Invoice Billing Mailings: Mail Invoice | 61 | Invoice Billing Mailings: Mail Invoice
62 | Invoice Billing Mailings: Mail First Late Notice | 62 | Invoice Billing Mailings: Mail First Late Notice
63 | Invoice Billing Mailings: Mail Second Late Notice | 63 | Invoice Billing Mailings: Mail Second Late Notice
64 | Invoice Billing Mailings: Mail Payment Thank You | 64 | Invoice Billing Mailings: Mail Payment Thank You
65 | Invoice Billing Mailings: Mail Monthly Recap | 65 | Invoice Billing Mailings: Mail Monthly Recap
66 | Invoice Billing Mailings: Mail Catalogs | 66 | Invoice Billing Mailings: Mail Catalogs
67 | Invoice Billing Mailings: Calculate Postage | 67 | Invoice Billing Mailings: Calculate Postage
68 | Invoice Billing Mailings: Calculate Foreign Postage | 68 | Invoice Billing Mailings: Calculate Foreign Postage
69 | Invoice Billing Mailings: Process Returned Mail | 69 | Invoice Billing Mailings: Process Returned Mail
70 | Invoice Billing Mailings: Pay Postage Charges | 70 | Invoice Billing Mailings: Pay Postage Charges
71 | Invoice Reporting: Report 1 | 71 | Invoice Reporting: Report 1
72 | Invoice Reporting: Report 2 | 72 | Invoice Reporting: Report 2
73 | Invoice Reporting: Report 3 | 73 | Invoice Reporting: Report 3
74 | Invoice Reporting: Report 4 | 74 | Invoice Reporting: Report 4
75 | Invoice Reporting: Report 5 | 75 | Invoice Reporting: Report 5
76 | Invoice Reporting: Report 6 | 76 | Invoice Reporting: Report 6
77 | Invoice Reporting: Report 7 | 77 | Invoice Reporting: Report 7
78 | Invoice Reporting: Report 8 | 78 | Invoice Reporting: Report 8
79 | Invoice Reporting: Report 9 | 79 | Invoice Reporting: Report 9
80 | Invoice Reporting: Report 10 | 80 | Invoice Reporting: Report 10
81 | Data Archive: Customer | 81 | Data Archive: Customer
82 | Data Archive: Invoice | 82 | Data Archive: Invoice
83 | Data Archive: Hourly | 83 | Data Archive: Hourly
84 | Data Archive: Daily | 84 | Data Archive: Daily
85 | Data Archive: Weekly | 85 | Data Archive: Weekly
86 | Data Archive: Quarterly | 86 | Data Archive: Quarterly
87 | Data Archive: Yearly | 87 | Data Archive: Yearly
88 | Data Archive: Retreive Backup | 88 | Data Archive: Retreive Backup
89 | Data Archive: Apply Backup | 89 | Data Archive: Apply Backup
90 | Data Archive: Verify Backup | 90 | Data Archive: Verify Backup
91 | Administration: User Logon Restrictions | 91 | Administration: User Logon Restrictions
92 | Administration: Add Normal User | 92 | Administration: Add Normal User
93 | Administration: Add Administrator User | 93 | Administration: Add Administrator User
94 | Administration: Remove Normal User | 94 | Administration: Remove Normal User
95 | Administration: Remove Administration User | 95 | Administration: Remove Administration User
96 | Administration: Reset User Password | 96 | Administration: Reset User Password
97 | Administration: Initiate Backup Restore | 97 | Administration: Initiate Backup Restore
98 | Administration: Initiate Report | 98 | Administration: Initiate Report
99 | Administration: Override Invoice Price | 99 | Administration: Override Invoice Price
100 | Administration: Override Invoice Total | 100 | Administration: Override Invoice Total

## Test Case Plan
Identification |  |  |  |  | Baseline | [7 empty] | Execution/Hours | 8 | 150% | 100% | 25% | 75% |  | Status |  |  |  | Schedule | Research |  | 2 |  |  | 1 | Design | 1 | 4 |  |  | 2 | Development | 1 | 4 |  |  | 2 | Data | 1 | 2 |  |  | 4 | Execution | 1 | 2 |  |  | 4 | Defect | 1 | 4 |  |  | 1 |  |  |  |  | Actual | Research |  |  |  |  | Design |  |  |  |  | Development |  |  |  |  | Data |  |  |  |  | Execution |  |  |  |  | Defect | [7 empty] | Notes
ID | Name | Business Area | Functional Area | Step | Original Plan | Added | Added Date | Added Reason | Deleted | Delete Date | Delete Reason | Associated Test Case ID | Test Run Type | Design | Develop | Data | Execution | Defect | Total | Status | Open Step | Hold Step | Hold Reason | Start Date | Tester | Start Date/Time | End Date/Time | Work Days | Calendar Days | Hours | Tester | Start Date/Time | End Date/Time | Work Days | Calendar Days | Hours | Tester | Start Date/Time | End Date/Time | Work Days | Calendar Days | Hours | Tester | Start Date/Time | End Date/Time | Work Days | Calendar Days | Hours | Tester | Start Date/Time | End Date/Time | Work Days | Calendar Days | Hours | Tester | Start Date/Time | End Date/Time | Work Days | Calendar Days | Hours | Close Date | Work Days | Calendar Days | Hours | Start Date | Tester | Start Date/Time | End Date/Time | Calendar Days | Hours | Tester | Start Date/Time | End Date/Time | Calendar Days | Hours | Tester | Start Date/Time | End Date/Time | Calendar Days | Hours | Tester | Start Date/Time | End Date/Time | Calendar Days | Hours | Tester | Start Date/Time | End Date/Time | Calendar Days | Hours | Tester | Start Date/Time | End Date/Time | Calendar Days | Hours | Close Date | Calendar Days | Hours | Notes | Comments | Issues
1 | Customer Data Load: ID | Customer | Calculation | SIT | Yes | [7 empty] | Batch | 8 | 12 | 8 | 2 | 6 | 36 |  |  |  |  | 2016-09-15 | Tester 1 | 2016-09-15 | 2016-09-16 | 2 | 2 | 8 |  | 2016-09-19 | 2016-09-19 | 1 | 1 | 12 |  | 2016-09-20 | 2016-09-21 | 2 | 2 | 4 |  | 2016-09-21 | 2016-09-21 | 1 | 1 | 4 |  | 2016-09-22 | 2016-09-22 | 1 | 1 | 4 |  | 2016-09-29 | 2016-09-29 | 1 | 1 | 1 | 2016-09-29 | 11 | 15 | 33
2 | Customer Data Load: Last Name | Customer | Data | SIT | Yes | [7 empty] | Batch | 3 | 4.5 | 3 | 0.75 | 2.25 | 13.5 |  |  |  |  | 2016-09-19 | Tester 2
3 | Customer Data Load: First Name | Customer | Data | SIT | Yes | [7 empty] | Batch | 3 | 4.5 | 3 | 0.75 | 2.25 | 13.5 |  |  |  |  | 2016-09-14 | Tester 3
4 | Customer Data Load: Street | Customer | Data | SIT | Yes | [7 empty] | Batch | 3 | 4.5 | 3 | 0.75 | 2.25 | 13.5 |  |  |  |  | 2016-09-12 | Tester 4
5 | Customer Data Load: City | Customer | Data | SIT | Yes | [7 empty] | Batch | 4 | 6 | 4 | 1 | 3 | 18 |  |  |  |  | 2016-09-19 | Tester 5
6 | Customer Data Load: State | Customer | Data | SIT | Yes | [7 empty] | Batch | 6 | 9 | 6 | 1.5 | 4.5 | 27 |  |  |  |  | 2016-09-21 | Tester 1
7 | Customer Data Load: ZIP | Customer | Data | SIT | Yes | [7 empty] | Batch | 8 | 12 | 8 | 2 | 6 | 36 |  |  |  |  | 2016-09-20 | Tester 2
8 | Customer Data Load: Phone | Customer | Data | SIT | Yes | [7 empty] | Batch | 7 | 10.5 | 7 | 1.75 | 5.25 | 31.5 |  |  |  |  | 2016-09-26 | Tester 3
9 | Customer Data Load: Mobile | Customer | Data | SIT | Yes | [7 empty] | Batch | 3 | 4.5 | 3 | 0.75 | 2.25 | 13.5 |  |  |  |  | 2016-09-19 | Tester 4
10 | Customer Data Load: Fax | Customer | Data | SIT | Yes |  |  |  | Yes |  |  |  | Batch | 7 | 10.5 | 7 | 1.75 | 5.25 | 31.5 |  |  |  |  | 2016-09-26 | Tester 5
11 | Customer Pre-Process: Verify ID | Customer | Code | SIT | Yes | [7 empty] | Automated | 4 | 6 | 4 | 1 | 3 | 18 |  |  |  |  | 2016-10-05 | Tester 1
12 | Customer Pre-Process: Merge to Existing Customer | Customer | Data | SIT | Yes | [7 empty] | Automated | 6 | 9 | 6 | 1.5 | 4.5 | 27 |  |  |  |  | 2016-09-27 | Tester 2
13 | Customer Pre-Process: Create New Customer | Customer | Code | SIT | Yes | [7 empty] | Automated | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-10-05 | Tester 3
14 | Customer Pre-Process: Calculate Region | Customer | Calculation | SIT | Yes | [7 empty] | Automated | 6 | 9 | 6 | 1.5 | 4.5 | 27 |  |  |  |  | 2016-10-05 | Tester 4
15 | Customer Pre-Process: Assign Sales Agent | Customer | Code | SIT | Yes | [7 empty] | Automated | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-09-27 | Tester 5
16 | Customer Pre-Process: Balance Sales Agents | Customer | Code | SIT | Yes | [7 empty] | Automated | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-10-12 | Tester 1
17 | Customer Pre-Process: Generate Customer List | Customer | Code | SIT | Yes | [7 empty] | Automated | 4 | 6 | 4 | 1 | 3 | 18 |  |  |  |  | 2016-10-10 | Tester 2
18 | Customer Pre-Process: Set up Invoice Template | Customer | Code | SIT | Yes | [7 empty] | Automated | 9 | 13.5 | 9 | 2.25 | 6.75 | 40.5 |  |  |  |  | 2016-10-10 | Tester 3
19 | Customer Pre-Process: Send Welcome Letter | Customer | Code | SIT | Yes | [7 empty] | Automated | 3 | 4.5 | 3 | 0.75 | 2.25 | 13.5 |  |  |  |  | 2016-10-07 | Tester 4
20 | Customer Pre-Process: Merge to Existing Customer | Customer | Data | SIT | Yes |  |  |  | Yes |  |  |  | Automated | 2 | 3 | 2 | 0.5 | 1.5 | 9 |  |  |  |  | 2016-10-04 | Tester 5
21 | Customer Maintence UI: Change Last Name | UI | UI | SIT | Yes | [7 empty] | Manual | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-10-17 | Tester 1
22 | Customer Maintence UI: Change First Name | UI | UI | SIT | Yes | [7 empty] | Manual | 2 | 3 | 2 | 0.5 | 1.5 | 9 |  |  |  |  | 2016-10-13 | Tester 2
23 | Customer Maintence UI: Change Street | UI | UI | SIT | Yes | [7 empty] | Manual | 2 | 3 | 2 | 0.5 | 1.5 | 9 |  |  |  |  | 2016-10-19 | Tester 3
24 | Customer Maintence UI: Change City | UI | UI | SIT | Yes | [7 empty] | Manual | 6 | 9 | 6 | 1.5 | 4.5 | 27 |  |  |  |  | 2016-10-19 | Tester 4
25 | Customer Maintence UI: Change State | UI | UI | SIT | Yes | [7 empty] | Manual | 9 | 13.5 | 9 | 2.25 | 6.75 | 40.5 |  |  |  |  | 2016-10-19 | Tester 5
26 | Customer Maintence UI: Change ZIP | UI | UI | SIT | Yes | [7 empty] | Manual | 8 | 12 | 8 | 2 | 6 | 36 |  |  |  |  | 2016-10-21 | Tester 1
27 | Customer Maintence UI: Change Phone | UI | UI | SIT | Yes | [7 empty] | Manual | 9 | 13.5 | 9 | 2.25 | 6.75 | 40.5 |  |  |  |  | 2016-10-24 | Tester 2
28 | Customer Maintence UI: Change Mobile | UI | UI | SIT | Yes | [7 empty] | Manual | 6 | 9 | 6 | 1.5 | 4.5 | 27 |  |  |  |  | 2016-10-25 | Tester 3
29 | Customer Maintence UI: Change Fax | UI | UI | SIT | Yes | [7 empty] | Manual | 2 | 3 | 2 | 0.5 | 1.5 | 9 |  |  |  |  | 2016-10-21 | Tester 4
30 | Customer Maintence UI: Save Changes | UI | UI | SIT | Yes |  |  |  | Yes |  |  |  | Manual | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-10-21 | Tester 5
31 | Customer Reporting: Report 1 | Reports | UI | SIT | Yes | [7 empty] | Manual | 8 | 12 | 8 | 2 | 6 | 36 |  |  |  |  | 2016-10-31 | Tester 1
32 | Customer Reporting: Report 2 | Reports | UI | SIT | Yes | [7 empty] | Manual | 7 | 10.5 | 7 | 1.75 | 5.25 | 31.5 |  |  |  |  | 2016-10-25 | Tester 2
33 | Customer Reporting: Report 3 | Reports | UI | SIT | Yes | [7 empty] | Manual | 8 | 12 | 8 | 2 | 6 | 36 |  |  |  |  | 2016-11-02 | Tester 3
34 | Customer Reporting: Report 4 | Reports | UI | SIT | Yes | [7 empty] | Manual | 8 | 12 | 8 | 2 | 6 | 36 |  |  |  |  | 2016-10-27 | Tester 4
35 | Customer Reporting: Report 5 | Reports | UI | SIT | Yes | [7 empty] | Manual | 8 | 12 | 8 | 2 | 6 | 36 |  |  |  |  | 2016-10-26 | Tester 5
36 | Customer Reporting: Report 6 | Reports | UI | SIT | Yes | [7 empty] | Manual | 3 | 4.5 | 3 | 0.75 | 2.25 | 13.5 |  |  |  |  | 2016-11-07 | Tester 1
37 | Customer Reporting: Report 7 | Reports | UI | SIT | Yes | [7 empty] | Manual | 7 | 10.5 | 7 | 1.75 | 5.25 | 31.5 |  |  |  |  | 2016-11-07 | Tester 2
38 | Customer Reporting: Report 8 | Reports | UI | SIT | Yes | [7 empty] | Manual | 4 | 6 | 4 | 1 | 3 | 18 |  |  |  |  | 2016-11-07 | Tester 3
39 | Customer Reporting: Report 9 | Reports | UI | SIT | Yes | [7 empty] | Manual | 4 | 6 | 4 | 1 | 3 | 18 |  |  |  |  | 2016-11-07 | Tester 4
40 | Customer Reporting: Report 10 | Financial | Calculation | SIT | Yes | [7 empty] | Manual | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-11-07 | Tester 5
41 | Invoice/Billing UI: Attach new Invoice to Customer | UI | UI | SIT | Yes | [7 empty] | Manual | 4 | 6 | 4 | 1 | 3 | 18 |  |  |  |  | 2016-11-14 | Tester 1
42 | Invoice/Billing UI: Add Item | UI | UI | SIT | Yes | [7 empty] | Manual | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-11-14 | Tester 2
43 | Invoice/Billing UI: Remove Item | UI | UI | SIT | Yes | [7 empty] | Manual | 8 | 12 | 8 | 2 | 6 | 36 |  |  |  |  | 2016-11-14 | Tester 3
44 | Invoice/Billing UI: Total Order | Financial | Calculation | SIT | Yes | [7 empty] | Manual | 4 | 6 | 4 | 1 | 3 | 18 |  |  |  |  | 2016-11-14 | Tester 4
45 | Invoice/Billing UI: Calcualate Tax | Financial | Calculation | SIT | Yes | [7 empty] | Manual | 2 | 3 | 2 | 0.5 | 1.5 | 9 |  |  |  |  | 2016-11-14 | Tester 5
46 | Invoice/Billing UI: Calculate Shipping | Financial | Calculation | SIT | Yes | [7 empty] | Manual | 9 | 13.5 | 9 | 2.25 | 6.75 | 40.5 |  |  |  |  | 2016-11-21 | Tester 1
47 | Invoice/Billing UI: Visa Card Transaction | UI | UI | SIT | Yes | [7 empty] | Manual | 7 | 10.5 | 7 | 1.75 | 5.25 | 31.5 |  |  |  |  | 2016-11-21 | Tester 2
48 | Invoice/Billing UI: Post Invoice | UI | UI | SIT | Yes | [7 empty] | Manual | 2 | 3 | 2 | 0.5 | 1.5 | 9 |  |  |  |  | 2016-11-21 | Tester 3
49 | Invoice/Billing UI: Cancel Invoice | UI | UI | SIT | Yes | [7 empty] | Manual | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-11-21 | Tester 4
50 | Invoice/Billing UI: Update Existing Invoice | UI | UI | SIT | Yes | [7 empty] | Manual | 9 | 13.5 | 9 | 2.25 | 6.75 | 40.5 |  |  |  |  | 2016-11-21 | Tester 5
51 | Invoice Billing Financials: Daily Totals | Billing | Code | SIT | Yes | [7 empty] | Automated | 2 | 3 | 2 | 0.5 | 1.5 | 9 |  |  |  |  | 2016-11-28 | Tester 1
52 | Invoice Billing Financials: Weekly Totals | Billing | Code | SIT | Yes | [7 empty] | Automated | 9 | 13.5 | 9 | 2.25 | 6.75 | 40.5 |  |  |  |  | 2016-11-28 | Tester 2
53 | Invoice Billing Financials: Monthly Totals | Billing | Code | SIT | Yes | [7 empty] | Automated | 8 | 12 | 8 | 2 | 6 | 36 |  |  |  |  | 2016-11-28 | Tester 3
54 | Invoice Billing Financials: Quarterly Totals | Billing | Code | SIT | Yes | [7 empty] | Automated | 9 | 13.5 | 9 | 2.25 | 6.75 | 40.5 |  |  |  |  | 2016-11-28 | Tester 4
55 | Invoice Billing Financials: Yearly Totals | Billing | Code | SIT | Yes | [7 empty] | Automated | 4 | 6 | 4 | 1 | 3 | 18 |  |  |  |  | 2016-11-28 | Tester 5
56 | Invoice Billing Financials: Quarterly Tax Due | Billing | Code | SIT | Yes | [7 empty] | Automated | 2 | 3 | 2 | 0.5 | 1.5 | 9 |  |  |  |  | 2016-12-05 | Tester 1
57 | Invoice Billing Financials: Quarterly Profit | Financial | Calculation | SIT | Yes | [7 empty] | Automated | 6 | 9 | 6 | 1.5 | 4.5 | 27 |  |  |  |  | 2016-12-05 | Tester 2
58 | Invoice Billing Financials: Quarterly Unpaid | Billing | Code | SIT | Yes | [7 empty] | Automated | 3 | 4.5 | 3 | 0.75 | 2.25 | 13.5 |  |  |  |  | 2016-12-05 | Tester 3
59 | Invoice Billing Financials: Yearly Profit | Financial | Calculation | SIT | Yes | [7 empty] | Automated | 9 | 13.5 | 9 | 2.25 | 6.75 | 40.5 |  |  |  |  | 2016-12-05 | Tester 4
60 | Invoice Billing Financials: Yearly Loss | Billing | Code | SIT | Yes | [7 empty] | Automated | 3 | 4.5 | 3 | 0.75 | 2.25 | 13.5 |  |  |  |  | 2016-12-05 | Tester 5
61 | Invoice Billing Mailings: Mail Invoice | Billing | Code | SIT | Yes | [7 empty] | Manual | 6 | 9 | 6 | 1.5 | 4.5 | 27 |  |  |  |  | 2016-12-12 | Tester 1
62 | Invoice Billing Mailings: Mail First Late Notice | Billing | Code | SIT | Yes | [7 empty] | Manual | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-12-12 | Tester 2
63 | Invoice Billing Mailings: Mail Second Late Notice | Billing | Code | SIT | Yes | [7 empty] | Manual | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-12-12 | Tester 3
64 | Invoice Billing Mailings: Mail Payment Thank You | Billing | Code | SIT | Yes | [7 empty] | Manual | 3 | 4.5 | 3 | 0.75 | 2.25 | 13.5 |  |  |  |  | 2016-12-12 | Tester 4
65 | Invoice Billing Mailings: Mail Monthly Recap | Billing | Code | SIT | Yes | [7 empty] | Manual | 6 | 9 | 6 | 1.5 | 4.5 | 27 |  |  |  |  | 2016-12-12 | Tester 5
66 | Invoice Billing Mailings: Mail Catalogs | Billing | Code | SIT | Yes | [7 empty] | Manual | 7 | 10.5 | 7 | 1.75 | 5.25 | 31.5 |  |  |  |  | 2016-12-19 | Tester 1
67 | Invoice Billing Mailings: Calculate Postage | Billing | Code | SIT | Yes | [7 empty] | Manual | 6 | 9 | 6 | 1.5 | 4.5 | 27 |  |  |  |  | 2016-12-19 | Tester 2
68 | Invoice Billing Mailings: Calculate Foreign Postage | Billing | Code | SIT | Yes | [7 empty] | Manual | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-12-19 | Tester 3
69 | Invoice Billing Mailings: Process Returned Mail | Billing | Code | SIT | Yes | [7 empty] | Manual | 8 | 12 | 8 | 2 | 6 | 36 |  |  |  |  | 2016-12-19 | Tester 4
70 | Invoice Billing Mailings: Pay Postage Charges | Billing | Code | SIT | Yes | [7 empty] | Manual | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-12-19 | Tester 5
71 | Invoice Reporting: Report 1 | Reports | UI | SIT | Yes | [7 empty] | Manual | 9 | 13.5 | 9 | 2.25 | 6.75 | 40.5 |  |  |  |  | 2016-12-26 | Tester 1
72 | Invoice Reporting: Report 2 | Reports | UI | SIT | Yes | [7 empty] | Manual | 6 | 9 | 6 | 1.5 | 4.5 | 27 |  |  |  |  | 2016-12-26 | Tester 2
73 | Invoice Reporting: Report 3 | Reports | UI | SIT | Yes | [7 empty] | Manual | 6 | 9 | 6 | 1.5 | 4.5 | 27 |  |  |  |  | 2016-12-26 | Tester 3
74 | Invoice Reporting: Report 4 | Reports | UI | SIT | Yes | [7 empty] | Manual | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-12-26 | Tester 4
75 | Invoice Reporting: Report 5 | Reports | UI | SIT | Yes | [7 empty] | Manual | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-12-26 | Tester 5
76 | Invoice Reporting: Report 6 | Reports | UI | SIT | Yes | [7 empty] | Manual | 7 | 10.5 | 7 | 1.75 | 5.25 | 31.5 |  |  |  |  | 2017-01-02 | Tester 1
77 | Invoice Reporting: Report 7 | Reports | UI | SIT | Yes | [7 empty] | Manual | 9 | 13.5 | 9 | 2.25 | 6.75 | 40.5 |  |  |  |  | 2017-01-02 | Tester 2
78 | Invoice Reporting: Report 8 | Financial | Calculation | SIT | Yes | [7 empty] | Manual | 4 | 6 | 4 | 1 | 3 | 18 |  |  |  |  | 2017-01-02 | Tester 3
79 | Invoice Reporting: Report 9 | Financial | Calculation | SIT | Yes | [7 empty] | Manual | 6 | 9 | 6 | 1.5 | 4.5 | 27 |  |  |  |  | 2017-01-02 | Tester 4
80 | Invoice Reporting: Report 10 | Financial | Calculation | SIT | Yes | [7 empty] | Manual | 6 | 9 | 6 | 1.5 | 4.5 | 27 |  |  |  |  | 2017-01-02 | Tester 5
81 | Data Archive: Customer | Admin | Data | SIT | Yes | [7 empty] | Batch | 3 | 4.5 | 3 | 0.75 | 2.25 | 13.5 |  |  |  |  | 2016-01-14 | Tester 1
82 | Data Archive: Invoice | Admin | Data | SIT | Yes | [7 empty] | Batch | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-01-14 | Tester 2
83 | Data Archive: Hourly | Admin | Data | SIT | Yes | [7 empty] | Batch | 4 | 6 | 4 | 1 | 3 | 18 |  |  |  |  | 2016-01-14 | Tester 3
84 | Data Archive: Daily | Admin | Data | SIT | Yes | [7 empty] | Batch | 4 | 6 | 4 | 1 | 3 | 18 |  |  |  |  | 2016-01-14 | Tester 4
85 | Data Archive: Weekly | Admin | Data | SIT | Yes | [7 empty] | Batch | 7 | 10.5 | 7 | 1.75 | 5.25 | 31.5 |  |  |  |  | 2016-01-14 | Tester 5
86 | Data Archive: Quarterly | Admin | Data | SIT | Yes | [7 empty] | Batch | 4 | 6 | 4 | 1 | 3 | 18 |  |  |  |  | 2016-01-21 | Tester 1
87 | Data Archive: Yearly | Admin | Data | SIT | Yes | [7 empty] | Batch | 3 | 4.5 | 3 | 0.75 | 2.25 | 13.5 |  |  |  |  | 2016-01-21 | Tester 2
88 | Data Archive: Retreive Backup | Admin | Data | SIT | Yes | [7 empty] | Batch | 9 | 13.5 | 9 | 2.25 | 6.75 | 40.5 |  |  |  |  | 2016-01-21 | Tester 3
89 | Data Archive: Apply Backup | Admin | Data | SIT | Yes | [7 empty] | Batch | 2 | 3 | 2 | 0.5 | 1.5 | 9 |  |  |  |  | 2016-01-21 | Tester 4
90 | Data Archive: Verify Backup | Admin | Data | SIT | Yes | [7 empty] | Batch | 7 | 10.5 | 7 | 1.75 | 5.25 | 31.5 |  |  |  |  | 2016-01-21 | Tester 5
91 | Administration: User Logon Restrictions | Admin | Code | SIT | Yes | [7 empty] | Manual | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-01-28 | Tester 1
92 | Administration: Add Normal User | Admin | Code | SIT | Yes | [7 empty] | Manual | 6 | 9 | 6 | 1.5 | 4.5 | 27 |  |  |  |  | 2016-01-28 | Tester 2
93 | Administration: Add Administrator User | Admin | Code | SIT | Yes | [7 empty] | Manual | 2 | 3 | 2 | 0.5 | 1.5 | 9 |  |  |  |  | 2016-01-28 | Tester 3
94 | Administration: Remove Normal User | Admin | Code | SIT | Yes | [7 empty] | Manual | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-01-28 | Tester 4
95 | Administration: Remove Administration User | Admin | Code | SIT | Yes | [7 empty] | Manual | 7 | 10.5 | 7 | 1.75 | 5.25 | 31.5 |  |  |  |  | 2016-01-28 | Tester 5
96 | Administration: Reset User Password | Admin | Code | SIT | Yes | [7 empty] | Manual | 9 | 13.5 | 9 | 2.25 | 6.75 | 40.5 |  |  |  |  | 2016-02-04 | Tester 1
97 | Administration: Initiate Backup Restore | Admin | Code | SIT | Yes | [7 empty] | Manual | 9 | 13.5 | 9 | 2.25 | 6.75 | 40.5 |  |  |  |  | 2016-02-04 | Tester 2
98 | Administration: Initiate Report | Admin | Code | SIT | Yes | [7 empty] | Manual | 5 | 7.5 | 5 | 1.25 | 3.75 | 22.5 |  |  |  |  | 2016-02-04 | Tester 3
99 | Administration: Override Invoice Price | Admin | Code | SIT | Yes | [7 empty] | Manual | 9 | 13.5 | 9 | 2.25 | 6.75 | 40.5 |  |  |  |  | 2016-02-04 | Tester 4
100 | Administration: Override Invoice Total | Admin | Code | SIT | Yes | [7 empty] | Manual | 9 | 13.5 | 9 | 2.25 | 6.75 | 40.5 |  |  |  |  | 2016-02-04 | Tester 5
Formulas:
Start Date/Time = +[Start Date]
Start Date/Time = WORKDAY([Start Date],(([Design]+[Develop]-1)/7))
End Date/Time = WORKDAY([Start Date],([Design]/7))
End Date/Time = WORKDAY([Start Date],(([Design]+[Develop])/7))
Work Days = NETWORKDAYS([Start Date/Time],[End Date/Time])
Work Days = NETWORKDAYS([Start Date],[Close Date])
Calendar Days = DAYS([End Date/Time],[Start Date/Time])+1
Calendar Days = DAYS([Close Date],[Start Date])+1
Close Date = +[End Date/Time]

## Executions
Identification |  |  | Status | [10 empty] | Notes
ID | Name | Execution Number | Status | Blocked Reason | Start Date/Time | End Date/Time | Calendar Days | Hours | Pass/Fail | Fail Reason | Fail Notes | Tester | Developer | Notes | Comments | Issues